## Slide 1
Quinn Peterson
Decay Pipe Windows FDR
26 June 2024
Decay Pipe Windows Final Design Review

## Slide 2: Topics
LBNF/DUNE Intro
  Beamline and NSCF are currently preparing for baselining/early procurements (CD2/3)
Decay Pipe Windows review
Charge Questions
Decay Window Overview
  EDMS Requirements
Interfaces
Risks
Schedule
01/25/24 Peer Review
DSDP Window
  Design
USDP Window
  Design
  Cost
  Installation
  QA/QC
Notes: Switch Peer Review to after schedule

## Slide 3: DUNE & LBNF
The Deep Underground Neutrino Experiment will be a world-leading experiment for neutrino science, potentially transforming our understanding of why the universe exists as it does.
The Long-Baseline Neutrino Facility is the infrastructure necessary to send a powerful beam of neutrinos 800 miles through the earth, and measure them deep underground at South Dakota’s Sanford Underground Research Facility.
DUNE/LBNF project will be the first internationally conceived, constructed, and operated mega-science project hosted by the DOE in the U.S.
The beamline is designed to commission at 1.2MW and increase to 2.4MW
06.26.24

## Slide 4: WBS 131.NSCFB.03.04 Scope
Absorber Complex
(LBNF-30)
Target
Complex
(LBNF-20)
Primary Beam Service Building
(LBNF-5)
Decay Region
Primary
Beamline
Enclosure
Fermilab
Main Injector
Tunnel
Proton Beam
From MI-10
Neutrino Beam
to SURF, SD
Extraction
Enclosure
Major
Vehicle
Access
Includes the Absorber, Instrumentation,
DS end of Decay pipe
Includes the US Decay Pipe window
The Primary beam window, Instrumentation
Focus of this review – Bulk Shielding in the Target Hall
06.26.24

## Slide 5: Decay Pipe Windows Final Design Review
Technical Peer Review Conducted January 25, 2024
  Committee: Patrick Hurh, Kris Anderson, Kavin Ammigan
The design of the Decay Pipe windows is ready for final design review
  Technical Peer review recommendations have been addressed or are close to completion
  Drawings are done
  The design is sufficiently mature
The Upstream Decay Pipe Window is being designed, procured, and fabricated and installed under the Beamline Scope.
The Downstream Decay Pipe Window is being designed and installed by CF as part of the Decay Pipe System. Beamline Scope is to provide a thermal/structural analysis including beam energy deposition to be appended to the AECOM FESHM 5031.5 engineering note and will be included as part of the FESHM Peer Review.
Note that the Upstream Decay Pipe Window and associated documentation refer to and rely in part on the design of a Remote Exchange Mechanism, however, this mechanism is outside of the scope of this review
This review will help to confirm our design choices, cost and schedule
06.26.24

## Slide 6: Charge Questions
Do the design choices satisfy the requirements?
Have all engineering analyses been performed and documented, and reviewed/peer reviewed and approved, where applicable? Does it meet FESHM standards?
  Are all 2D/3D mechanical model drawings complete and documented?
  Is there a centrally maintained, accessible to all, CAD assembly model with the appropriate level of detail needed for an integration model?
Have all lessons learned been incorporated into the final design?
Have the ESH issues been identified and analyzed appropriately?
Are installation, and testing plans in development?
  Have sufficient resources for installation and testing been identified?
Do project planning materials including interface documents, QA/QC plans, risk assessments, schedules, and cost estimates exist at a sufficient level of development for this stage of the design?
Have all recommendations from previous reviews been adequately addressed and approved by the relevant authority?
Has a peer review been done on the analysis?
06.26.24
Charge #

## Slide 7: Decay Windows Overview
USDP Window
DSDP Window
Comprises a Low Press Vessel Per FESHM 5031.5

## Slide 8: DSDP Window Overview
As this “Window” design is a weldment on the downstream end of the Decay Pipe, this assembly is considered a part of the pressure vessel and is designed, installed and tested by AECOM.
Beamline is responsible for providing design requirements and Thermal/Structural analysis to include beam loading on the window for design validation
Designed for 2.4MW Operation as this cannot be upgraded
DSDP Window

## Slide 9: USDP Window Overview
1.8m Diameter Al-6061-T6 aluminum window provided by Beamline to be installed at the Upstream Decay Pipe Snout Flange.
This is designed as a removable window separate from the Decay Pipe and a separate engineering note will be generated and attached to the AECOM note.
The flange defines the line that separates the Beamline deliverable USDP Window from the CF provided Decay Pipe structure at the USDP Decay Pipe Snout
Designed for 1.2MW but should survive 2.4MW operation
USDP Window
USDP Snout Flange

## Slide 10: Decay Windows Overview
Requirements:
USDP Window:
  1. Shall be replaceable consistent with safety practices
  2. Shall incorporate best practices to maximize lifetime
  3. Shall have a maximum leak rate of 200 cubic feet helium per year
  4. Shall be transparent to the beam as conventionally possible while meeting accepted engineering standards for pressure safety and facility lifetime requirements
  5. Shall minimize decay pipe helium loss when a window replacement is required
    Requirement 5 falls under the scope of the Remote Exchange Mechanism and will be reviewed during its FDR
DSDP Window:
  1. Shall be designed such that it will not require replacement
  2. Shall incorporate best practices to maximize lifetime and consider corrosion in addition to thermal and pressure
Absorber:
  The absorber shall sustain at least 2 successive accident beam pulses without damage to components or loss of functional ability
    While this is not a Decay Windows requirement, the windows must be able to sustain the accident case as well
    Accident case is defined as No-Target beam activation.

## Slide 11: Decay Windows Beamline Interfaces
Beam Windows Interfaces: ICD’s 20, 21, 30, 41, 61, 73, 122, 171
Charge 6

## Slide 12: Decay Windows Interfaces
Beamline Interfaces:
20: BW to TH Shield Pile
21: BW to RAW Water System
30: BW to Remote Handling
41: BW to Controls
61: BW to Alignment
73: BW To Installation Coordination
122: BW to MARS Modeling
171: BW to Decay Pipe
All interfaces checked and approved by system owners
CF Interface:
NSCF to Decay Pipe
  Controlled in separate document than Beamline Interfaces. (Located docdb-31052)
  Signed off by NSCF and Beamline
Charge 6
Notes: Remove color coding and refer to everything has checked and approved by owners

## Slide 13: Decay Windows Risks
Engineering Risk Assessment
Risk Register
  Manufacturing/Procurement Issues
    Contingency: 3mm thick USDP Window
Charge 4, 6

## Slide 14: Schedule
Procurement of USDP Window
Procurement of USDP Window Spare
Install of USDP Window
Charge 6

## Slide 15: January Technical Peer Review Recommendations
Technical Peer Review 01/25/24
  Reviewers: Patrick Hurh, Kris Anderson, Kavin Ammigan
Downstream Decay Pipe Window
  1. Evaluate and address comments on window materials and weld requirements with CF
Upstream Decay Pipe Window
  2. Re-design the USDP as a one-piece machined window and flange
  3. repeat analysis with one-piece design geometry and apply updated parameters
  4. Perform in-depth bolted joint engineering design/analysis
    Account for differential thermal expansion
    Evaluate impact of clamping to a non-flat snout flange surface
  5. Consider using the flange seal leak check mock-up to test impact thermal cucling of the snout flange on the seal quality
  6. Consider adding a permanent water-cooling line on the snout flange to keep USDPW seal joint/flanges a more uniform and lower temperature
Rec. #
Charge 8

## Slide 16: January Technical Peer Review Recommendations
Rec. #
Charge 8
BCR being processed. Once complete, recommendation is closed.
Design finalized and available on TC
Ang Lee’s analysis is complete. A writeup once he returns from vacation will close this recommendation
Bolted analysis conducted and requires peer review. Successful peer review will close this recommendation
Thermal cycling added to pressure test procedure. Completion of the test and documentation of results will close recommendation
Consideration has been made and a discussion on the impact documented. Review and approval by Beamline will close this recommendation
Specification drawing being created with flatness and bolt hole clocking tolerance. Release and delivery to CF will close this recommendation

## Slide 17: Downstream Decay Pipe Window

## Slide 18: DSDP Window Design
Specification Drawings located in Docdb-31052
Material: S304L Stainless Steel
  BCR Changing to S316L
Thickness: Varies among sections
Diameter Decay Pipe Connection: 4019.53 mm (13’ – 2.25”)
Outer Section Diameter: 2743.2 mm (9’)
Inner Section Diameter: 1828.8 mm (6’)
Design Standards:
  FESHM 5031.5
  ASME BVPC, Section VIII, Div. 1 & 2
  ASME XI
BCR being conducted to use weld code NAS1514 and to specify weld passivation to increase corrosion resistance
Charge 2, 7, 8
Rec. 1

## Slide 19: DSDP Window Analysis
Overview
  Design requirement to have window sustain accident case defined
  Accident case investigated at 2 and 5 accident pulses
    2 pulses is design requirement, 5 is investigated for insight into how close to failure and accident case will bring the window
  Analysis located at docdb-26309
Model and Boundary Conditions:
  Solid Model located in LBNF-doc-24999
  Energy deposition provided by Igor Rakhno located in LBNF-doc-23236
  Convective film coefficient hf=3 watt/m^2*K
    Conservative natural convection
  Fixed Temperature of 52C is placed at 12in Decay Pipe end based on AECOM analysis
  Off axis (72 cm) accident case
Charge 2, 7, 8
Notes: Add in that a FESHM note cannot be approved until after the vessel is constructed and a pressure test is conducted

## Slide 20: DSDP Windo Analysis
Thermal Results:
  On Axis Tmax after 2 and 5 accident pulses:
    Tmax 2 pulses: 155 C (311 F)
    Tmax 5 pulses: 214 C (417.2 F)
    Tmax change due to pulses: ~23 C/pulse (73.4 F)
  Off Axis (72 cm) Tmax after 2 and 5 accident pulses:
    Tmax 2 pulses: 158 C (316.4 F)
    Tmax 5 pulses: 198 C (388.4 F)
Charge 1, 2, 7, 8

## Slide 21: Decay Pipe Downstream Window Analysis Under 2.4 MW
Structural Results:
  On Axis:
    2 pulses: 13.5 ksi
    5 pulses: 28.2 ksi
  Off Axis:
    2 pulses: 10.1 ksi
    5 pulses: 25.2 ksi
  Per ASME VIII, DIV 2, part 5, allowable is 49.5 ksi
  Stress around weld joint area is ~2.2 ksi regardless of normal or accident cases
  Even after severe accident cases, the window remains functional
Analysis approved at Technical Peer Review
Analysis to be uploaded through TC and attached to AECOM FESHM 5031.5 note.
  FESHM Note located docdb-23864
Charge 2, 7, 8

## Slide 22: Upstream Decay Pipe Window

## Slide 23: USDP Window Design Overview
Topics:
  Dome Geometry
  Capture Bolt System
  Helicoflex Seal
  Cooling Loop
  Thermal/Structural Analysis
  Bolt Joint Analysis
Model controlled in TC: F10118812
  Drawings Complete and compiled in docdb 31052
Technical Peer Review conducted 01/25/24
Design Standards:
  Fermilab Engineering Manual
  FESHM 5031.5, Low Pressure Vessel
  ASME BVPC, Section VIII, Div. 1 & 2
  ASME PCC-1, Guidelines for Bolted Flange Joint Assembly
  MIL-HDBK-5, Metallic Materials and Elements for Aerospace Vehicle Structures
Charge 1, 2, 8

## Slide 24: USDP Window Design Overview
Total Internal pressure against window.
  MAWP = 5psi
    Specified by AECOM in their engineering calculations
  Interface with TH-Shield pile stating that internal pressure must be at or greater than TH Nitrogen
Domed window is one-piece machined window
Aluminum Window Diameter:
  1.5 m (~4.9 ft)
Aluminum Window Thickness:
  1.5 mm (~0.06 in)
  Thickness accepted and published in TDR as acceptable for neutrino yield
    TDR located
Outer Flange Diameter:
  1.8 m (~5.9 ft)
Charge 1, 2, 7
Rec. 2

## Slide 25: USDP Window Design Overview
Capture Bolts:
  Design based on Mu2e target window capture bolts
  Spring Loaded and held in place by cover plate
  Spring compresses into pocket. Does not interfere joint compression
  Design allows for bolts to be captured during a changeout procedure to assist with removable design
  Bolt Size: ¾-16 in
  Material: Grade 5 Titanium
    Corrosion Resistant
    Tungsten Disulfide coating to reduce friction and prevent galling
Cover Plate
Spring
0.75in Bolt
Charge 1, 2, 3

## Slide 26: Helicoflex Seal
Seal Parameters:
Specialized for Helium Sealing
Cross Section: 0.276 in
Diameter: 68.7in
Manufacturer Specifications
  Compression Force: 1542 lbs/in
    w/ 80 Bolts = 4160 lbs/bolt
  Max Operating Temp.: 392ºF = 200ºC
  Groove Design parameters provided by manufacturer to ensure proper seal seating

## Slide 27: Helicoflex Seal
Compression Load Requirements:
Manufacturer Catalogue located at docdb-31052
Optimal sealing load (Y_2) = 1542 lbs/in
Minimum sealing load (Y_0) = 660 lbs/in
Minimum service load (Y_m) = 228 lbs/in
Minimum sealing load after seating (Y_1) = 228 lbs/in
Manufacturer claims Helium leak tight up to 10150 psi at 68°F (20°C) and 4060 psi at 392°F (200°C)
Charge 1

## Slide 28: Helicoflex Seal
Seal Test 2016:
Location docdb-981
Conducted using test setup at Fermilab MI-8 service building
At 660 lbs/in shows <1sccm
  Requirement is 10 cc/min (200 ft^3/year)
Proves minimum sealing pressure
1542 lbs/in
660 lbs/in
228 lbs/in
Charge 1, 2, 5

## Slide 29: Helicoflex Seal
Additional Seal Test:
  Seal test being conducted at MI-8 looking at additional parameters of sealing.
  Draft of pressure test located in docdb-31135
3 Tests:
  Confirming torque requirements for seal compression in ideal parameters
  Sealing to out of flatness sealing face to determine sealing force requirements
    0.032 Amplitude. Twice manufacturer specification
  Ideal seal environment with thermal cycling using heat tape
    Cycling between max expected temperature and ambient
Charge 5
Rec. 5

## Slide 30: USDP Window Cooling Loop
Cooling loop necessary to reduce heat in flange at 2.4 MW to keep Helicoflex seal within operating temperature.
Cooling loop required to be removable to meet requirement of USDP Window being removable
Utilizing Swagelok compression fittings proven in NuMI Horn operation
Cooling lines only needed for 2.4 MW Operation
Charge 2

## Slide 31: USDP Window Cooling Loop
RAW Lines reach window through labyrinthed penetrations in the above T-Block
Characteristics:
  Heat Load = 16500 kW
  ΔT inlet to outlet = 10C
  Flow Rate = 6.2 gpm
  SS316 Piping
Connection accessed from top of T-Block shielding
Guide brackets on the top side of the window aid in aligning compression fittings
  Same design used for the NuMI Horns
RAW Piping Envelope drawing located docdb-31052

## Slide 32: USDP Window Permanent Cooling Loop Discussion
Per Technical Design Review of the Decay Windows, consideration was given to the addition of a permanent cooling loop on the USDP Snout Flange to provide more uniform temperature on sealing surface.
  Full discussion of conclusion located in docdb-31052
Decision is to not include this additional cooling loop.
1. Previous design used outdated thermal loading. New loading shows reduction in sealing area temperature by roughly 10C
2. The project has pushed for all systems with the potential to leak to be serviceable
3. Inclusion of a larger cooling loop that is to accommodate this recommendation would add substantial scope to the project to design a method of servicing the component
Charge 7
Rec. 6

## Slide 33: USDP Window Thermal/Structural Analysis
Charge 2
Overview
  Updated from previous analysis with peer review recommended modifications
Model and Boundary Conditions:
  Model located TC: F10118812
  Convection provided in docdb-28069
  Cooling channel is held at 45 C
    Calculation shows difference from wall to cooling fluid is roughly 4 C
    Calculation for temperature difference across piping wall located in docdb 31132
Rec. 2

## Slide 34: USDP Window Thermal/Structural Analysis
Charge 2
Thermal Results:
  Successfully hold sealing surface within optimal operating conditions at all accident cases
  Accident Cases:
    2 Pulses
      Tmax = 225 C
    5 Pulses
      Tmax = 241 C
Rec. 2

## Slide 35: USDP Window Thermal/Structural Analysis
Structural Results:
  Stresses are less than allowable for 2 pulse accident cases
Accident Cases:
  2 Pulses:
    Max Dynamic Stress = 17.1 ksi
  5 Pulses:
    Max Dynamic Stress = 20 ksi
ASME Allowable (ASME BPVC. II. D.C-2021, Part D, Table 5B):
  Yield = 34.2 ksi
  Ultimate = 42 ksi
MIL-HDBK-5 (MIL-HDBK-5 SECTION 3.6.2, Edition 5G, for 6061 ALLOY):
  Yield = 20.52 ksi
  Ultimate = 21.884 ksi
Analysis to be uploaded through TC and attached to AECOM FESHM 5031.5 note.
  FESHM Note located docdb-23864
Charge 2
Rec. 4

## Slide 36: USDP Window Bolted Joint Study
A bolted joint analysis was conducted to identify the required forces for clamping and effects of thermal expansion on the joint for bolt loosening and low-cycle fatigue
Analysis located at docdb-
  Analysis is in draft state and requires peer review before Technical Peer Review recommendation is considered met
References:
  Machinery’s Handbook
  Engineers Edge
Charge 2
Rec. 4

## Slide 37: USDP Window Bolted Joint Study
Minimum Bolt Spacing for Gasket Compression:
Minimum Force: 228 lbs/in
  Minimum service load of Seal
Maximum Force: 1542 lbs/in
  Seating force of seal. Seal groove diameter further compression after seating is reached
Safety factor of 3 used
Minimum bolt spacing: 7.47 in
Current Bolt Spacing: 2.7 in
Charge 2
Rec. 4

## Slide 38: USDP Window Bolted Joint Study
Required Torque:
Machinery’s Handbook 30th edition
Standard 70% yield preload
Torque wrench uncertainty = 25%
Allow for 10% preload loss due to local yielding
Tensile Yield of Ti-6Al-4V = 128000 psi
Calculated Preload = 13535.1 lbs
Load required by Helicoflex for seating
  4160 lbs
Required Torque = 60.1 ft-lbs
Charge 2
Rec. 4

## Slide 39: USDP Window Bolted Joint Study
Change in preload due to thermal loading:
Bell Helicopter Structural Design Manual
Bolt load after temperature change from ambient temperature and the product of the net thermal expansions and combined internal stiffness
Temp change of 41°C used taken from Ang Lee’s Analysis
P_T = 224.4 lbs
This force is adding to the preload 9375 lbs present in system. Change is not enough to loosen bolts
Charge 2
Rec. 4

## Slide 40: USDP Window Bolted Joint Study
Charge 2
Rec. 4
S-N Curve for Ti-6Al-4V
Investigation for Low-Cycle Fatigue:
Low cycle fatigue we are defining as 10^4 cycles or less from beam induced thermal expansion and contraction
Stress from restricted thermal expansion equations
  2 systems analyzed
    Restricted aluminum expansion
    Reinforced Titanium threaded into SS flange
  Total Stress Amplitude
    σ = 94.14 MPa
At 10^4 cycles, stress amplitude must be ~700 Mpa to induce fatigue failure

## Slide 41: USDP Window Cost Estimates
Charge 2
Rec. 4
Cost:
Fabricated Pieces = $60332.6
Hardware = $3871.02
Tungsten Disulfide Coating = $28800
Total = $93003.62

## Slide 42: USDP Window Installation
Installation will be conducted using the USDP Window Remote Exchange Mechanism. As such, a full definition on installation requirements or procedures is not able to be conducted until the FDR of the Remote Exchange Mechanism
Installation Plan:
  Phase 1 (Preparation):
    Window will be retrieved from storage. Perform pressure test and check for defects
    Mechanism will be retrieved and moved to high bay. Electrical and controls connections made and mechanical assemblies tested
  Phase 2 (Window Loading):
    Window is loaded onto mechanism
  Phase 3(Installation of Window):
    Window is installed onto flange
Preliminary Installation Procedure located docdb-31052
Full installation procedure will be reviewed at Exchange Mechanism FDR
Charge 2
Rec. 4

## Slide 43: USDP Window QA/QC
Draft Located docdb-31077
QC Procurement
  Vendor fabrications shall be procured with dimensional inspection reports, to be spot checked upon receipt
QC Fabrication
  An engineer or designated inspector will spot check these in-process measurements
  Fabrication records will be kept by the engineer
  Cooling loop will be pressure tested and certified
QC Installation
  Beamline is responsible with coordinating with NSCF for in process quality control measurements to meet design requirements for the USDP Window
  Beamline will coordinate with NSCF to conduct installation of USDP Window utilizing the USDP Window Remote Exchange Mechanism
Charge 2
Rec. 4

## Slide 44: Questions?

## Slide 45: Helicoflex Seal
Groove Design:
Depth = 0.237 ± 0.005in
Width = 0.354
Groove Finish = 32
Catalogue listed in Docdb-31052
Charge 2

## Slide 46: USDP Window Bolted Joint Study
Stress From Differential Thermal Expansion:
Charge 2
Rec. 4