## Slide 1
LBNF Clean Room Infrastructure Installation
Justin Freitag, Jim Stewart, Bill Miller

## Slide 2
Manpower and time resources
Work will be done in shifts
Shift 1 Day shift 05:00 to 15:00 Monday to Thursday (7h/d at 4d/w) Services available: 3 riggers and 2 surveyor
Shift 2 Evening shift 13:00 to 23:00 Monday to Thursday (7h/d at 4d/w) Services available: 3 riggers
Shift 3 Day shift from 06:00 to 16:00 Friday to Saturday (7h/d at 2d/w) Service available: 2 riggers
Personnel (per shift)
Management
  1 x CERN Supervisor
  1 x Shift Manager
  1 x Safety Officer
Subcontractor Technicians
  6 x Main Technicians (3 teams of 2 persons) Including one lead technician
To assemble the 4 main pieces in the gabarits, and at its final location. Mainly placing bolts by hand.
  6 x Bolt Tightening Technicians (3 teams of 2 persons)
To tighten the bolts
I&I Core Technicians
  4 x Bolt Tightening Technicians (2 team of 2 persons) Shift 3
To tighten the remaining bolts
  2 x G10 Technicians (1 team of 2 persons)
To glue the G10
  2 x Woodwork Technician (1 team of 2 persons)
To do the woodwork and the polystyrene
  Total: 20+3 persons/shift
        Main assumptions: Warm structure in 156 d (2’200h at 56h/w)
                Floor 26 d
                Small wall 6 d (per wall)
                39 portals 78 d
                Warm Skin 40 d (560h for 560 plates)
Needs Updated

## Slide 3: Assumptions and questions
The Cold boxes are constructed in parallel to the cryostat steel and are installed as step 1.
  How much of the cold boxes will be assembled on the surface?
  How much of the steel is fabricated at a factory and how much is self performed?
Do we want to install a small 2t bridge crane under the 4850 changing room so the room can stay in place when David installs his equipment?

## Slide 4
Fabricate Cold Box #3
  Duration: 3mo
  Crew: x welder x MT
T0-3mo
Cold box
Laydown/Assembly
Area

## Slide 5
Install Cold Box Pedestals
  Duration: 40 hrs
  Crew:
~2days
Cold box
Laydown/Assembly
Area
Cold Box Pedestals
Do we need to install the pedestal in front of the cryostat here?

## Slide 6
Install Cold Box#1
  Duration: 40 hrs
  Crew:
~2days
Cold box
Laydown/Assembly
Area
Cold Box #1

## Slide 7
Install Cold Box#2
  Duration: 40 hrs
  Crew:
2days
Cold box
Laydown/Assembly
Area
Cold Box #2

## Slide 8
Install Cold Box#3
  Duration: 40 hrs
  Crew:
2days
Cold box
Laydown/Assembly
Area
Cold Box #3

## Slide 9
Install N-S Bridge I-Beam #1
  Duration: 20 Hrs
  Crew:
Day 1
Bridge I-Beam#1

## Slide 10
Install Bridge I-Beam #2
  Duration: 20 Hrs
  Crew:
Day 2
Bridge I-Beam#2

## Slide 11
Install Bridge Internal Steel
  Duration: 20 Hrs
  Crew:
Day 5
Bridge internal steel

## Slide 12
Install Bridge Walking Surface
  Duration: 40 Hrs
  Crew:
Day 7
Walking Surface
Walking surface is either a metal decking or a concrete pad

## Slide 13
Install Bridge Guard Rails
  Duration: 20 Hrs
  Crew:
Day 8
Guard rails

## Slide 14
Install TCO Beams
  Duration: 40 Hrs
  Crew:
Day 10
TCO beams

## Slide 15
Install Bridge-to-Cryostat Structures
  Duration: 40 Hrs
  Crew:
Day 12
Walkway Structure

## Slide 16
Install Floor for 4850L Changing Room/Walkway
  Duration: 80 Hrs
  Crew:
Changing room floor support

## Slide 17
Install Cleanroom Crane (Mechanical)
  Duration: 80 Hrs
  Crew:
Connect Cleanroom Crane Power and Commission
  Duration: 80Hrs
  Crew:
-Activities are in parallel
-Commission should be in parallel to the next step
Day 16
Month 1

## Slide 18
Assemble/Install North and South APA Towers
  Duration: 120 Hrs (6 work days)
  Crew:
Day 22
Towers

## Slide 19
Install Cleanroom I-Beam #1&2
  Duration: 40 Hrs
  Crew:
Day 24
CR I-Beam #1 and #2

## Slide 20
Install Cleanroom Roof Structure
  Duration: 40 Hrs
  Crew:
CR roof internal steel
Day 26

## Slide 21
Install Raised Platform Supports
  Duration: 60 Hrs
  Crew:
Floor supports
Day 29

## Slide 22
Install Raised Platform Decking and Walkways
  Duration: 60 Hrs
  Crew:
Day 31
Floor decking

## Slide 23
Install Raised Platform Railings
  Duration: 60 Hrs
  Crew:
Day 32
Railings

## Slide 24
Install Raised Platform Stairs and Ships Ladders
  Duration: 60 Hrs
  Crew:
Day 35
Month 2
Ships Ladders/monorails

## Slide 25
Install Cleanroom West Wall Truss
  Duration: 80 Hrs
  Crew:
Truss West wall
Day 42

## Slide 26
Install Rails, Hoists, and Trollies
  Duration: 40 Hrs
  Crew:
Day 43
Assembly Rails/ Hoists/trollies

## Slide 27
Install Cleanroom East Wall
  Duration: 80 Hrs
  Crew:
NOTE: END PHASE 1 CLEAN ROOM CONSTRUCTION
Here the gaps between the cryostat and the cavern are sealed with plastic sheet.
The cryostat wall may be cleaned at this time if it is really dirty.
Seal cryostat to wall
Day 46

## Slide 28
Install APA Assembly Fixtures #1&2
  Duration: 80 Hrs
  Crew:
Install Cleanroom sprinklers
  Duration: xx Hrs
  Crew:
NOTE: BEGIN PHASE 2 CLEAN ROOM CONSTRUCTION
Day 4
Install 4 fixtures

## Slide 29
Install Temporary Cleanroom Power
  Duration: 80 Hrs
  Crew:
Day 13
Cleanroom Power Carts

## Slide 30
Install APA Assembly Fixtures #3&4
  Duration: 80 Hrs
  Crew:
Install 4 fixtures
Day 17
Month 1

## Slide 31
Install CPA Assembly Fixture
  Duration: 80 Hrs
  Crew:
CPA assembly fixture
Day 21
When is the jib crane installed?

## Slide 32
Construct 4910L Material Airlock
  Duration: 80 Hrs
  Crew:
SAS
Day 25

## Slide 33
Construct 4910L Changing Room
  Duration: 40 Hrs
  Crew:
Day 33
Month 2
Changing room 4910

## Slide 34
Install Walking Surface Over Cold Boxes
  Duration: 60 Hrs
  Crew:
Day 36
Cold box platform

## Slide 35
Install Remaining Roof and Wall Covering
  Duration: 160 Hrs
  Crew:
North wall
South wall
West wall
Roof
Day 44

## Slide 36
Construct 4850L Changing Room
  Duration: 80 Hrs
  Crew:
Day 48
Changing room

## Slide 37
Install CE Crosses on Cold Boxes
  Duration: 20 Hrs
  Crew:
Day 49
Crosses

## Slide 38
Install Washing Station in 4910L Material Airlock
  Duration: Hrs
  Crew:
Day 51
Month 3
Kitchen sink

## Slide 39
Add all loose eqp
ORC for all eqp
Dry-run tests
Clean everything
Commission cleanroom
  Duration: 1 month
  Crew:
Day 68
Month 4

## Slide 40: Discussion