## FD2_Cleanroom_Step-0
Summary | [5 empty] | SrMT | Tech | [44 empty] | 2025 | [51 empty] | 2026 | [51 empty] | 2027 | [51 empty] | 2028
| T0-AUP of North Cavern 25-Oct-2024 -P6 Dump Dec 20-23 |  | I&I | [6 empty] | -4 |  |  |  |  | -5 |  |  |  | -4 |  |  |  | -3 |  |  |  |  | -2 |  |  |  | -1 |  |  |  |  | 1 |  |  |  | 2 |  |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  |  | 7 |  |  |  | 8 |  |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  |  | 12 |  |  |  | 13 |  |  |  | 14 |  |  |  |  | 15 |  |  |  | 16 |  |  |  | 17 |  |  |  | 18 |  |  |  |  | 19 |  |  |  | 20 |  |  |  |  | 21 |  |  |  | 22 |  |  |  | 23 |  |  |  |  | 24 |  |  |  | 25 |  |  |  |  | 26 |  |  |  | 27 |  |  |  | 28 |  |  |  |  | 29 |  |  |  | 30 |  |  |  | 31 |  |  |  | 32 |  |  |  |  | 33 |  |  |  | 34 |  |  |  | 35 |  |  |  |  | 36 |  |  |  | 37 |  |  |  |  | 38 |  |  |  | 39 |  |  |  | 40 |  |  |  |  | 41 |  |  |  | 42 |  |  |  | 43 |  |  |  | 44 |  |  |  |  | 45 |  |  |  |  | 46 |  |  |  |  | 47 |  |  |  |  | 48 |  |  |  |  | 49 |  |  |  |  | 50 |  |  |  |  | 51
WBS/Activity | Activity Description |  | SrT | Weld | MT | Hours | Hours | Weld | -31 | -30 | -29 | -28 | -27 | -26 | -25 | -24 | -23 | -22 | -21 | -20 | -19 | -18 | -17 | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225
 | time axis 2023-03-25 to 2028-02-12
[167 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | #REF! |  | 2026-04-04: #REF!; 2026-04-11: #REF!; 2026-04-18: #REF!; 2026-04-25: #REF!; 2026-05-02: #REF!; 2026-05-09: #REF!; 2026-05-16: #REF!; 2026-05-23: #REF!; 2026-05-30: #REF!; 2026-06-06: #REF!; 2026-06-13: #REF!; 2026-06-20: #REF!; 2026-06-27: #REF!; 2026-07-04: #REF!; 2026-07-11: #REF!; 2026-07-18: #REF!; 2026-07-25: #REF!; 2026-08-01: #REF!; 2026-08-08: #REF!; 2026-08-15: #REF!; 2026-08-22: #REF!; 2026-08-29: #REF!; 2026-09-05: #REF!; 2026-09-12: #REF!; 2026-09-19: #REF!; 2026-09-26: #REF!; 2026-10-03: #REF!; 2026-10-10: #REF!; 2026-10-17: #REF!; 2026-10-24: #REF!; 2026-10-31: #REF!; 2026-11-07: #REF!; 2026-11-14: #REF!; 2026-11-21: #REF!; 2026-11-28: #REF!; 2026-12-05: #REF!; 2026-12-12: #REF!; 2026-12-19: #REF!; 2026-12-26: #REF!; 2027-01-02: #REF!; 2027-01-09: #REF!; 2027-01-16: #REF!; 2027-01-23: #REF!; 2027-01-30: #REF!; 2027-02-06: #REF!; 2027-02-13: #REF!; 2027-02-20: #REF!; 2027-02-27: #REF!; 2027-03-06: #REF!; 2027-03-13: #REF!; 2027-03-20: #REF!; 2027-03-27: #REF!; 2027-04-03: #REF!; 2027-04-10: #REF!; 2027-04-17: #REF!; 2027-04-24: #REF!; 2027-05-01: #REF!; 2027-05-08: #REF!; 2027-05-15: #REF!; 2027-05-22: #REF!; 2027-05-29: #REF!; 2027-06-05: #REF!; 2027-06-12: #REF!; 2027-06-19: #REF!; 2027-06-26: #REF!; 2027-07-03: #REF!; 2027-07-10: #REF!; 2027-07-17: #REF!; 2027-07-24: #REF!; 2027-07-31: #REF!; 2027-08-07: #REF!; 2027-08-14: #REF!; 2027-08-21: #REF!; 2027-08-28: #REF!; 2027-09-04: #REF!; 2027-09-11: #REF!; 2027-09-18: #REF!; 2027-09-25: #REF!; 2027-10-02: #REF!; 2027-10-09: #REF!; 2027-10-16: #REF!; 2027-10-23: #REF!; 2027-10-30: #REF!; 2027-11-06: #REF!; 2027-11-13: #REF!; 2027-11-20: #REF!; 2027-11-27: #REF!; 2027-12-04: #REF!; 2027-12-11: #REF!; 2027-12-18: #REF!; 2027-12-25: #REF!; 2028-01-01: #REF!; 2028-01-08: #REF!; 2028-01-15: #REF!; 2028-01-22: #REF!; 2028-01-29: #REF!; 2028-02-05: #REF!; 2028-02-12: #REF!
|  | Hours |  |  |  | #REF! |  |  | 2026-04-04: #REF!; 2026-04-11: #REF!; 2026-04-18: #REF!; 2026-04-25: #REF!; 2026-05-02: #REF!; 2026-05-09: #REF!; 2026-05-16: #REF!; 2026-05-23: #REF!; 2026-05-30: #REF!; 2026-06-06: #REF!; 2026-06-13: #REF!; 2026-06-20: #REF!; 2026-06-27: #REF!; 2026-07-04: #REF!; 2026-07-11: #REF!; 2026-07-18: #REF!; 2026-07-25: #REF!; 2026-08-01: #REF!; 2026-08-08: #REF!; 2026-08-15: #REF!; 2026-08-22: #REF!; 2026-08-29: #REF!; 2026-09-05: #REF!; 2026-09-12: #REF!; 2026-09-19: #REF!; 2026-09-26: #REF!; 2026-10-03: #REF!; 2026-10-10: #REF!; 2026-10-17: #REF!; 2026-10-24: #REF!; 2026-10-31: #REF!; 2026-11-07: #REF!; 2026-11-14: #REF!; 2026-11-21: #REF!; 2026-11-28: #REF!; 2026-12-05: #REF!; 2026-12-12: #REF!; 2026-12-19: #REF!; 2026-12-26: #REF!; 2027-01-02: #REF!; 2027-01-09: #REF!; 2027-01-16: #REF!; 2027-01-23: #REF!; 2027-01-30: #REF!; 2027-02-06: #REF!; 2027-02-13: #REF!; 2027-02-20: #REF!; 2027-02-27: #REF!; 2027-03-06: #REF!; 2027-03-13: #REF!; 2027-03-20: #REF!; 2027-03-27: #REF!; 2027-04-03: #REF!; 2027-04-10: #REF!; 2027-04-17: #REF!; 2027-04-24: #REF!; 2027-05-01: #REF!; 2027-05-08: #REF!; 2027-05-15: #REF!; 2027-05-22: #REF!; 2027-05-29: #REF!; 2027-06-05: #REF!; 2027-06-12: #REF!; 2027-06-19: #REF!; 2027-06-26: #REF!; 2027-07-03: #REF!; 2027-07-10: #REF!; 2027-07-17: #REF!; 2027-07-24: #REF!; 2027-07-31: #REF!; 2027-08-07: #REF!; 2027-08-14: #REF!; 2027-08-21: #REF!; 2027-08-28: #REF!; 2027-09-04: #REF!; 2027-09-11: #REF!; 2027-09-18: #REF!; 2027-09-25: #REF!; 2027-10-02: #REF!; 2027-10-09: #REF!; 2027-10-16: #REF!; 2027-10-23: #REF!; 2027-10-30: #REF!; 2027-11-06: #REF!; 2027-11-13: #REF!; 2027-11-20: #REF!; 2027-11-27: #REF!; 2027-12-04: #REF!; 2027-12-11: #REF!; 2027-12-18: #REF!; 2027-12-25: #REF!; 2028-01-01: #REF!; 2028-01-08: #REF!; 2028-01-15: #REF!; 2028-01-22: #REF!; 2028-01-29: #REF!; 2028-02-05: #REF!; 2028-02-12: #REF!
FDC.05.02.06 | Warm Cryostat #2 Installation |  |  |  |  | 5420 | 16440 | 0 | bar: 2026-04-04 to 2028-02-12
A82030 | Mark floor for I-beams, survey cavern floor and beam placement Cryostat #2 | 1 |  |  | 3 |  | 120 |  | 2024-08-24: 3
| Mark floor for I-beams, survey cavern floor and beam placement Cryostat #2 |  | 1 |  |  | 40 | bar: 2024-08-24
A82040 | Install Floor Structure Cryostat #2 - FNAL personnel | 11 |  |  | 1.8182 |  | 800 |  | 2024-08-31: 1; 2024-09-07: 2; 2024-09-14: 2; 2024-09-21: 2; 2024-09-28: 2; 2024-10-05: 2; 2024-10-12: 2; 2024-10-19: 2; 2024-10-26: 2; 2024-11-02: 2; 2024-11-09: 1
A82060 | Level Floor, Grout undearneath Beams, including Wood Forms #2 | 3 |  |  | 1.6667 |  | 200 |  | 2024-11-09: 1; 2024-11-16: 2; 2024-11-23: 2
|  |  | 1.6667 |  |  | 200 |  |  | 2024-11-09: 1; 2024-11-16: 2; 2024-11-23: 2
A82070 | Install pipes for water condensation Cryostat #2 | 2 |  |  | 4 |  | 320 |  | 2024-11-30: 4; 2024-12-07: 4
|  |  | 2 |  |  | 160 |  |  | 2024-11-30: 2; 2024-12-07: 2
A82080 | Install tertiary membrane on the floor structure - Cryostat #2 - FNAL personnel | 6 |  |  | 1.6667 |  | 400 |  | 2024-12-14: 2; 2024-12-21: 2; 2024-12-28: 1; 2025-01-04: 1; 2025-01-11: 2; 2025-01-18: 2
A82110 | Install East Wall Steel Structure Cryostat #2 - FNAL personnel | 2 |  |  | 2 |  | 160 |  | 2025-02-01: 2; 2025-02-08: 2
A82100 | Install TCO pedestal + miscellanea Cryostat #2 | 1 |  |  | 1.5 |  | 60 |  | 2025-02-01: 1.5
| Install TCO pedestal + miscellanea Cryostat #2 |  | 0.5 |  |  | 20 |  |  | 2025-02-01: 0.5
A82130 | Install Cryostat #2 Major Portals 1-20 - FNAL personnel | 16 |  |  | 1.5625 |  | 1000 |  | 2025-02-22: 2; 2025-03-01: 2; 2025-03-08: 2; 2025-03-15: 2; 2025-03-22: 2; 2025-03-29: 2; 2025-04-05: 2; 2025-04-12: 2; 2025-04-19: 2; 2025-04-26: 1; 2025-05-03: 1; 2025-05-10: 1; 2025-05-17: 1; 2025-05-24: 1; 2025-05-31: 1; 2025-06-07: 1
A82170 | Install Cryostat #2 Tertiary membrane main body East half - FNAL personnel | 9 |  |  | 1.7778 |  | 640 |  | 2025-05-24: 2; 2025-05-31: 2; 2025-06-07: 2; 2025-06-14: 2; 2025-06-21: 2; 2025-06-28: 2; 2025-07-05: 2; 2025-07-12: 1; 2025-07-19: 1
A82150 | Install Cryostat #2 Major Portals 21-39 - FNAL personnel | 14 |  |  | 1.7857 |  | 1000 |  | 2025-05-24: 2; 2025-05-31: 2; 2025-06-07: 2; 2025-06-14: 2; 2025-06-21: 2; 2025-06-28: 2; 2025-07-05: 2; 2025-07-12: 2; 2025-07-19: 2; 2025-07-26: 2; 2025-08-02: 2; 2025-08-09: 1; 2025-08-16: 1; 2025-08-23: 1
A82250 | Cryostat #2 bolts torque qualification and QC - East half (weekends only, FNAL personnel) | 10 |  |  | 1.8 |  | 720 |  | 2025-05-31: 1; 2025-06-07: 2; 2025-06-14: 2; 2025-06-21: 2; 2025-06-28: 2; 2025-07-05: 2; 2025-07-12: 2; 2025-07-19: 2; 2025-07-26: 2; 2025-08-02: 1
|  |  | 0.45 |  |  | 180 |  |  | 2025-05-31: 0.25; 2025-06-07: 0.5; 2025-06-14: 0.5; 2025-06-21: 0.5; 2025-06-28: 0.5; 2025-07-05: 0.5; 2025-07-12: 0.5; 2025-07-19: 0.5; 2025-07-26: 0.5; 2025-08-02: 0.25
A82190 | Install Cryostat #2 Tertiary membrane main body West half | 9 |  |  | 1.7778 |  | 640 |  | 2025-07-19: 1; 2025-07-26: 2; 2025-08-02: 2; 2025-08-09: 2; 2025-08-16: 2; 2025-08-23: 2; 2025-08-30: 2; 2025-09-06: 2; 2025-09-13: 1
A82350 | Install cryostat ladders, top walking surface and guardrails for Cryostat #2 - FNAL personnel | 9 |  |  | 2.5 |  | 900 |  | 2025-07-19: 1; 2025-07-26: 3; 2025-08-02: 3; 2025-08-09: 3; 2025-08-16: 3; 2025-08-23: 3; 2025-08-30: 3; 2025-09-06: 3; 2025-09-13: 0.5
A82260 | Cryostat #2 bolts torque qualification and QC - West half (weekends only, FNAL personnel) | 9 |  |  | 2 |  | 720 |  | 2025-08-02: 2; 2025-08-09: 2; 2025-08-16: 2; 2025-08-23: 2; 2025-08-30: 2; 2025-09-06: 2; 2025-09-13: 2; 2025-09-20: 2; 2025-09-27: 2
|  |  | 0.5 |  |  | 180 |  |  | 2025-08-02: 0.5; 2025-08-09: 0.5; 2025-08-16: 0.5; 2025-08-23: 0.5; 2025-08-30: 0.5; 2025-09-06: 0.5; 2025-09-13: 0.5; 2025-09-20: 0.5; 2025-09-27: 0.5
A82210 | Install Cryostat #2 input ventilation on the manholes - FNAL personnel | 3 |  |  | 1.6667 |  | 200 |  | 2025-08-09: 2; 2025-08-16: 2; 2025-08-23: 1
|  |  | 0.83333 |  |  | 100 |  |  | 2025-08-09: 1; 2025-08-16: 1; 2025-08-23: 0.5
A82220 | Install Cryostat #2 West Wall and build TCO opening - FNAL personnel | 7 |  |  | 1.7143 |  | 480 |  | 2025-08-16: 2; 2025-08-23: 2; 2025-08-30: 2; 2025-09-06: 2; 2025-09-13: 2; 2025-09-20: 1; 2025-09-27: 1
A82240 | Cryostat #2 leak test on tertiary membrane - FNAL personnel | 5 |  |  | 1.6 |  | 320 |  | 2025-09-06: 1; 2025-09-13: 2; 2025-09-20: 2; 2025-09-27: 2; 2025-10-04: 1
|  |  | 1.6 |  |  | 320 |  |  | 2025-09-06: 1; 2025-09-13: 2; 2025-09-20: 2; 2025-09-27: 2; 2025-10-04: 1
A82360 | Install walkways for Cryostat #2 - FNAL personnel | 4 |  |  | 4.5 |  | 720 |  | 2025-09-13: 4; 2025-09-20: 5; 2025-09-27: 5; 2025-10-04: 4
|  |  | 1.5 |  |  | 240 |  |  | 2025-09-13: 1; 2025-09-20: 2; 2025-09-27: 2; 2025-10-04: 1
A82370 | Install central stairs for Cryostat #2 - FNAL personnel | 5 |  |  | 3.2 |  | 640 |  | 2025-10-11: 2; 2025-10-18: 4; 2025-10-25: 4; 2025-11-01: 4; 2025-11-08: 2
|  |  | 1.6 |  |  | 320 |  |  | 2025-10-11: 1; 2025-10-18: 2; 2025-10-25: 2; 2025-11-01: 2; 2025-11-08: 1
A82380 | Install detector mezzanine for Cryostat #2 - FNAL personnel | 4 |  |  | 3.5 |  | 560 |  | 2025-11-01: 2; 2025-11-08: 4; 2025-11-15: 4; 2025-11-22: 4
|  |  | 1.75 |  |  | 280 |  |  | 2025-11-01: 1; 2025-11-08: 2; 2025-11-15: 2; 2025-11-22: 2
A82400 | Install Cryogenic mezzanine level 1 for Cryostat #2 - FNAL personnel | 5 |  |  | 3.3333 |  | 800 |  | 2025-11-08: 2; 2025-11-15: 4; 2025-11-22: 4; 2025-11-29: 4; 2025-12-06: 4; 2025-12-13: 2
|  |  | 1.6667 |  |  | 400 |  |  | 2025-11-08: 1; 2025-11-15: 2; 2025-11-22: 2; 2025-11-29: 2; 2025-12-06: 2; 2025-12-13: 1
A82390 | Install racks on detector mezzanine for Cryostat #2 - FNAL personnel | 3 |  |  | 3.3333 |  | 400 |  | 2025-11-29: 4; 2025-12-06: 4; 2025-12-13: 2
|  |  | 1.6667 |  |  | 200 |  |  | 2025-11-29: 2; 2025-12-06: 2; 2025-12-13: 1
A82410 | Install Cryogenic mezzanine level 2 for Cryostat #2- FNAL personnel | 0 |  |  | 3 |  | 600 |  | 2025-12-13: 2; 2025-12-20: 4; 2025-12-27: 4; 2026-01-03: 4; 2026-01-10: 1
|  |  | 1.5 |  |  | 300 |  |  | 2025-12-13: 1; 2025-12-20: 2; 2025-12-27: 2; 2026-01-03: 1.5; 2026-01-10: 1
A82420 | Install South Cavern Barracks on Cryo Mezzanine + HVAC + Safety- FNAL personnel | 0 |  |  | 3.3333 |  | 800 |  | 2025-12-13: 2; 2025-12-20: 4; 2025-12-27: 4; 2026-01-03: 4; 2026-01-10: 2; 2026-01-17: 4
|  |  | 1.6667 |  |  | 400 |  |  | 2025-12-13: 1; 2025-12-20: 2; 2025-12-27: 2; 2026-01-03: 2; 2026-01-10: 1; 2026-01-17: 2
A82430 | Install South Cavern DAQ room with racks, power, network- FNAL personnel | 0 |  |  | 3.2 |  | 640 |  | 2026-01-31: 2; 2026-02-07: 4; 2026-02-14: 4; 2026-02-21: 4; 2026-02-28: 2
|  |  | 1.6 |  |  | 320 |  |  | 2026-01-31: 1; 2026-02-07: 2; 2026-02-14: 2; 2026-02-21: 2; 2026-02-28: 1
A82440 | Install grey room in the South Cavern - FNAL personnel | 6 |  |  | 3.3333 |  | 800 |  | 2026-01-31: 2; 2026-02-07: 4; 2026-02-14: 4; 2026-02-21: 4; 2026-02-28: 4; 2026-03-07: 2
|  |  | 1.6667 |  |  | 400 |  |  | 2026-01-31: 1; 2026-02-07: 2; 2026-02-14: 2; 2026-02-21: 2; 2026-02-28: 2; 2026-03-07: 1
A82460 | Initial outfitting of the grey room in the South Cavern - FNAL personnel | 1 |  |  | 1.8333 |  | 1100 |  | 2026-03-14: 1; 2026-03-21: 2; 2026-03-28: 2; 2026-04-04: 2; 2026-04-11: 2; 2026-04-18: 2; 2026-04-25: 2; 2026-05-02: 2; 2026-05-09: 2; 2026-05-16: 2; 2026-05-23: 2; 2026-05-30: 2; 2026-06-06: 2; 2026-06-13: 1.5; 2026-06-20: 1
|  |  | 1.8333 |  |  | 1100 |  |  | 2026-03-14: 1; 2026-03-21: 2; 2026-03-28: 2; 2026-04-04: 2; 2026-04-11: 2; 2026-04-18: 2; 2026-04-25: 2; 2026-05-02: 2; 2026-05-09: 2; 2026-05-16: 2; 2026-05-23: 2; 2026-05-30: 2; 2026-06-06: 2; 2026-06-13: 1.5; 2026-06-20: 1
A82480 | Install top walking surface for Cryostat #2 - FNAL personnel | 0 |  |  | 4 |  | 160 |  | 2026-07-18: 4
|  |  | 2 |  |  | 80 |  |  | 2026-07-18: 2
A82450 | Install the TCO beam for Cryostat #2 | 0 |  |  | 6 |  | 240 |  | 2026-12-19: 6
|  |  | 2 |  |  | 80 |  |  | 2026-12-19: 2
A82470 | Final outfitting of the grey room in the South Cavern - FNAL personnel | 0 |  |  | 3.75 |  | 300 |  | 2026-12-26: 1.5; 2027-01-02: 6
|  |  | 1.25 |  |  | 100 |  |  | 2026-12-26: 0.5; 2027-01-02: 2
FDC.05.02.07 | Cold Cryostat #2 Installation |  |  |  |  | 4000 | 5800 | 0 | bar: 2025-06-28 to 2027-01-16
A83000 | Install cold cryostat (insulation and membrane) first 20% of Cyrostat 2 - FNAL personnel | 0 |  |  | 1.1923 |  | 620 |  | 2025-11-22: 1; 2025-11-29: 1.5; 2025-12-06: 1.5; 2025-12-13: 1.5; 2025-12-20: 1.5; 2025-12-27: 1.5; 2026-01-03: 1.5; 2026-01-10: 0.5; 2026-01-17: 1.5; 2026-01-24: 1.5; 2026-01-31: 1; 2026-02-07: 0.5; 2026-02-14: 0.5
|  |  | 1.1923 |  |  | 620 |  |  | 2025-11-22: 1; 2025-11-29: 1.5; 2025-12-06: 1.5; 2025-12-13: 1.5; 2025-12-20: 1.5; 2025-12-27: 1.5; 2026-01-03: 1.5; 2026-01-10: 0.5; 2026-01-17: 1.5; 2026-01-24: 1.5; 2026-01-31: 1; 2026-02-07: 0.5; 2026-02-14: 0.5
A83020 | Install cold cryostat (insulation and membrane) second 20% of Cyrostat 2 - FNAL personnel | 0 |  |  | 1.1923 |  | 620 |  | 2026-02-21: 0.5; 2026-02-28: 1; 2026-03-07: 1; 2026-03-14: 1; 2026-03-21: 1; 2026-03-28: 1; 2026-04-04: 1; 2026-04-11: 1; 2026-04-18: 1; 2026-04-25: 2; 2026-05-02: 2; 2026-05-09: 2; 2026-05-16: 1
|  |  | 1.1923 |  |  | 620 |  |  | 2026-02-21: 0.5; 2026-02-28: 1; 2026-03-07: 1; 2026-03-14: 1; 2026-03-21: 1; 2026-03-28: 1; 2026-04-04: 1; 2026-04-11: 1; 2026-04-18: 1; 2026-04-25: 2; 2026-05-02: 2; 2026-05-09: 2; 2026-05-16: 1
A83040 | Install cold cryostat (insulation and membrane) third 20% of Cyrostat 2 - FNAL personnel | 0 |  |  | 1.4091 |  | 620 |  | 2026-05-09: 0.5; 2026-05-16: 1; 2026-05-23: 1; 2026-05-30: 1; 2026-06-06: 1; 2026-06-13: 1; 2026-06-20: 2; 2026-06-27: 2; 2026-07-04: 2; 2026-07-11: 2; 2026-07-18: 2
|  |  | 1.4091 |  |  | 620 |  |  | 2026-05-09: 0.5; 2026-05-16: 1; 2026-05-23: 1; 2026-05-30: 1; 2026-06-06: 1; 2026-06-13: 1; 2026-06-20: 2; 2026-06-27: 2; 2026-07-04: 2; 2026-07-11: 2; 2026-07-18: 2
A83060 | Install cold cryostat (insulation and membrane) fourth 20% of Cyrostat 2 - FNAL personnel | 0 |  |  | 1.4091 |  | 620 |  | 2026-07-25: 1; 2026-08-01: 1; 2026-08-08: 1; 2026-08-15: 1; 2026-08-22: 1; 2026-08-29: 1; 2026-09-05: 2; 2026-09-12: 2; 2026-09-19: 2; 2026-09-26: 2; 2026-10-03: 1.5
|  |  | 1.4091 |  |  | 620 |  |  | 2026-07-25: 1; 2026-08-01: 1; 2026-08-08: 1; 2026-08-15: 1; 2026-08-22: 1; 2026-08-29: 1; 2026-09-05: 2; 2026-09-12: 2; 2026-09-19: 2; 2026-09-26: 2; 2026-10-03: 1.5
A83080 | Install cold cryostat (insulation and membrane) last 20% of Cyrostat 2 - FNAL personnel | 0 |  |  | 1.4091 |  | 620 |  | 2026-10-03: 0.5; 2026-10-10: 1; 2026-10-17: 1; 2026-10-24: 1; 2026-10-31: 1; 2026-11-07: 1; 2026-11-14: 2; 2026-11-21: 2; 2026-11-28: 2; 2026-12-05: 2; 2026-12-12: 2
|  |  | 1.4091 |  |  | 620 |  |  | 2026-10-03: 0.5; 2026-10-10: 1; 2026-10-17: 1; 2026-10-24: 1; 2026-10-31: 1; 2026-11-07: 1; 2026-11-14: 2; 2026-11-21: 2; 2026-11-28: 2; 2026-12-05: 2; 2026-12-12: 2
A83110 | Install Internal Cryogenics in Cryostat #2 - FNAL personnel | 0 |  |  | 3.75 |  | 900 |  | 2026-10-03: 3; 2026-10-10: 4; 2026-10-17: 4; 2026-10-24: 4; 2026-10-31: 4; 2026-11-07: 3.5
|  |  | 1.25 |  |  | 300 |  |  | 2026-10-03: 1; 2026-10-10: 1.5; 2026-10-17: 1.5; 2026-10-24: 1.5; 2026-10-31: 1.5; 2026-11-07: 0.5
A83120 | Leak checking in Cryostat #2 - FNAL personnel | 0 |  |  | 4.0909 |  | 1800 |  | 2026-10-10: 2.5; 2026-10-17: 4.5; 2026-10-24: 4.5; 2026-10-31: 4.5; 2026-11-07: 4.5; 2026-11-14: 4.5; 2026-11-21: 4.5; 2026-11-28: 4.5; 2026-12-05: 4.5; 2026-12-12: 4.5; 2026-12-19: 2
|  |  | 1.3636 |  |  | 600 |  |  | 2026-10-10: 0.5; 2026-10-17: 1.5; 2026-10-24: 1.5; 2026-10-31: 1.5; 2026-11-07: 1.5; 2026-11-14: 1.5; 2026-11-21: 1.5; 2026-11-28: 1.5; 2026-12-05: 1.5; 2026-12-12: 1.5; 2026-12-19: 1
| Installation of Detector Infrastructure on top of Warm Cryostat #2 |  |  |  |  | 5320 | 6320 | 1280
A85000 | Cut feedthrough holes in the tertiary membrane of Cryostat #2 | 5 |  |  | 1.6 |  | 320 |  | 2026-01-24: 1; 2026-01-31: 2; 2026-02-07: 2; 2026-02-14: 2; 2026-02-21: 1
|  |  | 1.6 |  |  | 320 |  |  | 2026-01-24: 1; 2026-01-31: 2; 2026-02-07: 2; 2026-02-14: 2; 2026-02-21: 1
A85020 | Install miniracks and supports on top of Cryostat #2 | 3 |  |  | 1.6667 |  | 200 |  | 2026-01-31: 1; 2026-02-07: 2; 2026-02-14: 2
|  |  | 1.6667 |  |  | 200 |  |  | 2026-01-31: 1; 2026-02-07: 2; 2026-02-14: 2
A85030 | Install cable trays on top of Cryostat #2 | 5 |  |  | 2 |  | 400 |  | 2026-02-07: 2; 2026-02-14: 2; 2026-02-21: 2; 2026-02-28: 2; 2026-03-07: 2
|  |  | 2 |  |  | 400 |  |  | 2026-02-07: 2; 2026-02-14: 2; 2026-02-21: 2; 2026-02-28: 2; 2026-03-07: 2
A85050 | Install cables/fibers from the feedthroughs to the detector racks for Detector #2 | 10 |  |  | 1.4 |  | 560 |  | 2026-03-07: 1; 2026-03-14: 1; 2026-03-21: 2; 2026-03-28: 2; 2026-04-04: 1; 2026-04-11: 1; 2026-04-18: 1; 2026-04-25: 2; 2026-05-02: 2; 2026-05-09: 1
|  |  | 1.4 |  |  | 560 |  |  | 2026-03-07: 1; 2026-03-14: 1; 2026-03-21: 2; 2026-03-28: 2; 2026-04-04: 1; 2026-04-11: 1; 2026-04-18: 1; 2026-04-25: 2; 2026-05-02: 2; 2026-05-09: 1
A85060 | Install cables/fibers from the top of the cryostat and mezzanine to DAQ racks for Detector #2 | 10 |  |  | 1.4 |  | 560 |  | 2026-03-07: 1; 2026-03-14: 1; 2026-03-21: 2; 2026-03-28: 2; 2026-04-04: 1; 2026-04-11: 1; 2026-04-18: 1; 2026-04-25: 2; 2026-05-02: 2; 2026-05-09: 1
|  |  | 1.4 |  |  | 560 |  |  | 2026-03-07: 1; 2026-03-14: 1; 2026-03-21: 2; 2026-03-28: 2; 2026-04-04: 1; 2026-04-11: 1; 2026-04-18: 1; 2026-04-25: 2; 2026-05-02: 2; 2026-05-09: 1
A85010 | Install crossing tubes and supports for Cryostat #2 | 7 |  |  | 3.4286 |  | 960 |  | 2026-03-21: 2; 2026-03-28: 4; 2026-04-04: 4; 2026-04-11: 4; 2026-04-18: 4; 2026-04-25: 4; 2026-05-02: 2
|  |  | 1.7143 |  |  | 480 |  |  | 2026-03-21: 1; 2026-03-28: 2; 2026-04-04: 2; 2026-04-11: 2; 2026-04-18: 2; 2026-04-25: 2; 2026-05-02: 1
|  | 7 |  | 1.7143 |  |  |  | 480 | 2026-03-21: 1; 2026-03-28: 2; 2026-04-04: 2; 2026-04-11: 2; 2026-04-18: 2; 2026-04-25: 2; 2026-05-02: 1
A85070 | Install isolation transformer for Cryostat #2 | 2 |  |  | 1 |  | 80 | bar: 2026-04-25 to 2026-05-02
|  |  | 1 |  |  | 80 | bar: 2026-04-25 to 2026-05-02
A85100 | Install lighting to both mezzanines for Detector #2 | 3 |  |  | 1.3333 |  | 160 |  | 2026-04-25: 1; 2026-05-02: 2; 2026-05-09: 1
|  |  | 1.3333 |  |  | 160 |  |  | 2026-04-25: 1; 2026-05-02: 2; 2026-05-09: 1
A85090 | Install cryogenic mezzanine compressed air for Detector #2 | 4 |  |  | 1.5 |  | 240 |  | 2026-04-25: 1; 2026-05-02: 2; 2026-05-09: 2; 2026-05-16: 1
|  |  | 1.5 |  |  | 240 |  |  | 2026-04-25: 1; 2026-05-02: 2; 2026-05-09: 2; 2026-05-16: 1
A85160 | Install ground monitor for Detector #2 | 5 |  |  | 1.6 |  | 320 |  | 2026-04-25: 1; 2026-05-02: 2; 2026-05-09: 2; 2026-05-16: 2; 2026-05-23: 1
|  |  | 1.6 |  |  | 320 |  |  | 2026-04-25: 1; 2026-05-02: 2; 2026-05-09: 2; 2026-05-16: 2; 2026-05-23: 1
A85040 | Install GAr purge lines to all flanges of Cryostat #2 Part 1 | 7 |  |  | 1.4286 |  | 400 |  | 2026-04-25: 1; 2026-05-02: 1; 2026-05-09: 1; 2026-05-16: 1; 2026-05-23: 2; 2026-05-30: 2; 2026-06-06: 2
|  |  | 0.71429 |  |  | 200 |  |  | 2026-04-25: 0.5; 2026-05-02: 0.5; 2026-05-09: 0.5; 2026-05-16: 0.5; 2026-05-23: 1; 2026-05-30: 1; 2026-06-06: 1
|  |  |  | 1.4286 |  |  |  | 400 | 2026-04-25: 1; 2026-05-02: 1; 2026-05-09: 1; 2026-05-16: 1; 2026-05-23: 2; 2026-05-30: 2; 2026-06-06: 2
A85080 | Install AC and UPS power to both mezzanines and cables/cable trays from CUC for Detector #2 | 6 |  |  | 1.6667 |  | 400 |  | 2026-05-02: 1; 2026-05-09: 2; 2026-05-16: 2; 2026-05-23: 2; 2026-05-30: 2; 2026-06-06: 1
|  |  | 1.6667 |  |  | 400 |  |  | 2026-05-02: 1; 2026-05-09: 2; 2026-05-16: 2; 2026-05-23: 2; 2026-05-30: 2; 2026-06-06: 1
A85045 | Install GAr purge lines to all flanges of Cryostat #2 Part 2 | 7 |  |  | 1.4286 |  | 400 |  | 2026-06-06: 1; 2026-06-13: 1; 2026-06-20: 1; 2026-06-27: 1; 2026-07-04: 2; 2026-07-11: 2; 2026-07-18: 2
|  |  | 0.71429 |  |  | 200 |  |  | 2026-06-06: 0.5; 2026-06-13: 0.5; 2026-06-20: 0.5; 2026-06-27: 0.5; 2026-07-04: 1; 2026-07-11: 1; 2026-07-18: 1
|  |  |  | 1.4286 |  |  |  | 400 | 2026-06-06: 1; 2026-06-13: 1; 2026-06-20: 1; 2026-06-27: 1; 2026-07-04: 2; 2026-07-11: 2; 2026-07-18: 2
A85110 | Connect power to detector mezzanine racks, including cable trays, cables, PS for Detector #2 | 4 |  |  | 2 |  | 320 |  | 2026-08-15: 2; 2026-08-22: 2; 2026-08-29: 2; 2026-09-05: 2
|  |  | 2 |  |  | 320 |  |  | 2026-08-15: 2; 2026-08-22: 2; 2026-08-29: 2; 2026-09-05: 2
A85120 | Install DUNE detector safety system for Detector #2 | 4 |  |  | 2 |  | 320 |  | 2026-09-05: 2; 2026-09-12: 2; 2026-09-19: 2; 2026-09-26: 2
|  |  | 2 |  |  | 320 |  |  | 2026-09-05: 2; 2026-09-12: 2; 2026-09-19: 2; 2026-09-26: 2
A85140 | Install cryostat GN2 system | 2 |  |  | 2 |  | 160 |  | 2026-09-26: 2; 2026-10-03: 2
|  |  | 1 |  |  | 80 | bar: 2026-09-26 to 2026-10-03
A85130 | Installation of instrumentation readout Detector #2 | 3 |  |  | 2.6667 |  | 320 |  | 2026-09-26: 2; 2026-10-03: 4; 2026-10-10: 2
|  |  | 1.3333 |  |  | 160 |  |  | 2026-09-26: 1; 2026-10-03: 2; 2026-10-10: 1
A85150 | Complete setup of the grey room for Detector #2 | 1 |  |  | 1.6667 |  | 200 |  | 2027-01-09: 1; 2027-01-16: 2; 2027-01-23: 2; 2027-01-30: 2; 2027-02-06: 1
|  |  | 1.6667 |  |  | 320 |  |  | 2027-01-09: 1; 2027-01-16: 2; 2027-01-23: 2; 2027-01-30: 2; 2027-02-06: 1
05.04.03 | Detector #2 Installation | [212 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
05.04.03.01 | Preparation for Installation |  |  |  |  | 2679.8 | 8320 | 1560 | [160 empty] | Step 0 - Preparation for FD2 Installation
A48435 | CRP Superstructure Cleaning and QC in the Hall |  |  |  | 3.2 |  | 1280 | [199 empty] | 2 | 4 | 1 | 4 | 4 | 4 | 4 | 1: 4; 2: 4; 3: 1
|  |  | 0.44444 |  |  | 160 | [200 empty] | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 1: 0.5; 2: 0.5; 3: 0
A364962 | Installation Top CRP Electronic Chimneys #2 |  |  |  | 4.4167 |  | 1590 | [185 empty] | 1.75 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4
|  |  |  | 1.6667 |  |  |  | 600 | [184 empty] | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
|  |  | 2.2078 |  |  | 794.8 | [186 empty] | 1 | 3 | 3 | 3 | 2.87 | 2 | 2 | 2 | 1
New Activity | Install uTCA Crates and T_CRP Electronics #2 |  |  |  | 1.0312 |  | 330 | [206 empty] | 5: 1.25; 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 1; 12: 1
|  |  | 0.51562 |  |  | 165 | [207 empty] | 5: 0.525; 6: 0.525; 7: 0.525; 8: 0.525; 9: 0.525; 10: 0.5; 11: 0.5; 12: 0.5
A47931 | Prepare Cryostat False Floor Parts for Installation |  |  |  | 3.2 |  | 1280 | [169 empty] | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 2
|  |  | 0.5 |  |  | 200 | [170 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
A50020 | Install Cryostat floor |  |  |  | 8 |  | 960 | [186 empty] | 8 | 8 | 8
|  |  | 1.3333 |  |  | 160 | [187 empty] | 0.5 | 2 | 1.5
A50030 | Rough Clean Cryostat |  |  |  | 8 |  | 960 | [203 empty] | 8 | 8 | 8
|  |  | 2 |  |  | 240 | [204 empty] | 2 | 2 | 2
A364832 | Installation Bot CRP Electronics Feed-Thru/Crosses/Warm Cables #2-Part 1 |  |  |  | 1.8462 |  | 960 | [200 empty] | 1 | 2 | 2 | 2 | 2 | 2 | 1: 2; 2: 2; 3: 2; 4: 2; 5: 2; 6: 2; 7: 1
|  |  |  | 0.61538 |  |  |  | 320 | [199 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1: 1; 2: 0.5; 3: 0.5; 4: 0.5; 5: 0.5; 6: 0.5; 7: 0.5
|  |  | 0.92308 |  |  | 480 | [201 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1: 1; 2: 1; 3: 1; 4: 1; 5: 1; 6: 1; 7: 0.5
A364833 | Installation Bot CRP Electronics Feed-Thru/Crosses/Warm Cables #2-Part 2 |  |  |  | 3 |  | 960 | [206 empty] | 8: 3; 9: 3; 10: 3; 11: 3; 12: 3; 13: 3; 14: 3; 15: 3
|  |  |  | 2 |  |  |  | 640 | [205 empty] | 8: 2; 9: 2; 10: 2; 11: 2; 12: 2; 13: 2; 14: 2; 15: 2
|  |  | 1.5 |  |  | 480 | [207 empty] | 8: 1; 9: 2; 10: 2; 11: 2; 12: 2; 13: 1; 14: 1; 15: 1
| MT - Total FTE hours | 8320 | [166 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 120 | 120 | 120 | 120 | 160 | 160 | 160 | 160 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 520 | 520 | 520 | 200 | 200 | 200 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 80 | 200 | 120 | 240 | 560 | 560 | 560 | 1: 240; 2: 240; 3: 120; 4: 80; 5: 130; 6: 120; 7: 80; 8: 160; 9: 160; 10: 160; 11: 160; 12: 160; 13: 120; 14: 120; 15: 120
| SrMT - Total FTE hours | 2679.8 | [166 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 140 | 200 | 180 | 114.8 | 80 | 80 | 80 | 40 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 40 | 60 | 140 | 140 | 140 | 1: 60; 2: 60; 3: 40; 4: 40; 5: 61; 6: 61; 7: 41; 8: 61; 9: 101; 10: 100; 11: 100; 12: 100; 13: 40; 14: 40; 15: 40
| Welder - Total Hours | 1560 | [166 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 40 | 40 | 1: 40; 2: 20; 3: 20; 4: 20; 5: 20; 6: 20; 7: 20; 8: 80; 9: 80; 10: 80; 11: 80; 12: 80; 13: 80; 14: 80; 15: 80
| T_CRP Consortia - Total FTE hours | 800 | [166 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [35 empty] | 4: 80; 5: 80; 6: 80; 7: 80; 8: 80; 9: 80; 10: 80; 11: 80; 12: 80; 13: 80
| B_Elec Consortia - Total FTE hours | 2240 | [205 empty] | 75 | 110 | 110 | 110 | 110 | 110 | 1: 110; 2: 110; 3: 110; 4: 110; 5: 110; 6: 110; 7: 110; 8: 110; 9: 110; 10: 110; 11: 110; 12: 110; 13: 110; 14: 110; 15: 75
| PD Consortia - Total FTE hours | 1260 | [205 empty] | 60 | 60 | 60 | 60 | 60 | 60 | 1: 60; 2: 60; 3: 60; 4: 60; 5: 60; 6: 60; 7: 60; 8: 60; 9: 60; 10: 60; 11: 60; 12: 60; 13: 60; 14: 60; 15: 60
| TDE Consortia - Total FTE hours | 1200 | [173 empty] | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120
| DAQ Consortia - Total FTE Hours | 2520 | [205 empty] | 120 | 120 | 120 | 120 | 120 | 120 | 1: 120; 2: 120; 3: 120; 4: 120; 5: 120; 6: 120; 7: 120; 8: 120; 9: 120; 10: 120; 11: 120; 12: 120; 13: 120; 14: 120; 15: 120

## FD2 Installation
Activity | Month | [150 empty] | 43 | [57 empty] | 44 | [67 empty] | 45 | [55 empty] | 46 | [69 empty] | 47
| Week | [8 empty] | Week 1 | [11 empty] | 2028-02-16 |  | Week 2 | [11 empty] | 2028-02-23 |  | Week 3 | [11 empty] | 2028-03-01 |  | Week 4 | [11 empty] | 2028-03-08 |  | Week 5 | [11 empty] | 2028-03-15 |  | Week 6 | [11 empty] | 2028-03-22 |  | Week 7 | [11 empty] | 2028-03-29 |  | Week 8 | [11 empty] | 2028-04-05 |  | Week 9 | [11 empty] | 2028-04-12 |  | Week 10 | [11 empty] | 2028-04-19 |  | Week 11 | [11 empty] | 2028-04-26 |  | Week 12 | [11 empty] | 2028-05-03 |  | Week 13 | [11 empty] | 2028-05-10 |  | Week 14 | [11 empty] | 2028-05-17 |  | Week 15 | [11 empty] | 2028-05-24 |  | Week 16 | [11 empty] | 2028-05-31 |  | Week 17 | [11 empty] | 2028-06-07 |  | Week 18 | [11 empty] | 2028-06-14 |  | Week 19 | [11 empty] | 2028-06-21 |  | Week 20 | [11 empty] | 2028-06-28 |  | Week 21 | [11 empty] | 2028-07-05 |  | Week 22 | [11 empty] | 2028-07-12 |  | Week 23 | [11 empty] | 2028-07-19 |  | Week 24 | [11 empty] | 2028-07-26 |  | Week 25 | [11 empty] | 2028-08-02 |  | Week 26 | [11 empty] | 2028-08-09 |  | Week 27 | [11 empty] | 2028-08-16 |  | Week 27 | [11 empty] | 2028-08-23 |  | Week 28 | [11 empty] | 2028-08-23 |  | Week 29 | [11 empty] | 2028-08-30 |  | Week 30 | [11 empty] | 2028-08-30 |  | Week 31 | [11 empty] | 2028-09-06
| Day | B_Elec | T_Elec | CRP | HV | PD | Cal | SrMT | MT | 2028-02-10 |  | 2028-02-11 |  | 2028-02-12 |  | 2028-02-13 |  | 2028-02-14 |  | 2028-02-15 |  | 2028-02-16 |  | 2028-02-17 |  | 2028-02-18 |  | 2028-02-19 |  | 2028-02-20 |  | 2028-02-21 |  | 2028-02-22 |  | 2028-02-23 |  | 2028-02-24 |  | 2028-02-25 |  | 2028-02-26 |  | 2028-02-27 |  | 2028-02-28 |  | 2028-02-29 |  | 2028-03-01 |  | 2028-03-02 |  | 2028-03-03 |  | 2028-03-04 |  | 2028-03-05 |  | 2028-03-06 |  | 2028-03-07 |  | 2028-03-08 |  | 2028-03-09 |  | 2028-03-10 |  | 2028-03-11 |  | 2028-03-12 |  | 2028-03-13 |  | 2028-03-14 |  | 2028-03-15 |  | 2028-03-16 |  | 2028-03-17 |  | 2028-03-18 |  | 2028-03-19 |  | 2028-03-20 |  | 2028-03-21 |  | 2028-03-22 |  | 2028-03-23 |  | 2028-03-24 |  | 2028-03-25 |  | 2028-03-26 |  | 2028-03-27 |  | 2028-03-28 |  | 2028-03-29 |  | 2028-03-30 |  | 2028-03-31 |  | 2028-04-01 |  | 2028-04-02 |  | 2028-04-03 |  | 2028-04-04 |  | 2028-04-05 |  | 2028-04-06 |  | 2028-04-07 |  | 2028-04-08 |  | 2028-04-09 |  | 2028-04-10 |  | 2028-04-11 |  | 2028-04-12 |  | 2028-04-13 |  | 2028-04-14 |  | 2028-04-15 |  | 2028-04-16 |  | 2028-04-17 |  | 2028-04-18 |  | 2028-04-19 |  | 2028-04-20 |  | 2028-04-21 |  | 2028-04-22 |  | 2028-04-23 |  | 2028-04-24 |  | 2028-04-25 |  | 2028-04-26 |  | 2028-04-27 |  | 2028-04-28 |  | 2028-04-29 |  | 2028-04-30 |  | 2028-05-01 |  | 2028-05-02 |  | 2028-05-03 |  | 2028-05-04 |  | 2028-05-05 |  | 2028-05-06 |  | 2028-05-07 |  | 2028-05-08 |  | 2028-05-09 |  | 2028-05-10 |  | 2028-05-11 |  | 2028-05-12 |  | 2028-05-13 |  | 2028-05-14 |  | 2028-05-15 |  | 2028-05-16 |  | 2028-05-17 |  | 2028-05-18 |  | 2028-05-19 |  | 2028-05-20 |  | 2028-05-21 |  | 2028-05-22 |  | 2028-05-23 |  | 2028-05-24 |  | 2028-05-25 |  | 2028-05-26 |  | 2028-05-27 |  | 2028-05-28 |  | 2028-05-29 |  | 2028-05-30 |  | 2028-05-31 |  | 2028-06-01 |  | 2028-06-02 |  | 2028-06-03 |  | 2028-06-04 |  | 2028-06-05 |  | 2028-06-06 |  | 2028-06-07 |  | 2028-06-08 |  | 2028-06-09 |  | 2028-06-10 |  | 2028-06-11 |  | 2028-06-12 |  | 2028-06-13 |  | 2028-06-14 |  | 2028-06-15 |  | 2028-06-16 |  | 2028-06-17 |  | 2028-06-18 |  | 2028-06-19 |  | 2028-06-20 |  | 2028-06-21 |  | 2028-06-22 |  | 2028-06-23 |  | 2028-06-24 |  | 2028-06-25 |  | 2028-06-26 |  | 2028-06-27 |  | 2028-06-28 |  | 2028-06-29 |  | 2028-06-30 |  | 2028-07-01 |  | 2028-07-02 |  | 2028-07-03 |  | 2028-07-04 |  | 2028-07-05 |  | 2028-07-06 |  | 2028-07-07 |  | 2028-07-08 |  | 2028-07-09 |  | 2028-07-10 |  | 2028-07-11 |  | 2028-07-12 |  | 2028-07-13 |  | 2028-07-14 |  | 2028-07-15 |  | 2028-07-16 |  | 2028-07-17 |  | 2028-07-18 |  | 2028-07-19 |  | 2028-07-20 |  | 2028-07-21 |  | 2028-07-22 |  | 2028-07-23 |  | 2028-07-24 |  | 2028-07-25 |  | 2028-07-26 |  | 2028-07-27 |  | 2028-07-28 |  | 2028-07-29 |  | 2028-07-30 |  | 2028-07-31 |  | 2028-08-01 |  | 2028-08-02 |  | 2028-08-03 |  | 2028-08-04 |  | 2028-08-05 |  | 2028-08-06 |  | 2028-08-07 |  | 2028-08-08 |  | 2028-08-09 |  | 2028-08-10 |  | 2028-08-11 |  | 2028-08-12 |  | 2028-08-13 |  | 2028-08-14 |  | 2028-08-15 |  | 2028-08-16 |  | 2028-08-17 |  | 2028-08-18 |  | 2028-08-19 |  | 2028-08-20 |  | 2028-08-21 |  | 2028-08-22 |  | 2028-08-23 |  | 2028-08-17 |  | 2028-08-18 |  | 2028-08-19 |  | 2028-08-20 |  | 2028-08-21 |  | 2028-08-22 |  | 2028-08-23 |  | 2028-08-24 |  | 2028-08-25 |  | 2028-08-26 |  | 2028-08-27 |  | 2028-08-28 |  | 2028-08-29 |  | 2028-08-30 |  | 2028-08-24 |  | 2028-08-25 |  | 2028-08-26 |  | 2028-08-27 |  | 2028-08-28 |  | 2028-08-29 |  | 2028-08-30 |  | 2028-08-31 |  | 2028-09-01 |  | 2028-09-02 |  | 2028-09-03 |  | 2028-09-04 |  | 2028-09-05 |  | 2028-09-06 |  |  |  | FTE | FTE
| Schedule dates based of P6 output June, 2023 output | # FTE | # FTE | # FTE | # FTE | # FTE | # FTE | # FTE | # FTE | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM |  |  | Days | Hrs
50010 | Crew Training, Dry Runs Proceedure - Step 1 | [7 empty] | 2.6667 | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  |  |  | 4 |  | 4 |  | 0 |  | 0 |  | 0 |  | 0 | [423 empty] | 50010 |  | 32 | 320 | MT
[8 empty] | 1.6667 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 1 |  | 1 |  | 1 |  | 1 | [425 empty] | 20 | 200 | SrMT
|  | 2 | [7 empty] | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | [425 empty] | 24 | 240 | B_Elec
[6 empty] | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | [425 empty] | 24 | 240 | PD
|  |  |  | 2 | [5 empty] | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | [425 empty] | 24 | 240 | CRP
ORC cryostat roof cable tray installation ORC TDE/CRP cable installation ORC CRP super structure assembly ORC wall calbe tray support installation ORC CRP support winch instalation and operation ORC CRP support hoisting ORC wall PD installation ORC BDE cable and cable tray installation ORC Roof penetration leak testing ORC HV extender installation Crew training
51200 | Bring cleanroom into operation | [7 empty] | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  |  |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 | [422 empty] | 51200 |  | 48 | 480 | MT
[8 empty] | 1 |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | [424 empty] | 12 | 120 | SrMT
Close tarp walls , turn on air filters and env. Monitoring. 2-Shifts Clean changing room walls, floor, tools and furnishings. 2-Shifts Bring supplies into changing rooms and train CR proceedures 1-Shift Clean all grey room walls and floor 3-Shifts Clean all furnishings and equipment 4-Shifts 12 evening Shifts total
50030 | Rough Clean Cryostat | [7 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [422 empty] | 50030 |  | 96 | 960 | MT
[8 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [424 empty] | 24 | 240 | SrMT
Clean Cryostat Walls and floor, Check floor ESD, Bring lifts into cryostat.
Two Scissor lifts with 2 cleaners on each and one ground person.
50630 | Install HV feedthru and extender | [7 empty] | 4 | [18 empty] | 4 |  | 4 | [427 empty] | 50630 |  | 8 | 80 | MT
[8 empty] | 1 | [19 empty] | 1 |  | 1 | [429 empty] | 2 | 20 | SrMT
[5 empty] | 2 | [22 empty] | 2 |  | 2 | [429 empty] | 4 | 40 | HV
Install HV feedthrough 4hr
Install HV extender 7h
Check continuity 2hr
50050 | Install East wall PD | [7 empty] | 4 | [22 empty] | 4 |  | 4 | [423 empty] | 50050 |  | 8 | 80 | MT
[8 empty] | 1 | [23 empty] | 1 |  | 1 | [425 empty] | 2 | 20 | SrMT
[6 empty] | 2 | [25 empty] | 2 |  | 2 | [425 empty] | 4 | 40 | PD
51230 | Prepare Membrane PDs installation and move materials for PD consortia to test Membrane XA | [7 empty] | 0
0
[6 empty] | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
Place support kits near install location
Install lifting eyes on M10 bolts
50220 | Install T_CRP circular cable trays and internal signal flat cables: Two teams I&I help first install the mechanical cable trays for 18 shifts then they assist in installing the cables for 18 shifts | [7 empty] | 3 | [28 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [380 empty] | 50220 |  | 162 | 1620 | MT
[8 empty] | 1.5 | [29 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [382 empty] | 54 | 540 | SrMT
|  |  |  | 2 | [33 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [382 empty] | 108 | 1080 | CRP
First 1-1/2 weeks install mechanical cable trays - 3 scissor lifts Second 1-1/2 weeks Two scissor lifts. One I&I and one CRP in each lift. One I&I on the ground plus 1 SrMT 3 FTE CRP consortia
50230 | Install CRP_SS support flanges and winch mounts | [7 empty] | 3 | [42 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [394 empty] | 50230 |  | 36 | 360 | MT
[8 empty] | 1 | [43 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [396 empty] | 12 | 120 | SrMT
|  |  |  | 1 | [47 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [396 empty] | 12 | 120 | CRP
Mount 4 CRP support flanges on cryostat roof 2hr 4I&I 1CRP (2I&I teams)
Leakcheck and survey 4 CRP roof feedthrough 2hr 4I&I. (2I&I teams)
Load test some or all the winches to be determined
16 SST x 4 support flanges=64 flanges need 5 per shift for 1 week
51210 | Build 12 Large SST: The 4 small Super Structures are one piece. The 12 Large ones come in 3 pieces that need to be bolted otgether | [7 empty] | 3 | [57 empty] | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  |  |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 | [366 empty] | 51210 |  | 36 | 360 | MT
[8 empty] | 1 | [58 empty] | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | [368 empty] | 12 | 120 | SrMT
|  |  |  | 1 | [62 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [368 empty] | 0 | 0 | CRP
Transport CRP support structure pieces into cryostat 1hr 3I&I
Assemble CRP support structure 3hr 3I&I
Survey and adjust CRP support structure 5hr 3I&I
2 shifts per CRP support structure - total 16 days
51220 | Install and Survey 4 small SST and 12 Large SST | [7 empty] | 3 | [56 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | [360 empty] | 51220 |  | 84 | 840 | MT
[8 empty] | 1 | [57 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | [362 empty] | 28 | 280 | SrMT
|  |  |  | 3 | [61 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | [362 empty] | 56 | 560 | CRP
Move SS to location attach winch ropes 4MT 1hr
Lift CRP support structure 2hr 4I&I 3CRP
Disconnect winches . 4MT 3CRP 1hr
Survey of all CRP connectors 2 CRP 1 shift
1 shift to lift CRP_SST 1 shift to Survey CRP_SST 16 support structures - 32 shifts
50090 | Install thermometers and purity monitor mount-Day Shift | [7 empty] | 1 | [44 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [396 empty] | 50090 |  | 8 | 80 | MT
[7 empty] | 4 | [46 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [398 empty] | 32 | 320 | Calci
51240 | Install top cryostat support wall cable tray and membrane PD | [7 empty] | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [422 empty] | 51240 |  | 88 | 880 | MT
[8 empty] | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [424 empty] | 22 | 220 | SrMT
Crew of two people in two scissor lifts and one on the ground. 40 cable tray supports and 38 I-Beams. Install 2 supports 1.5 hr Install one I-Beam 1hr Two support I-Beam per shift and 20 shifts total
51250 | Install floor eyebolts, Eall PD support, and BDS cable tray brackets | [7 empty] | 3 | [28 empty] | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | [408 empty] | 51250 |  | 84 | 840 | MT
[8 empty] | 1 | [29 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [410 empty] | 12 | 120 | SrMT
|  | 2 | [35 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [410 empty] | 24 | 240 | CRP
Chase M-10 bolts and install eyebolts 4MT 2 shifts Install Wall PDS support strings 4MT 2PDS 4 shifts Epoxy BDC cable tray guides to membrane 4 MT 6 shifts Load test top cable tray supports in parallel
50070 | Row 1 & 2: Install B_Elec Cable trays and Arapuca modules | [7 empty] | 7 | [42 empty] | 7 | 7 | 7 | 7
[8 empty] | 1 | [43 empty] | 1 | 1 | 1 | 1
|  | 6 | [49 empty] | 2 | 2 | 4 | 4 | 4 | [401 empty] | 50070 |  | 56 | 560 | MT
[6 empty] | 4 | [45 empty] | 2 | 2 | 4 | 4 | 4 | [403 empty] | 8 | 80 | SrMT
[460 empty] | 32 | 320 | B_Elec
[460 empty] | 32 | 320
[460 empty] | 28 | 280
[460 empty] | 4 | 40
[460 empty] | 16 | 160
[9 empty] | 7 | [46 empty] | 7 | 7 | 7 | 7 | [400 empty] | 32 | 320 | B_Elec
[8 empty] | 1 | [47 empty] | 1 | 1 | 1 | 1 | [400 empty] | 32 | 320 | PD
|  | 4 | [53 empty] | 2 | 2 | 4 | 4 | 4
[6 empty] | 4 | [49 empty] | 2 | 2 | 4 | 4 | 4
50080 | Row 3 & 4: Install B_Elec Cable trays and Arapuca modules | [7 empty] | 7 | [50 empty] | 7 | 7 | 7 | 7
[8 empty] | 1 | [51 empty] | 1 | 1 | 1 | 1
|  | 6 | [57 empty] | 2 | 2 | 4 | 4 |  |  | 4 | [391 empty] | 50080 |  | 56 | 560 | MT
[6 empty] | 4 | [53 empty] | 2 | 2 | 4 | 4 |  |  | 4 | [393 empty] | 8 | 80 | SrMT
[9 empty] | 7 | [56 empty] | 7 | 7 | 7 | 7 | [390 empty] | 32 | 320 | B_Elec
[8 empty] | 1 | [57 empty] | 1 | 1 | 1 | 1 | [390 empty] | 32 | 320 | PD
|  | 6 | [63 empty] | 2 | 2 | 4 | 4 | 4
[6 empty] | 4 | [59 empty] | 2 | 2 | 4 | 4 | 4
50090 | Row 5 & 6: Install B_Elec Cable trays and Arapuca modules | [7 empty] | 7 | [60 empty] | 7 | 7 | 7 | 7
[8 empty] | 1 | [61 empty] | 1 | 1 | 1 | 1
|  | 6 | [67 empty] | 2 | 2 | 4 | 4 | 4 | [383 empty] | 50090 |  | 56 | 560 | MT
[6 empty] | 4 | [63 empty] | 2 | 2 | 4 | 4 | 4 | [385 empty] | 8 | 80 | SrMT
[9 empty] | 7 | [64 empty] | 7 | 7 | 7 | 7 | [382 empty] | 32 | 320 | B_Elec
[8 empty] | 1 | [65 empty] | 1 | 1 | 1 | 1 | [382 empty] | 32 | 320 | PD
|  | 6 | [71 empty] | 2 | 2 | 4 | 4 |  |  | 4
[6 empty] | 4 | [67 empty] | 2 | 2 | 4 | 4 |  |  | 4
50100 | Row 7 & 8: Install B_Elec Cable trays and Arapuca modules | [7 empty] | 7 | [70 empty] | 7 | 7 | 7 | 7
[8 empty] | 1 | [71 empty] | 1 | 1 | 1 | 1
|  | 6 | [77 empty] | 2 | 2 | 4 | 4 | 4 | [373 empty] | 50100 |  | 56 | 560 | MT
[6 empty] | 4 | [73 empty] | 2 | 2 | 4 | 4 | 4 | [375 empty] | 8 | 80 | SrMT
[9 empty] | 7 | [74 empty] | 7 | 7 | 7 | 7 | [372 empty] | 32 | 320 | B_Elec
[8 empty] | 1 | [75 empty] | 1 | 1 | 1 | 1 | [372 empty] | 32 | 320 | PD
|  | 6 | [81 empty] | 2 | 2 | 4 | 4 | 4
[6 empty] | 4 | [77 empty] | 2 | 2 | 4 | 4 | 4
50110 | Row 9 & 10: Install B_Elec Cable trays and Arapuca modules | [7 empty] | 7 | [78 empty] | 7 | 7 | 7 | 7
[8 empty] | 1 | [79 empty] | 1 | 1 | 1 | 1
|  | 6 | [85 empty] | 2 | 2 | 4 | 4 |  |  | 4 | [363 empty] | 50110 |  | 56 | 560 | MT
[6 empty] | 4 | [81 empty] | 2 | 2 | 4 | 4 |  |  | 4 | [365 empty] | 8 | 80 | SrMT
[9 empty] | 7 | [84 empty] | 7 | 7 | 7 | 7 | [362 empty] | 32 | 320 | B_Elec
[8 empty] | 1 | [85 empty] | 1 | 1 | 1 | 1 | [362 empty] | 32 | 320 | PD
|  | 6 | [91 empty] | 2 | 2 | 4 | 4 | 4
[6 empty] | 4 | [87 empty] | 2 | 2 | 4 | 4 | 4
50120 | Row 11 & 12: Install B_Elec Cable trays and Arapuca modules | [7 empty] | 7 | [88 empty] | 7 | 7 | 7 | 7
[8 empty] | 1 | [89 empty] | 1 | 1 | 1 | 1
|  | 6 | [95 empty] | 2 | 2 | 4 | 4 | 4 | [355 empty] | 50120 |  | 56 | 560 | MT
[6 empty] | 4 | [91 empty] | 2 | 2 | 4 | 4 | 4 | [357 empty] | 8 | 80 | SrMT
[9 empty] | 7 | [92 empty] | 7 | 7 | 7 | 7 | [354 empty] | 32 | 320 | B_Elec
[8 empty] | 1 | [93 empty] | 1 | 1 | 1 | 1 | [354 empty] | 32 | 320 | PD
|  | 6 | [99 empty] | 2 | 2 | 4 | 4 |  |  | 4
[6 empty] | 4 | [95 empty] | 2 | 2 | 4 | 4 |  |  | 4
50130 | Row 13 & 14: Install B_Elec Cable trays and Arapuca modules | [7 empty] | 7 | [98 empty] | 7 | 7 | 7 | 7
[8 empty] | 1 | [99 empty] | 1 | 1 | 1 | 1
|  | 6 | [105 empty] | 2 | 2 | 4 | 4 | 4 | [345 empty] | 50130 |  | 56 | 560 | MT
[6 empty] | 4 | [101 empty] | 2 | 2 | 4 | 4 | 4 | [347 empty] | 8 | 80 | SrMT
[9 empty] | 7 | [102 empty] | 7 | 7 | 7 | 7 | [344 empty] | 32 | 320 | B_Elec
[8 empty] | 1 | [103 empty] | 1 | 1 | 1 | 1 | [344 empty] | 32 | 320 | PD
|  | 6 | [109 empty] | 2 | 2 | 4 | 4 | 4
[6 empty] | 4 | [105 empty] | 2 | 2 | 4 | 4 | 4
50140 | Row 15 & 16: Install B_Elec Cable trays and Arapuca modules | [7 empty] | 7 | [106 empty] | 7 | 7 | 7 | 7
[8 empty] | 1 | [107 empty] | 1 | 1 | 1 | 1
|  | 6 | [113 empty] | 2 | 2 | 4 | 4 |  |  | 4 | [335 empty] | 50140 |  | 56 | 560 | MT
[6 empty] | 4 | [109 empty] | 2 | 2 | 4 | 4 |  |  | 4 | [337 empty] | 8 | 80 | SrMT
[9 empty] | 7 | [112 empty] | 7 | 7 | 7 | 7 | [334 empty] | 32 | 320 | B_Elec
[8 empty] | 1 | [113 empty] | 1 | 1 | 1 | 1 | [334 empty] | 32 | 320 | PD
|  | 6 | [119 empty] | 2 | 2 | 4 | 4 | 4
[6 empty] | 4 | [115 empty] | 2 | 2 | 4 | 4 | 4
50150 | Row 17 & 18: Install B_Elec Cable trays and Arapuca modules | [7 empty] | 7 | [116 empty] | 7 | 7 | 7 | 7
[8 empty] | 1 | [117 empty] | 1 | 1 | 1 | 1
|  | 6 | [123 empty] | 2 | 2 | 4 | 4 | 4 | [327 empty] | 50150 |  | 56 | 560 | MT
[6 empty] | 4 | [119 empty] | 2 | 2 | 4 | 4 | 4 | [329 empty] | 8 | 80 | SrMT
[9 empty] | 7 | [120 empty] | 7 | 7 | 7 | 7 | [326 empty] | 32 | 320 | B_Elec
[8 empty] | 1 | [121 empty] | 1 | 1 | 1 | 1 | [326 empty] | 32 | 320 | PD
|  | 6 | [127 empty] | 2 | 2 | 4 | 4 |  |  | 4
[6 empty] | 4 | [123 empty] | 2 | 2 | 4 | 4 |  |  | 4
50160 | Row 19 & 20: Install B_Elec Cable trays and Arapuca modules | [7 empty] | 7 | [126 empty] | 7 | 7 | 7 | 7
[8 empty] | 1 | [127 empty] | 1 | 1 | 1 | 1
|  | 6 | [133 empty] | 2 | 2 | 4 | 4 | 4 | [317 empty] | 50160 |  | 56 | 560 | MT
[6 empty] | 4 | [129 empty] | 2 | 2 | 4 | 4 | 4 | [319 empty] | 8 | 80 | SrMT
[9 empty] | 7 | [130 empty] | 7 | 7 | 7 | 7 | [316 empty] | 32 | 320 | B_Elec
[8 empty] | 1 | [131 empty] | 1 | 1 | 1 | 1 | [316 empty] | 32 | 320 | PD
|  | 6 | [137 empty] | 2 | 2 | 4 | 4 | 4
[6 empty] | 4 | [133 empty] | 2 | 2 | 4 | 4 | 4
50170 | Cleanup Steup 1 | [7 empty] | 7 | [135 empty] | 7 | 7.6 | [311 empty] | 50170 |  | 14.6 | 146 | MT
[8 empty] | 1 | [136 empty] | 1 | 1 | [313 empty] | 2 | 20 | SrMT
Step1 05.04.03.02 | Circular Cable tray, SST-CRP Super Structure, Install membrane PDs, Bot_Elec cable trays and cables | [7 empty] | 7 | 8 | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  |  | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 |  |  | 16 | 16 | 17 | 17 | 17 | 17 | 14 | 14 | 14 | 14 | 13 | 13 |  |  | 13 | 16 | 13 | 16 | 13 | 16 | 13 | 16 | 13 | 16 | 13 | 16 |  |  | 10 | 13 | 10 | 13 | 10 | 13 | 10 | 13 | 10 | 13 | 10 | 13 |  |  | 10 | 10 | 10 | 10 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 |  |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 |  |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 |  |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 7 | 7.6 | 0 | [310 empty] | PD BElec Cable |  | 1264.6 | 12646 | MT
[8 empty] | 1 |  | 3 | 2 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 |  |  | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | S | S | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | T |  | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 |  | W | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | A | L | 2 | 3 | 2 | 3 | 2 | 3 | 2 | 3 | 2 | 3 | 2 | 3 | L |  | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | P | D | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | [312 empty] | 282 | 2820 | SrMT
|  |  |  | 2 | [5 empty] | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 |  |  | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [312 empty] | 200 | 2000 | CRP
|  | 6 | [7 empty] | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 |  | B | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 |  | E | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | L | E | 2 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | C |  | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | & |  | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | C | I | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | R |  | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | C | A | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | B | L | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 4 | 0 | 0 | 0 | E | [311 empty] | 368 | 3680 | B_Elec
[6 empty] | 4 |  |  |  | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 |  |  | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 6 | 0 | 6 | 0 |  |  | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 |  |  | 4 | 2 | 6 | 4 | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 |  |  | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 |  |  | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 |  |  | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 |  |  | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 |  |  | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 |  |  | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 4 | 0 | 0 | 0 | [312 empty] | 444 | 4440 | PD
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [312 empty] | 32 | 320 | Calci
50190 | Setup Top CRP Installation equipment, Crew Training, Dry Runs of Procedures | [7 empty] | 2 | [70 empty] | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | [353 empty] | 50190 |  | 24 | 240 | MT
[5 empty] | 2 | [74 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [355 empty] | 0 | 0 | HV
|  |  |  | 4 | [75 empty] | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | [355 empty] | 24 | 240 | CRP
[6 empty] | 1 | [73 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [355 empty] | 0 | 0 | PD
|  |  | 2 | [76 empty] | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | [355 empty] | 24 | 240 | T_Elec
50200 | Material Handling : Top CRP & Cathode Module: Receive CRP crates, Cathode assembly and Arapucas. Prep each crate. Unpack shipping crates outside gray room, clean and move inside | [7 empty] | 1 | [70 empty] | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | [213 empty] | 50200 |  | 72 | 720 | MT
[5 empty] | 1 | [74 empty] | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | [215 empty] | 72 | 720 | HV
[6 empty] | 2 | [73 empty] | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | [215 empty] | 144 | 1440 | PD
|  |  |  | 2 | [159 empty] | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | [217 empty] | 70 | 700 | CRP
At assembly table (cryostat) assembly/QC 2 panel sections 2hr
Test and install the 4 Arapuca modules in each Cathode plane 6hr
50210 | Support for consortia preparation activities Top CRP & Cathode Modules: including assembly of CRU into CRP | [7 empty] | 1 | [70 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [142 empty] | 50210 |  | 204 | 2040 | MT
[8 empty] | 1 | [71 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [144 empty] | 204 | 2040 | SrMT
50240 | Install CRP 1 & 2 on SS1: Install CRPs 1 and 2 move using the X-Y lift table to raise to cabling height-Cable and test, raise to final position and attach to Super Structure | [7 empty] | 4 | [98 empty] | 4 | 4 | [348 empty] | 50240 |  | 8 | 80 | MT
[8 empty] | 1 | [99 empty] | 1 | 1 | [350 empty] | 2 | 20 | SrMT
|  |  |  | 3 | [103 empty] | 3 | 3 | [350 empty] | 6 | 60 | CRP
|  |  | 1 | [104 empty] | 1 | 1 | [350 empty] | 2 | 20 | T_Elec
50260 | Install CRP 3 & 4 on SS2: Install CRPs 3 and 4 move using the X-Y lift table to raise to cabling height-Cable and test, raise to final position and attach to Super Structure | [7 empty] | 4 | [100 empty] | 4 | 4 | [346 empty] | 50260 |  | 8 | 80 | MT
[8 empty] | 1 | [101 empty] | 1 | 1 | [348 empty] | 2 | 20 | SrMT
|  |  |  | 3 | [105 empty] | 3 | 3 | [348 empty] | 6 | 60 | CRP
|  |  | 1 | [106 empty] | 1 | 1 | [348 empty] | 2 | 20 | T_Elec
50280 | Install CRP 5-10 on SS3: Install CRPs 5 - 10 move using the X-Y lift table to raise to cabling height-Cable and test, raise to final position and attach to Super Structure | [7 empty] | 4 | [102 empty] | 4 | 4 | 4 | 4 | 4 | 4 | [340 empty] | 50280 |  | 24 | 240 | MT
[8 empty] | 1 | [103 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [342 empty] | 6 | 60 | SrMT
|  |  |  | 3 | [107 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [342 empty] | 18 | 180 | CRP
|  |  | 1 | [108 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [342 empty] | 6 | 60 | T_Elec
50310 | Install CRPs 11 - 16 on SS4: Install CRPs 11 - 16 move using the X-Y lift table to raise to cabling height-Cable and test, raise to final position and attach to Super Structure | [7 empty] | 4 | [108 empty] | 4 | 4 |  |  | 4 | 4 | 4 | 4 | [332 empty] | 50310 |  | 24 | 240 | MT
[8 empty] | 1 | [109 empty] | 1 | 1 |  |  | 1 | 1 | 1 | 1 | [334 empty] | 6 | 60 | SrMT
|  |  |  | 3 | [113 empty] | 3 | 3 |  |  | 3 | 3 | 3 | 3 | [334 empty] | 18 | 180 | CRP
|  |  | 1 | [114 empty] | 1 | 1 |  |  | 1 | 1 | 1 | 1 | [334 empty] | 6 | 60 | T_Elec
50330 | Noise Test #1: Close Cryostat and test for noise 2MT 2 TDE | [7 empty] | 4 | [115 empty] | Test | 4 | 4 | [330 empty] | 50330 |  | 8 | 80 | MT
|  |  | 1 | [122 empty] | 1 | 1 | [332 empty] | 2 | 20 | T_Elec
50340 | Install CRPs 17 - 22 on SS5: Install CRPs 17 - 22 move using the X-Y lift table to raise to cabling height-Cable and test, raise to final position and attach to Super Structure | [7 empty] | 4 | [118 empty] | 4 | 4 | 4 | 4 | 4 | 4 | [324 empty] | 50340 |  | 24 | 240 | MT
[8 empty] | 1 | [119 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [326 empty] | 6 | 60 | SrMT
|  |  |  | 3 | [123 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [326 empty] | 18 | 180 | CRP
|  |  | 1 | [124 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [326 empty] | 6 | 60 | T_Elec
50350 | Install CRPs 23 - 28 on SS6: Install CRPs 23 - 28 move using the X-Y lift table to raise to cabling height-Cable and test, raise to final position and attach to Super Structure | [7 empty] | 4 | [126 empty] | 4 | 4 | 4 | 4 | 4 | 4 | [316 empty] | 50350 |  | 24 | 240 | MT
[8 empty] | 1 | [127 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [318 empty] | 6 | 60 | SrMT
|  |  |  | 3 | [131 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [318 empty] | 18 | 180 | CRP
|  |  | 1 | [132 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [318 empty] | 6 | 60 | T_Elec
50370 | Install CRPs 29 - 34 on SS7: Install CRPs 29 - 34 move using the X-Y lift table to raise to cabling height-Cable and test, raise to final position and attach to Super Structure | [7 empty] | 4 | [132 empty] | 4 | 4 | 4 | 4 | 4 | 4 | [310 empty] | 50370 |  | 24 | 240 | MT
[8 empty] | 1 | [133 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [312 empty] | 6 | 60 | SrMT
|  |  |  | 3 | [137 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [312 empty] | 18 | 180 | CRP
|  |  | 1 | [138 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [312 empty] | 6 | 60 | T_Elec
50390 | Noise Test #2: Close Cryostat and test for noise 2MT 2 TDE | [7 empty] | 4 | [140 empty] | 4 | 4 | Test | [305 empty] | 50390 |  | 8 | 80 | MT
|  |  | 1 | [146 empty] | 1 | 1 | [308 empty] | 2 | 20 | T_Elec
50400 | Install CRPs 35 - 40 on SS8: Install CRPs 35 - 40 move using the X-Y lift table to raise to cabling height-Cable and test, raise to final position and attach to Super Structure | [7 empty] | 4 | [142 empty] | 4 | 4 | 4 | 4 | 4 | 4 | [300 empty] | 50400 |  | 24 | 240 | MT
[8 empty] | 1 | [143 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [302 empty] | 6 | 60 | SrMT
|  |  |  | 3 | [147 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [302 empty] | 18 | 180 | CRP
|  |  | 1 | [148 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [302 empty] | 6 | 60 | T_Elec
50420 | Install CRPs 41 - 46 on SS9: Install CRPs 41 - 46 move using the X-Y lift table to raise to cabling height-Cable and test, raise to final position and attach to Super Structure | [7 empty] | 4 | [148 empty] | 4 | 4 | 4 | 4 |  |  | 4 | 4 | [292 empty] | 50420 |  | 24 | 240 | MT
[8 empty] | 1 | [149 empty] | 1 | 1 | 1 | 1 |  |  | 1 | 1 | [294 empty] | 6 | 60 | SrMT
|  |  |  | 3 | [153 empty] | 3 | 3 | 3 | 3 |  |  | 3 | 3 | [294 empty] | 18 | 180 | CRP
|  |  | 1 | [154 empty] | 1 | 1 | 1 | 1 |  |  | 1 | 1 | [294 empty] | 6 | 60 | T_Elec
50440 | Install CRPs 47 - 52 on SS10: Install CRPs 47 - 52 move using the X-Y lift table to raise to cabling height-Cable and test, raise to final position and attach to Super Structure | [7 empty] | 4 | [156 empty] | 4 | 4 | 4 | 4 | 4 | 4 | [286 empty] | 50440 |  | 24 | 240 | MT
[8 empty] | 1 | [157 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [288 empty] | 6 | 60 | SrMT
|  |  |  | 3 | [161 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [288 empty] | 18 | 180 | CRP
|  |  | 1 | [162 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [288 empty] | 6 | 60 | T_Elec
50460 | Install CRPs 53 - 58 on SS11: Install CRPs 53 - 58 move using the X-Y lift table to raise to cabling height-Cable and test, raise to final position and attach to Super Structure | [7 empty] | 4 | [162 empty] | 4 | 4 | 4 | 4 |  |  | 4 | 4 | [278 empty] | 50460 |  | 24 | 240 | MT
[8 empty] | 1 | [163 empty] | 1 | 1 | 1 | 1 |  |  | 1 | 1 | [280 empty] | 6 | 60 | SrMT
|  |  |  | 2 | [167 empty] | 3 | 3 | 3 | 3 |  |  | 3 | 3 | [280 empty] | 18 | 180 | CRP
|  |  | 1 | [168 empty] | 1 | 1 | 1 | 1 |  |  | 1 | 1 | [280 empty] | 6 | 60 | T_Elec
50480 | Install CRPs 59 - 64 on SS12: Install CRPs 59 - 64 move using the X-Y lift table to raise to cabling height-Cable and test, raise to final position and attach to Super Structure | [7 empty] | 4 | [170 empty] | 4 | 4 | 4 | 4 | 4 | 4 | [272 empty] | 50480 |  | 24 | 240 | MT
[8 empty] | 1 | [171 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [274 empty] | 6 | 60 | SrMT
|  |  |  | 2 | [175 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [274 empty] | 18 | 180 | CRP
|  |  | 1 | [176 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [274 empty] | 6 | 60 | T_Elec
50500 | Noise Test #3: Close Cryostat and test for noise 2MT 2 TDE | [7 empty] | 4 | [175 empty] | Test | 4 | 4 | [270 empty] | 50500 |  | 8 | 80 | MT
|  |  | 1 | [182 empty] | 1 | 1 | [272 empty] | 2 | 20 | T_Elec
50510 | Install CRPs 65 - 70 on SS13: Install CRPs 65 - 70 move using the X-Y lift table to raise to cabling height-Cable and test, raise to final position and attach to Super Structure | [7 empty] | 4 | [178 empty] | 4 | 4 |  |  | 4 | 4 | 4 | 4 | [262 empty] | 50510 |  | 24 | 240 | MT
[8 empty] | 1 | [179 empty] | 1 | 1 |  |  | 1 | 1 | 1 | 1 | [264 empty] | 6 | 60 | SrMT
|  |  |  | 2 | [183 empty] | 3 | 3 |  |  | 3 | 3 | 3 | 3 | [264 empty] | 18 | 180 | CRP
|  |  | 1 | [184 empty] | 1 | 1 |  |  | 1 | 1 | 1 | 1 | [264 empty] | 6 | 60 | T_Elec
50530 | Install CRPs 70 - 76 on SS14: Install CRPs 70 - 76 move using the X-Y lift table to raise to cabling height-Cable and test, raise to final position and attach to Super Structure | [7 empty] | 4 | [186 empty] | 4 | 4 | 4 | 4 | 4 | 4 | [256 empty] | 50530 |  | 24 | 240 | MT
[8 empty] | 1 | [187 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [258 empty] | 6 | 60 | SrMT
|  |  |  | 2 | [191 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [258 empty] | 18 | 180 | CRP
|  |  | 1 | [192 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [258 empty] | 6 | 60 | T_Elec
50550 | Install CRPs 77 - 78 on SS15: Install CRPs 77 - 78 move using the X-Y lift table to raise to cabling height-Cable and test, raise to final position and attach to Super Structure- One shift added because of limited access | [7 empty] | 4 | [192 empty] | 4 | 4 |  |  | 4 | [251 empty] | 50550 |  | 12 | 120 | MT
[8 empty] | 1 | [193 empty] | 1 | 1 |  |  | 1 | [253 empty] | 3 | 30 | SrMT
|  |  |  | 2 | [197 empty] | 3 | 3 |  |  | 3 | [253 empty] | 9 | 90 | CRP
|  |  | 1 | [198 empty] | 1 | 1 |  |  | 1 | [253 empty] | 3 | 30 | T_Elec
50570 | Install CRPs 79 - 80 on SS16: Install CRPs 79 - 80 move using the X-Y lift table to raise to cabling height-Cable and test, raise to final position and attach to Super Structure - One shift added because of limited access | [7 empty] | 4 | [197 empty] | 4 | 4 | 4 | [248 empty] | 50570 |  | 12 | 120 | MT
[8 empty] | 1 | [198 empty] | 1 | 1 | 1 | [250 empty] | 3 | 30 | SrMT
|  |  |  | 2 | [202 empty] | 3 | 3 | 3 | [250 empty] | 9 | 90 | CRP
|  |  | 1 | [203 empty] | 1 | 1 | 1 | [250 empty] | 3 | 30 | T_Elec
50590 | Noise Test #4: Close Cryostat and test for noise 2MT 2 TDE | [7 empty] | 4 | [199 empty] | Test | 4 | 4 | [246 empty] | 50590 |  | 8 | 80 | MT
|  |  | 1 | [206 empty] | 1 | 1 | [248 empty] | 2 | 20 | T_Elec
Step 2 05.04.03.03 | Installation of Top CRP | [7 empty] | 1 | [70 empty] | 4 | 1 | 4 | 1 | 4 | 1 | 4 | 1 | 4 | 1 | 4 | 1 |  |  | 4 | 1 | 4 | 1 | 4 | 1 | 4 | 1 | 4 | 1 | 4 | 1 |  |  | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 |  |  | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 |  |  | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 |  |  | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 |  |  | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 |  |  | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 |  |  | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 | 6 | 5 |  |  | 6 | 5 | 6 | 5 | 6 | 5 | 2 | 1 | 2 | 1 | 2 | 1 | [240 empty] | Top CRP |  | 564 | 5640 | MT
[8 empty] | 1 | [71 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | T | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | O | P | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | C | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | R | P | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [242 empty] | 202 | 2020 | SrMT
|  |  |  | 2 | [75 empty] | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 |  |  | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 |  |  | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 2 | 0 | 5 | 3 |  |  | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 |  |  | 5 | 3 | 5 | 3 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | [242 empty] | 318 | 3180 | CRP
|  |  | 2 | [76 empty] | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 |  |  | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | [242 empty] | 114 | 1140 | T_Elec
50660 | Setup for Field Cage Assembly: First 2 days are HV Underground Training, Setup HV FC cathode assembly | [7 empty] | 2 | [126 empty] | 0 |  | 0 |  | 2 |  | 2 | [315 empty] | 50660 |  | 4 | 40 | MT
[5 empty] | 2 | [130 empty] | 2 |  | 2 |  | 2 |  | 2 | [317 empty] | 8 | 80 | HV
[6 empty] | 1 | [129 empty] | 2 |  | 2 |  | 2 |  | 2 | [317 empty] | 8 | 80 | PD
50670 | Support Field Cage module fabrication | [7 empty] | 1 | [126 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [198 empty] | 50670 |  | 108 | 1080 | MT
[8 empty] | 1 | [451 empty] | 0 | 0 | SrMT
[5 empty] | 4 | [130 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [200 empty] | 432 | 4320 | HV
50650 | Prepare for Field Cage installation, Crew Training, dry runs & procedure review | [7 empty] | 2 | [134 empty] | 2 |  | 2 |  |  |  | 2 |  | 2 | [305 empty] | 50650 |  | 8 | 80 | MT
[144 empty] | 2 |  | 2 |  |  |  | 2 |  | 2 | [307 empty] | 8 | 80 | HV
[6 empty] | 1 | [137 empty] | 2 |  | 2 |  |  |  | 2 |  | 2 | [307 empty] | 8 | 80 | PD
50680 | Install Field Cage Super Module 1-East End Wall: Install East Endwall SM1 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install East Endwall SM1 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT | [7 empty] | 5 | [144 empty] | 5 | [303 empty] | 50680 |  | 10 | 100 | MT
[8 empty] | 1 | [145 empty] | 1 | [305 empty] | 2 | 20 | SrMT
[5 empty] | 1 | [148 empty] | 1 | [305 empty] | 3 | 30 | HV
[9 empty] | 5 | [146 empty] | 5
[8 empty] | 1 | [147 empty] | 1
[5 empty] | 2 | [150 empty] | 2
| Remove floor section along cyrostat wall | [246 empty] | PD | [13 empty] | PD | [13 empty] | PD | [13 empty] | PD
Install top FC sections 1hr
Install second FC sections 1hr
Install third FC sections 1hr
Install fourth FC sections 1hr
East Endwall SB1: Electrical connections and QC, survey and adjust 3hr
50690 | Install Field Cage Super Module 2-East End Wall: Install East Endwall SB2 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install East Endwall SM2 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT | [7 empty] | 5 | [148 empty] | 5 | [299 empty] | 50690 |  | 10 | 100 | MT
[8 empty] | 1 | [149 empty] | 1 | [301 empty] | 2 | 20 | SrMT
[5 empty] | 1 | [152 empty] | 2 | [301 empty] | 4 | 40 | HV
[9 empty] | 5 | [150 empty] | 5
[8 empty] | 1 | [151 empty] | 1
[5 empty] | 2 | [154 empty] | 2
Install top FC sections 1hr
Install second FC sections 1hr
Install third FC sections 1hr
Install fourth FC sections 1hr
East Endwall SB2: Electrical connections and QC, survey and adjust
50700 | Install Field Cage Super Module 3: Install South Wall SM3 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install South Wall SM3 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [154 empty] | 5 | [293 empty] | 50700
[8 empty] | 1 | [155 empty] | 1
[5 empty] | 1 | [158 empty] | 1
[9 empty] | 5 | [156 empty] | 5 | [293 empty] | 13 | 130 | MT
[8 empty] | 1 | [157 empty] | 1 | [293 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [160 empty] | 2 | [293 empty] | 6 | 60 | HV
[9 empty] | 1 | [158 empty] | 3 | [291 empty] | 3 | 30 | PD
[5 empty] | 1 | [162 empty] | 1
[6 empty] | 3 | [161 empty] | 3
50710 | Install Field Cage Super Module 4: Install North Wall SM4 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install North Wall SM4 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [160 empty] | 5 | [287 empty] | 50710
[8 empty] | 1 | [161 empty] | 1
[5 empty] | 1 | [164 empty] | 1
[9 empty] | 5 | [162 empty] | 5 | [287 empty] | 13 | 130 | MT
[8 empty] | 1 | [163 empty] | 1 | [287 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [166 empty] | 2 | [287 empty] | 6 | 60 | HV
[9 empty] | 1 | [164 empty] | 3 | [285 empty] | 3 | 30 | PD
[5 empty] | 1 | [168 empty] | 1
[6 empty] | 3 | [167 empty] | 3
50720 | Install Field Cage Super Module 5: Install South Wall SM5 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install South Wall SM5 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [168 empty] | 5 | [279 empty] | 50720
[8 empty] | 1 | [169 empty] | 1
[5 empty] | 1 | [172 empty] | 1
[9 empty] | 5 | [170 empty] | 5 | [279 empty] | 13 | 130 | MT
[8 empty] | 1 | [171 empty] | 1 | [279 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [174 empty] | 2 | [279 empty] | 6 | 60 | HV
[9 empty] | 1 | [172 empty] | 3 | [277 empty] | 3 | 30 | PD
[5 empty] | 1 | [176 empty] | 1
[6 empty] | 3 | [175 empty] | 3
50730 | Install Field Cage Super Module 6: Install North Wall SM6 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install North Wall SM6 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [174 empty] | 5 | [273 empty] | 50730
[8 empty] | 1 | [175 empty] | 1
[5 empty] | 1 | [178 empty] | 1
[9 empty] | 5 | [176 empty] | 5 | [273 empty] | 13 | 130 | MT
[8 empty] | 1 | [177 empty] | 1 | [273 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [180 empty] | 2 | [273 empty] | 6 | 60 | HV
[9 empty] | 1 | [178 empty] | 3 | [271 empty] | 3 | 30 | PD
[5 empty] | 1 | [182 empty] | 1
[6 empty] | 3 | [181 empty] | 3
50740 | Install Field Cage Super Module 7: Install South Wall SM7 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install South Wall SM7 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [182 empty] | 5 | [265 empty] | 50740
[8 empty] | 1 | [183 empty] | 1
[5 empty] | 1 | [186 empty] | 1
[9 empty] | 5 | [184 empty] | 5 | [265 empty] | 13 | 130 | MT
[8 empty] | 1 | [185 empty] | 1 | [265 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [188 empty] | 2 | [265 empty] | 6 | 60 | HV
[9 empty] | 1 | [186 empty] | 3 | [263 empty] | 3 | 30 | PD
[5 empty] | 1 | [190 empty] | 1
[6 empty] | 3 | [189 empty] | 3
50750 | Install Field Cage Super Module 8: Install North Wall SM8 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install North Wall SM8 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [188 empty] | 5 | [259 empty] | 50750
[8 empty] | 1 | [189 empty] | 1
[5 empty] | 1 | [192 empty] | 1
[9 empty] | 5 | [190 empty] | 5 | [259 empty] | 13 | 130 | MT
[8 empty] | 1 | [191 empty] | 1 | [259 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [194 empty] | 2 | [259 empty] | 6 | 60 | HV
[9 empty] | 1 | [192 empty] | 3 | [257 empty] | 3 | 30 | PD
[5 empty] | 1 | [196 empty] | 1
[6 empty] | 3 | [195 empty] | 3
50760 | Install Field Cage Super Module 9: Install South Wall SM9 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install South Wall SM9 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [196 empty] | 5 | [251 empty] | 50760
[8 empty] | 1 | [197 empty] | 1
[5 empty] | 1 | [200 empty] | 1
[9 empty] | 5 | [198 empty] | 5 | [251 empty] | 13 | 130 | MT
[8 empty] | 1 | [199 empty] | 1 | [251 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [202 empty] | 2 | [251 empty] | 6 | 60 | HV
[9 empty] | 1 | [200 empty] | 3 | [249 empty] | 3 | 30 | PD
[5 empty] | 1 | [204 empty] | 1
[6 empty] | 3 | [203 empty] | 3
50770 | Install Field Cage Super Module 10: Install North Wall SM10 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install North Wall SM10 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [202 empty] | 5 | [245 empty] | 50770
[8 empty] | 1 | [203 empty] | 1
[5 empty] | 1 | [206 empty] | 1
[9 empty] | 5 | [204 empty] | 5 | [245 empty] | 13 | 130 | MT
[8 empty] | 1 | [205 empty] | 1 | [245 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [208 empty] | 2 | [245 empty] | 6 | 60 | HV
[9 empty] | 1 | [206 empty] | 3 | [243 empty] | 3 | 30 | PD
[5 empty] | 1 | [210 empty] | 1
[6 empty] | 3 | [209 empty] | 3
50780 | Install Field Cage Super Module 11: Install South Wall SM11 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install South Wall SM11 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [210 empty] | 5 | [237 empty] | 50780
[8 empty] | 1 | [211 empty] | 1
[5 empty] | 1 | [214 empty] | 1
[9 empty] | 5 | [212 empty] | 5 | [237 empty] | 13 | 130 | MT
[8 empty] | 1 | [213 empty] | 1 | [237 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [216 empty] | 2 | [237 empty] | 6 | 60 | HV
[9 empty] | 1 | [214 empty] | 3 | [235 empty] | 3 | 30 | PD
[5 empty] | 1 | [218 empty] | 1
[6 empty] | 3 | [217 empty] | 3
50790 | Install Field Cage Super Module 12: Install North Wall SM12 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install North Wall SM12 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [216 empty] | 5 | [231 empty] | 50790
[8 empty] | 1 | [217 empty] | 1
[5 empty] | 1 | [220 empty] | 1
[9 empty] | 5 | [218 empty] | 5 | [231 empty] | 13 | 130 | MT
[8 empty] | 1 | [219 empty] | 1 | [231 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [222 empty] | 2 | [231 empty] | 6 | 60 | HV
[9 empty] | 1 | [220 empty] | 3 | [229 empty] | 3 | 30 | PD
[5 empty] | 1 | [224 empty] | 1
[6 empty] | 3 | [223 empty] | 3
50800 | Install Field Cage Super Module 13: Install South Wall SM13 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install South Wall SM13 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [224 empty] | 5 | [223 empty] | 50800
[8 empty] | 1 | [225 empty] | 1
[5 empty] | 1 | [228 empty] | 1
[9 empty] | 5 | [226 empty] | 5 | [223 empty] | 13 | 130 | MT
[8 empty] | 1 | [227 empty] | 1 | [223 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [230 empty] | 2 | [223 empty] | 6 | 60 | HV
[9 empty] | 1 | [228 empty] | 3 | [221 empty] | 3 | 30 | PD
[5 empty] | 1 | [232 empty] | 1
[6 empty] | 3 | [231 empty] | 3
50810 | Install Field Cage Super Module 14: Install North Wall SM14 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install North Wall SM14 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [230 empty] | 5 | [217 empty] | 50810
[8 empty] | 1 | [231 empty] | 1
[5 empty] | 1 | [234 empty] | 1
[9 empty] | 5 | [232 empty] | 5 | [217 empty] | 13 | 130 | MT
[8 empty] | 1 | [233 empty] | 1 | [217 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [236 empty] | 2 | [217 empty] | 6 | 60 | HV
[9 empty] | 1 | [234 empty] | 3 | [215 empty] | 3 | 30 | PD
[5 empty] | 1 | [238 empty] | 1
[6 empty] | 3 | [237 empty] | 3
50820 | Install Field Cage Super Module 15: Install South Wall SM15 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install South Wall SM15 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [238 empty] | 5 | [209 empty] | 50820
[8 empty] | 1 | [239 empty] | 1
[5 empty] | 1 | [242 empty] | 1
[9 empty] | 5 | [240 empty] | 5 | [209 empty] | 13 | 130 | MT
[8 empty] | 1 | [241 empty] | 1 | [209 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [244 empty] | 2 | [209 empty] | 6 | 60 | HV
[9 empty] | 1 | [242 empty] | 3 | [207 empty] | 3 | 30 | PD
[5 empty] | 1 | [246 empty] | 1
[6 empty] | 3 | [245 empty] | 3
50830 | Install Field Cage Super Module 16: Install North Wall SM16 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install North Wall SM16 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [244 empty] | 5 | [203 empty] | 50830
[8 empty] | 1 | [245 empty] | 1
[5 empty] | 1 | [248 empty] | 1
[9 empty] | 5 | [246 empty] | 5 | [203 empty] | 13 | 130 | MT
[8 empty] | 1 | [247 empty] | 1 | [203 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [250 empty] | 2 | [203 empty] | 6 | 60 | HV
[9 empty] | 1 | [248 empty] | 3 | [201 empty] | 3 | 30 | PD
[5 empty] | 1 | [252 empty] | 1
[6 empty] | 3 | [251 empty] | 3
50840 | Install Field Cage Super Module 17: Install South Wall SM17 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install South Wall SM17 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [252 empty] | 5 | [195 empty] | 50840
[8 empty] | 1 | [253 empty] | 1
[5 empty] | 1 | [256 empty] | 1
[9 empty] | 5 | [254 empty] | 5 | [195 empty] | 13 | 130 | MT
[8 empty] | 1 | [255 empty] | 1 | [195 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [258 empty] | 2 | [195 empty] | 6 | 60 | HV
[9 empty] | 1 | [256 empty] | 3 | [193 empty] | 3 | 30 | PD
[5 empty] | 1 | [260 empty] | 1
[6 empty] | 3 | [259 empty] | 3
50850 | Install Field Cage Super Module 18: Install North Wall SM18 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install North Wall SM18 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [258 empty] | 5 | [189 empty] | 50850
[8 empty] | 1 | [259 empty] | 1
[5 empty] | 1 | [262 empty] | 1
[9 empty] | 5 | [260 empty] | 5 | [189 empty] | 13 | 130 | MT
[8 empty] | 1 | [261 empty] | 1 | [189 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [264 empty] | 2 | [189 empty] | 6 | 60 | HV
[9 empty] | 1 | [262 empty] | 3 | [187 empty] | 3 | 30 | PD
[5 empty] | 1 | [266 empty] | 1
[6 empty] | 3 | [265 empty] | 3
50860 | Install Field Cage Super Module 19: Install South Wall SM19 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install South Wall SM19 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [266 empty] | 5 | [181 empty] | 50860
[8 empty] | 1 | [267 empty] | 1
[5 empty] | 1 | [270 empty] | 1
[9 empty] | 5 | [268 empty] | 5 | [181 empty] | 13 | 130 | MT
[8 empty] | 1 | [269 empty] | 1 | [181 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [272 empty] | 2 | [181 empty] | 6 | 60 | HV
[9 empty] | 1 | [270 empty] | 3 | [179 empty] | 3 | 30 | PD
[5 empty] | 1 | [274 empty] | 1
[6 empty] | 3 | [273 empty] | 3
50870 | Install Field Cage Super Module 20: Install North Wall SM20 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install North Wall SM20 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [272 empty] | 5 | [175 empty] | 50870
[8 empty] | 1 | [273 empty] | 1
[5 empty] | 1 | [276 empty] | 1
[9 empty] | 5 | [274 empty] | 5 | [175 empty] | 13 | 130 | MT
[8 empty] | 1 | [275 empty] | 1 | [175 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [278 empty] | 2 | [175 empty] | 6 | 60 | HV
[9 empty] | 1 | [276 empty] | 3 | [173 empty] | 3 | 30 | PD
[5 empty] | 1 | [280 empty] | 1
[6 empty] | 3 | [279 empty] | 3
50880 | Install Field Cage Super Module 21: Install South Wall SM21 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install South Wall SM21 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [280 empty] | 5 | [167 empty] | 50880
[8 empty] | 1 | [281 empty] | 1
[5 empty] | 1 | [284 empty] | 1
[9 empty] | 5 | [282 empty] | 5 | [167 empty] | 13 | 130 | MT
[8 empty] | 1 | [283 empty] | 1 | [167 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [286 empty] | 2 | [167 empty] | 6 | 60 | HV
[9 empty] | 1 | [284 empty] | 3 | [165 empty] | 3 | 30 | PD
[5 empty] | 1 | [288 empty] | 1
[6 empty] | 3 | [287 empty] | 3
50890 | Install Field Cage Super Module 22: Install North Wall SM22 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install North Wall SM22 section 1-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT Route PD fibers through HV support structure to Cathode PD plane | [7 empty] | 5 | [286 empty] | 5 | [161 empty] | 50890
[8 empty] | 1 | [287 empty] | 1
[5 empty] | 1 | [290 empty] | 1
[9 empty] | 5 | [288 empty] | 5 | [161 empty] | 13 | 130 | MT
[8 empty] | 1 | [289 empty] | 1 | [161 empty] | 3 | 30 | SrMT
[5 empty] | 2 | [292 empty] | 2 | [161 empty] | 6 | 60 | HV
[9 empty] | 1 | [290 empty] | 3 | [159 empty] | 3 | 30 | PD
[5 empty] | 1 | [294 empty] | 1
[6 empty] | 3 | [293 empty] | 3
50900 | Partial Installation Field Cage Super Module 23/24 - West End wall: Install East Endwall SM23/24 XY table and winch Teams/Shift-Top Cryo 1 HV, 1 SrMT, 2 MT - Cryostat 3 MT Install East Endwall SM23/24section 1-2 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT | [7 empty] | 5 | [294 empty] | 5 | [153 empty] | 50900 |  | 10 | 100 | MT
[8 empty] | 1 | [295 empty] | 1 | [155 empty] | 2 | 20 | SrMT
[5 empty] | 1 | [298 empty] | 1 | [155 empty] | 3 | 30 | HV
[9 empty] | 5 | [296 empty] | 5
[8 empty] | 1 | [297 empty] | 1
[5 empty] | 2 | [300 empty] | 2
Step 3 05.04.03.04 | Installation of HV Field Cage | [7 empty] | 1 | [126 empty] | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 |  |  | 3 | 1 | 3 | 1 | 6 | 1 | 6 | 1 | 6 | 1 | 6 | 1 |  |  | 6 | 1 | 6 | 1 | 4 | 1 | 6 | 1 | 6 | 1 | 4 | 1 |  |  | 6 | 1 | 6 | 1 | 4 | 1 | 6 | 1 | 6 | 1 | 4 | 1 |  |  | 6 | 1 | 6 | 1 | 4 | 1 | 6 | 1 | 6 | 1 | 4 | 1 |  |  | 6 | 1 | 6 | 1 | 4 | 1 | 6 | 1 | 6 | 1 | 4 | 1 |  |  | 6 | 1 | 6 | 1 | 4 | 1 | 6 | 1 | 6 | 1 | 4 | 1 |  |  | 6 | 1 | 6 | 1 | 4 | 1 | 6 | 1 | 6 | 1 | 4 | 1 |  |  | 6 | 1 | 6 | 1 | 4 | 1 | 6 | 1 | 6 | 1 | 4 | 1 |  |  | 5 | 0 | 5 | 0 | 3 | 0 | 5 | 0 | 5 | 0 | 3 | 0 |  |  | 5 | 0 | 5 | 0 | 3 | 0 | 5 | 0 | 5 | 0 | 3 | 0 |  |  | 5 | 0 | 5 | 0 | 3 | 0 | 5 | 0 | 5 | 0 | 3 | 0 |  |  | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [142 empty] | HV FC |  | 410 | 4100 | MT
[8 empty] | 1 | [127 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | H | V | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 |  | F | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | I | E | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | L | D | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 |  | C | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | A | G | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | E |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [144 empty] | 46 | 460 | SrMT
[5 empty] | 1 | [130 empty] | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 5 | 4 | 6 | 4 | 6 | 4 | 6 | 4 |  |  | 5 | 4 | 6 | 4 | 5 | 4 | 5 | 4 | 6 | 4 | 5 | 4 |  |  | 5 | 4 | 6 | 4 | 5 | 4 | 5 | 4 | 6 | 4 | 5 | 4 |  |  | 5 | 4 | 6 | 4 | 5 | 4 | 5 | 4 | 6 | 4 | 5 | 4 |  |  | 5 | 4 | 6 | 4 | 5 | 4 | 5 | 4 | 6 | 4 | 5 | 4 |  |  | 5 | 4 | 6 | 4 | 5 | 4 | 5 | 4 | 6 | 4 | 5 | 4 |  |  | 5 | 4 | 6 | 4 | 5 | 4 | 5 | 4 | 6 | 4 | 5 | 4 |  |  | 5 | 4 | 6 | 4 | 5 | 4 | 5 | 4 | 6 | 4 | 5 | 4 |  |  | 1 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 1 | 0 |  |  | 1 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 1 | 0 |  |  | 1 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 1 | 0 |  |  | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [144 empty] | 530 | 5300 | HV
[6 empty] | 2 | [129 empty] | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [144 empty] | 76 | 760 | PD
New Activity | Prepare for Cathode installation, Crew Training, dry runs & procedure review | [7 empty] | 4 | [169 empty] | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  |  |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  | 4
[6 empty] | 2 | [172 empty] | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
[5 empty] | 2 | [173 empty] | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
50250 | Install SS1 Cathodes 1 & 2: Place on work platform, attach Cathodes together, make HV and PD Fiber connections and remove work platform. 4MT 2HV 2PD | [7 empty] | 4 | [196 empty] | 4 | 4 | 4 | 4 | [248 empty] | 50250 |  | 16 | 160 | MT
[6 empty] | 2 | [199 empty] | 2 | 2 | 2 | 2 | [250 empty] | 8 | 80 | PD
[5 empty] | 2 | [200 empty] | 2 | 2 | 2 | 2 | [250 empty] | 8 | 80 | HV
50270 | Install SS2 Cathodes 3 & 4: Place on work platform, attach Cathodes together, make HV and PD Fiber connections and remove work platform. 4MT 2HV 2PD | [7 empty] | 4 | [200 empty] | 4 | 4 | 4 | 4 | [244 empty] | 50270 |  | 16 | 160 | MT
[6 empty] | 2 | [203 empty] | 2 | 2 | 2 | 2 | [246 empty] | 8 | 80 | PD
[5 empty] | 2 | [204 empty] | 2 | 2 | 2 | 2 | [246 empty] | 8 | 80 | HV
50290 | Install SS3 Cathodes 5 -10: Place on work platform, attach Cathodes together, make HV and PD Fiber connections and adjust Top CRP-Cathode gap, and remove work platform. 4MT 2HV 2PD | [7 empty] | 4 | [204 empty] | 4 | 4 | 4 | 4 | [240 empty] | 50290
[6 empty] | 2 | [207 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [208 empty] | 2 | 2 | 2 | 2
[9 empty] | 4 | [210 empty] | 4 | 4 | 4 | 4 | [236 empty] | 48 | 480 | MT
[6 empty] | 2 | [213 empty] | 2 | 2 | 2 | 2 | [236 empty] | 24 | 240 | PD
[5 empty] | 2 | [214 empty] | 2 | 2 | 2 | 2 | [236 empty] | 24 | 240 | HV
[9 empty] | 4 | [214 empty] | 4 | 4 | 4 | 4
[6 empty] | 2 | [217 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [218 empty] | 2 | 2 | 2 | 2
50320 | Install SS4 Cathode 11 - 16: Place on work platform, attach Cathodes together, make HV and PD Fiber connections and adjust Top CRP-Cathode gap, and remove work platform. 4MT 2HV 2PD | [7 empty] | 4 | [218 empty] | 4 | 4 | 4 | 4 | [226 empty] | 50320
[6 empty] | 2 | [221 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [222 empty] | 2 | 2 | 2 | 2
[9 empty] | 4 | [224 empty] | 4 | 4 | 4 | 4 | [222 empty] | 48 | 480 | MT
[6 empty] | 2 | [227 empty] | 2 | 2 | 2 | 2 | [222 empty] | 24 | 240 | PD
[5 empty] | 2 | [228 empty] | 2 | 2 | 2 | 2 | [222 empty] | 24 | 240 | HV
[9 empty] | 4 | [228 empty] | 4 | 4 | 4 | 4
[6 empty] | 2 | [231 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [232 empty] | 2 | 2 | 2 | 2
50340 | Install SS5 Cathode 17 - 22: Place on work platform, attach Cathodes together, make HV and PD Fiber connections and adjust Top CRP-Cathode gap, and remove work platform. 4MT 2HV 2PD | [7 empty] | 4 | [232 empty] | 4 | 4 | 4 | 4 | [212 empty] | 50340
[6 empty] | 2 | [235 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [236 empty] | 2 | 2 | 2 | 2
[9 empty] | 4 | [238 empty] | 4 | 4 | 4 | 4 | [208 empty] | 48 | 480 | MT
[6 empty] | 2 | [241 empty] | 2 | 2 | 2 | 2 | [208 empty] | 24 | 240 | PD
[5 empty] | 2 | [242 empty] | 2 | 2 | 2 | 2 | [208 empty] | 24 | 240 | HV
[9 empty] | 4 | [242 empty] | 4 | 4 | 4 | 4
[6 empty] | 2 | [245 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [246 empty] | 2 | 2 | 2 | 2
50360 | Install SS6 Cathode 23 - 28: Place on work platform, attach Cathodes together, make HV and PD Fiber connections and adjust Top CRP-Cathode gap, and remove work platform. 4MT 2HV 2PD | [7 empty] | 4 | [246 empty] | 4 | 4 | 4 | 4 | [198 empty] | 50360
[6 empty] | 2 | [249 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [250 empty] | 2 | 2 | 2 | 2
[9 empty] | 4 | [252 empty] | 4 | 4 | 4 | 4 | [194 empty] | 48 | 480 | MT
[6 empty] | 2 | [255 empty] | 2 | 2 | 2 | 2 | [194 empty] | 24 | 240 | PD
[5 empty] | 2 | [256 empty] | 2 | 2 | 2 | 2 | [194 empty] | 24 | 240 | HV
[9 empty] | 4 | [256 empty] | 4 | 4 | 4 | 4
[6 empty] | 2 | [259 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [260 empty] | 2 | 2 | 2 | 2
50380 | Install SS7 Cathode 29 - 34: Place on work platform, attach Cathodes together, make HV and PD Fiber connections and adjust Top CRP-Cathode gap, and remove work platform. 4MT 2HV 2PD | [7 empty] | 4 | [260 empty] | 4 | 4 | 4 | 4 | [184 empty] | 50380
[6 empty] | 2 | [263 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [264 empty] | 2 | 2 | 2 | 2
[9 empty] | 4 | [266 empty] | 4 | 4 | 4 | 4 | [180 empty] | 48 | 480 | MT
[6 empty] | 2 | [269 empty] | 2 | 2 | 2 | 2 | [180 empty] | 24 | 240 | PD
[5 empty] | 2 | [270 empty] | 2 | 2 | 2 | 2 | [180 empty] | 24 | 240 | HV
[9 empty] | 4 | [270 empty] | 4 | 4 | 4 | 4
[6 empty] | 2 | [273 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [274 empty] | 2 | 2 | 2 | 2
50410 | Install SS8 Cathode 35 - 36: Place on work platform, attach Cathodes together, make HV and PD Fiber connections and adjust Top CRP-Cathode gap, and remove work platform. 4MT 2HV 2PD | [7 empty] | 4 | [274 empty] | 4 | 4 | 4 | 4 | [170 empty] | 50410
[6 empty] | 2 | [277 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [278 empty] | 2 | 2 | 2 | 2
[9 empty] | 4 | [280 empty] | 4 | 4 | 4 | 4 | [166 empty] | 48 | 480 | MT
[6 empty] | 2 | [283 empty] | 2 | 2 | 2 | 2 | [166 empty] | 24 | 240 | PD
[5 empty] | 2 | [284 empty] | 2 | 2 | 2 | 2 | [166 empty] | 24 | 240 | HV
[9 empty] | 4 | [284 empty] | 4 | 4 | 4 | 4
[6 empty] | 2 | [287 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [288 empty] | 2 | 2 | 2 | 2
50430 | Install SS9 Cathode 41 - 46: Place on work platform, attach Cathodes together, make HV and PD Fiber connections and adjust Top CRP-Cathode gap, and remove work platform. 4MT 2HV 2PD | [7 empty] | 4 | [288 empty] | 4 | 4 | 4 | 4 | [156 empty] | 50430
[6 empty] | 2 | [291 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [292 empty] | 2 | 2 | 2 | 2
[9 empty] | 4 | [294 empty] | 4 | 4 | 4 | 4 | [152 empty] | 48 | 480 | MT
[6 empty] | 2 | [297 empty] | 2 | 2 | 2 | 2 | [152 empty] | 24 | 240 | PD
[5 empty] | 2 | [298 empty] | 2 | 2 | 2 | 2 | [152 empty] | 24 | 240 | HV
[9 empty] | 4 | [298 empty] | 4 | 4 | 4 | 4
[6 empty] | 2 | [301 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [302 empty] | 2 | 2 | 2 | 2
50450 | Install SS10 Cathode 47 - 52: Place on work platform, attach Cathodes together, make HV and PD Fiber connections and adjust Top CRP-Cathode gap, and remove work platform. 4MT 2HV 2PD | [7 empty] | 4 | [302 empty] | 4 | 4 | 4 | 4 | [142 empty] | 50450
[6 empty] | 2 | [305 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [306 empty] | 2 | 2 | 2 | 2
[9 empty] | 4 | [308 empty] | 4 | 4 | 4 | 4 | [138 empty] | 48 | 480 | MT
[6 empty] | 2 | [311 empty] | 2 | 2 | 2 | 2 | [138 empty] | 24 | 240 | PD
[5 empty] | 2 | [312 empty] | 2 | 2 | 2 | 2 | [138 empty] | 24 | 240 | HV
[9 empty] | 4 | [312 empty] | 4 | 4 | 4 | 4
[6 empty] | 2 | [315 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [316 empty] | 2 | 2 | 2 | 2
50470 | Install SS11 Cathode 53 - 58: Place on work platform, attach Cathodes together, make HV and PD Fiber connections and adjust Top CRP-Cathode gap, and remove work platform. 4MT 2HV 2PD | [7 empty] | 4 | [316 empty] | 4 | 4 | 4 | 4 | [128 empty] | 50470
[6 empty] | 2 | [319 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [320 empty] | 2 | 2 | 2 | 2
[9 empty] | 4 | [322 empty] | 4 | 4 | 4 | 4 | [124 empty] | 48 | 480 | MT
[6 empty] | 2 | [325 empty] | 2 | 2 | 2 | 2 | [124 empty] | 24 | 240 | PD
[5 empty] | 2 | [326 empty] | 2 | 2 | 2 | 2 | [124 empty] | 24 | 240 | HV
[9 empty] | 4 | [326 empty] | 4 | 4 | 4 | 4
[6 empty] | 2 | [329 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [330 empty] | 2 | 2 | 2 | 2
50490 | Install SS12 Cathode 59 - 64: Place on work platform, attach Cathodes together, make HV and PD Fiber connections and adjust Top CRP-Cathode gap, and remove work platform. 4MT 2HV 2PD | [7 empty] | 4 | [330 empty] | 4 | 4 | 4 | 4 | [114 empty] | 50490
[6 empty] | 2 | [333 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [334 empty] | 2 | 2 | 2 | 2
[9 empty] | 4 | [336 empty] | 4 | 4 | 4 | 4 | [110 empty] | 48 | 480 | MT
[6 empty] | 2 | [339 empty] | 2 | 2 | 2 | 2 | [110 empty] | 24 | 240 | PD
[5 empty] | 2 | [340 empty] | 2 | 2 | 2 | 2 | [110 empty] | 24 | 240 | HV
[9 empty] | 4 | [340 empty] | 4 | 4 | 4 | 4
[6 empty] | 2 | [343 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [344 empty] | 2 | 2 | 2 | 2
50520 | Install SS13 Cathode 65 - 70: Place on work platform, attach Cathodes together, make HV and PD Fiber connections and adjust Top CRP-Cathode gap, and remove work platform. 4MT 2HV 2PD | [7 empty] | 4 | [344 empty] | 4 | 4 | 4 | 4 | [100 empty] | 50520
[6 empty] | 2 | [347 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [348 empty] | 2 | 2 | 2 | 2
[9 empty] | 4 | [350 empty] | 4 | 4 | 4 | 4 | [96 empty] | 48 | 480 | MT
[6 empty] | 2 | [353 empty] | 2 | 2 | 2 | 2 | [96 empty] | 24 | 240 | PD
[5 empty] | 2 | [354 empty] | 2 | 2 | 2 | 2 | [96 empty] | 24 | 240 | HV
[9 empty] | 4 | [354 empty] | 4 | 4 | 4 | 4
[6 empty] | 2 | [357 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [358 empty] | 2 | 2 | 2 | 2
50540 | Install SS14 Cathode 71 - 76: Place on work platform, attach Cathodes together, make HV and PD Fiber connections and adjust Top CRP-Cathode gap, and remove work platform. 4MT 2HV 2PD | [7 empty] | 4 | [358 empty] | 4 | 4 | 4 | 4 | [86 empty] | 50540
[6 empty] | 2 | [361 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [362 empty] | 2 | 2 | 2 | 2
[9 empty] | 4 | [364 empty] | 4 | 4 | 4 | 4 | [82 empty] | 48 | 480 | MT
[6 empty] | 2 | [367 empty] | 2 | 2 | 2 | 2 | [82 empty] | 24 | 240 | PD
[5 empty] | 2 | [368 empty] | 2 | 2 | 2 | 2 | [82 empty] | 24 | 240 | HV
[9 empty] | 4 | [368 empty] | 4 | 4 | 4 | 4
[6 empty] | 2 | [371 empty] | 2 | 2 | 2 | 2
[5 empty] | 2 | [372 empty] | 2 | 2 | 2 | 2
50560 | Install SS 15 Cathode 77 & 78: Place on work platform, attach Cathodes together, make HV and PD Fiber connections and remove work platform. 4MT 2HV 2PD | [7 empty] | 4 | [372 empty] | 4 | 4 | 4 | 4 | [72 empty] | 50560 |  | 16 | 160 | MT
[6 empty] | 2 | [375 empty] | 2 | 2 | 2 | 2 | [74 empty] | 8 | 80 | PD
[5 empty] | 2 | [376 empty] | 2 | 2 | 2 | 2 | [74 empty] | 8 | 80 | HV
50580 | Install SS16 Cathode 79 & 80: Place on work platform, attach Cathodes together, make HV and PD Fiber connectionsand remove work platform. 4MT 2HV 2PD | [7 empty] | 4 | [378 empty] | 4 | 4 | 4 | 4 | 4 | 4 | [64 empty] | 50580 |  | 24 | 240 | MT
[6 empty] | 2 | [381 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [66 empty] | 12 | 120 | PD
[5 empty] | 2 | [382 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [66 empty] | 12 | 120 | HV
50600 | Cathode survey and Cleanup | [7 empty] | 9 | [384 empty] | 4 | 4 | 4 | 4 | [60 empty] | 50600 |  | 16 | 160 | MT
Step 4 05.04.03.03 | Install HV Cathode plane Install PD and PD fibers | [7 empty] | 1 | [168 empty] | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 |  |  | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | [58 empty] | HV Cath |  | 712 | 7120 | MT
[6 empty] | 2 | [171 empty] | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 |  |  | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | H | V | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | C | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | A | T | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | H | O | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | D | E | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | [60 empty] | 348 | 3480 | PD
[5 empty] | 1 | [172 empty] | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 |  |  | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | [60 empty] | 348 | 3480 | HV
50930 | Support for consortia preparation activities | [7 empty] | 1 | [259 empty] | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [16 empty] | 50930 |  | 156 | 1560 | MT
[8 empty] | 1 | [260 empty] | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 12 | 120 | SrMT
50940 | Setup for B_CRP installation, ORC, Dry runs and procedure review: This task only orrurs on the day shift | [7 empty] | 1 | [258 empty] | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 | [163 empty] | 50940 |  | 24 | 240 | MT
[8 empty] | 1 | [259 empty] | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 | [165 empty] | 24 | 240 | SrMT
|  | 2 | [265 empty] | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 | [165 empty] | 24 | 240 | B_Elec
|  |  |  | 3 | [263 empty] | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 2 |  | 2 |  | 2 | [165 empty] | 24 | 240 | CRP
50950 Row 1 CRP 1-4 | B_CRP row1: Remove floor, clean, survey, adjust cables | [7 empty] | 3 | [286 empty] | 3 | [162 empty] | 50950 Row 1 CRP 1-4
[8 empty] | 1 | [287 empty] | 1
|  |  |  | 3 | [291 empty] | 3
|  | 2 | [293 empty] | 2
Remove false floor row 1: 2.5 hr 4MT
Clean Cryostat floor row 1: 1hr 4MT
Survey B_CRP locations and mark 4hr 2 survey
Adjust cables for installation 4hr in parallel to survey 4 B_Elec
| B_CRP row1: Test cables and finish survey | [7 empty] | 3 | [287 empty] | 3
[8 empty] | 0 | [288 empty] | 0
|  |  |  | 3 | [292 empty] | 3
|  | 2 | [294 empty] | 2
Install test FEMB and check all cables 1 shift
Complete survey 1 shift
| B_CRP R1: Prepare install B_CRP 1 and 3 | [7 empty] | 3 | [288 empty] | 3
[8 empty] | 1 | [289 empty] | 1
|  |  |  | 3 | [293 empty] | 3
|  | 2 | [295 empty] | 2
Move B_CRP 1 to the installation location 1 hr
Rotate CRP 1 to be anode up. 1hr
Lift CRP 1, remove transport table, sit on floor 1 hr
Move B_CRP 3 to the installation location 1 hr
Rotate CRP 3 to be anode up. 1hr
Lift CRP 3, remove transport table, sit on floor 1 hr
| B_CRP R1: Install CRP 1 and 3 and survey | [7 empty] | 3 | [289 empty] | 3 | [160 empty] | 18 | 180
[8 empty] | 1 | [290 empty] | 1 | [160 empty] | 5 | 50
|  |  |  | 3 | [294 empty] | 3 | [160 empty] | 18 | 180
|  | 2 | [296 empty] | 2 | [160 empty] | 12 | 120
Lift CRP1 and place in position. 1hr
Connect cables and test 4 hr
Lift CRP3 and place in position 1hr
Connect cables and test 4 hr (in parallel to CRP 1 testing)
| B_CRP R1: Prepare install B_CRP 2 and 4 | [7 empty] | 3 | [290 empty] | 3
[8 empty] | 1 | [291 empty] | 1
|  |  |  | 3 | [295 empty] | 3
|  | 2 | [297 empty] | 2
Move B_CRP 2 to the installation location 1 hr
Rotate CRP 2 to be anode up. 1hr
Lift CRP 2, remove transport table, sit on floor 1 hr
Move B_CRP 4 to the installation location 1 hr
Rotate CRP 4 to be anode up. 1hr
Lift CRP 4, remove transport table, sit on floor 1 hr
| B_CRP R1: Install CRP 2 and 4 | [7 empty] | 3 | [291 empty] | 3
[8 empty] | 1 | [292 empty] | 1
|  |  |  | 3 | [296 empty] | 3
|  | 2 | [298 empty] | 2
Lift CRP2 and place in position. 1hr
Connect cables and test 4 hr
Lift CRP4 and place in position 1hr
Connect cables and test 4 hr (in parallel to CRP 2 testing)
50960 | B_CRP row2: Remove floor, clean, survey stands, adjust cables, Test Cables for B_CRP, put in final position for CRPs 5-8 | [7 empty] | 3 | [294 empty] | 3 | [154 empty] | 50960 Row 2 CRP 5-8
[8 empty] | 1 | [295 empty] | 1
|  |  |  | 3 | [299 empty] | 3
|  | 2 | [301 empty] | 2
[9 empty] | 3 | [295 empty] | 3
[8 empty] | 0 | [296 empty] | 0
|  |  |  | 3 | [300 empty] | 3 | [154 empty] | 18 | 180
|  | 2 | [302 empty] | 2 | [154 empty] | 5 | 50
[9 empty] | 3 | [296 empty] | 3 | [153 empty] | 18 | 180
[8 empty] | 1 | [297 empty] | 1 | [153 empty] | 12 | 120
|  |  |  | 3 | [301 empty] | 3
|  | 2 | [303 empty] | 2
[9 empty] | 3 | [297 empty] | 3
[8 empty] | 1 | [298 empty] | 1
|  |  |  | 3 | [302 empty] | 3
|  | 2 | [304 empty] | 2
[9 empty] | 3 | [298 empty] | 3
[8 empty] | 1 | [299 empty] | 1
|  |  |  | 2 | [303 empty] | 3
|  | 2 | [305 empty] | 2
[9 empty] | 3 | [299 empty] | 3
[8 empty] | 1 | [300 empty] | 1
|  |  |  | 2 | [304 empty] | 3
|  | 2 | [306 empty] | 2
50970 | Installation B_CRP Row 3: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 9-12 | [7 empty] | 3 | [300 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [143 empty] | 50970 | 18 | 180
[8 empty] | 1 | [301 empty] | 1 |  | 1 | 1 | 1 | 1 | [144 empty] | 5 | 50
|  |  |  | 3 | [305 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [144 empty] | 18 | 180
|  | 2 | [307 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [144 empty] | 12 | 120
50980 | Installation B_CRP Row 4: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 13-16 | [7 empty] | 3 | [308 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [135 empty] | 50980 | 18 | 180
[8 empty] | 1 | [309 empty] | 1 |  | 1 | 1 | 1 | 1 | [136 empty] | 5 | 50
|  |  |  | 3 | [313 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [136 empty] | 18 | 180
|  | 2 | [315 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [136 empty] | 12 | 120
50990 | Installation B_CRP Row 5: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 17-20 | [7 empty] | 3 | [314 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [129 empty] | 50990 | 18 | 180
[8 empty] | 1 | [315 empty] | 1 |  | 1 | 1 | 1 | 1 | [130 empty] | 5 | 50
|  |  |  | 3 | [319 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [130 empty] | 18 | 180
|  | 2 | [321 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [130 empty] | 12 | 120
51000 | Installation B_CRP Row 6: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 21-24 | [7 empty] | 3 | [322 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [121 empty] | 51000 | 18 | 180
[8 empty] | 1 | [323 empty] | 1 |  | 1 | 1 | 1 | 1 | [122 empty] | 5 | 50
|  |  |  | 3 | [327 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [122 empty] | 18 | 180
|  | 2 | [329 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [122 empty] | 12 | 120
51010 | Installation B_CRP Row 7: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 25-28 | [7 empty] | 3 | [328 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [115 empty] | 51010 | 18 | 180
[8 empty] | 1 | [329 empty] | 1 |  | 1 | 1 | 1 | 1 | [116 empty] | 5 | 50
|  |  |  | 3 | [333 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [116 empty] | 18 | 180
|  | 2 | [335 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [116 empty] | 12 | 120
51020 | Installation B_CRP Row 8: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 29-32 | [7 empty] | 3 | [336 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [107 empty] | 51020 | 18 | 180
[8 empty] | 1 | [337 empty] | 1 |  | 1 | 1 | 1 | 1 | [108 empty] | 5 | 50
|  |  |  | 3 | [341 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [108 empty] | 18 | 180
|  | 2 | [343 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [108 empty] | 12 | 120
51030 | Installation B_CRP Row 9: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 33-36 | [7 empty] | 3 | [342 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [101 empty] | 51030 | 18 | 180
[8 empty] | 1 | [343 empty] | 1 |  | 1 | 1 | 1 | 1 | [102 empty] | 5 | 50
|  |  |  | 3 | [347 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [102 empty] | 18 | 180
|  | 2 | [349 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [102 empty] | 12 | 120
51040 | Installation B_CRP Row 10: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 37-40 | [7 empty] | 3 | [350 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [93 empty] | 51040 | 18 | 180
[8 empty] | 1 | [351 empty] | 1 |  | 1 | 1 | 1 | 1 | [94 empty] | 5 | 50
|  |  |  | 3 | [355 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [94 empty] | 18 | 180
|  | 2 | [357 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [94 empty] | 12 | 120
51050 | Installation B_CRP Row 11: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 41-44 | [7 empty] | 3 | [356 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [87 empty] | 51050 | 18 | 180
[8 empty] | 1 | [357 empty] | 1 |  | 1 | 1 | 1 | 1 | [88 empty] | 5 | 50
|  |  |  | 3 | [361 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [88 empty] | 18 | 180
|  | 2 | [363 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [88 empty] | 12 | 120
51060 | Installation B_CRP Row 12: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 45-48 | [7 empty] | 3 | [364 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [79 empty] | 51060 | 18 | 180
[8 empty] | 1 | [365 empty] | 1 |  | 1 | 1 | 1 | 1 | [80 empty] | 5 | 50
|  |  |  | 3 | [369 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [80 empty] | 18 | 180
|  | 2 | [371 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [80 empty] | 12 | 120
51070 | Installation B_CRP Row 13: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 49-52 | [7 empty] | 3 | [370 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [73 empty] | 51070 | 18 | 180
[8 empty] | 1 | [371 empty] | 1 |  | 1 | 1 | 1 | 1 | [74 empty] | 5 | 50
|  |  |  | 3 | [375 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [74 empty] | 18 | 180
|  | 2 | [377 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [74 empty] | 12 | 120
51080 | Installation B_CRP Row 14: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 53-56 | [7 empty] | 3 | [378 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [65 empty] | 51080 | 18 | 180
[8 empty] | 1 | [379 empty] | 1 |  | 1 | 1 | 1 | 1 | [66 empty] | 5 | 50
|  |  |  | 3 | [383 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [66 empty] | 18 | 180
|  | 2 | [385 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [66 empty] | 12 | 120
51090 | Installation B_CRP Row 15: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 57-60 | [7 empty] | 3 | [384 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [59 empty] | 51090 | 18 | 180
[8 empty] | 1 | [385 empty] | 1 |  | 1 | 1 | 1 | 1 | [60 empty] | 5 | 50
|  |  |  | 3 | [389 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [60 empty] | 18 | 180
|  | 2 | [391 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [60 empty] | 12 | 120
51100 | Installation B_CRP Row 16: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 61-64 | [7 empty] | 3 | [392 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [51 empty] | 51100 | 18 | 180
[8 empty] | 1 | [393 empty] | 1 |  | 1 | 1 | 1 | 1 | [52 empty] | 5 | 50
|  |  |  | 3 | [397 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [52 empty] | 18 | 180
|  | 2 | [399 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [52 empty] | 12 | 120
51110 | Installation B_CRP Row 17: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 65-68 | [7 empty] | 3 | [398 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [45 empty] | 51110 | 18 | 180
[8 empty] | 1 | [399 empty] | 1 |  | 1 | 1 | 1 | 1 | [46 empty] | 5 | 50
|  |  |  | 3 | [403 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [46 empty] | 18 | 180
|  | 2 | [405 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [46 empty] | 12 | 120
51120 | Installation B_CRP Row 18: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 69-72 | [7 empty] | 3 | [406 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [37 empty] | 51120 | 18 | 180
[8 empty] | 1 | [407 empty] | 1 |  | 1 | 1 | 1 | 1 | [38 empty] | 5 | 50
|  |  |  | 3 | [411 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [38 empty] | 18 | 180
|  | 2 | [413 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [38 empty] | 12 | 120
51130 | Installation B_CRP Row 19: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 73-76 | [7 empty] | 3 | [412 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [31 empty] | 51130 | 18 | 180
[8 empty] | 1 | [413 empty] | 1 |  | 1 | 1 | 1 | 1 | [32 empty] | 5 | 50
|  |  |  | 3 | [417 empty] | 3 | 3 | 3 | 3 | 3 | 3 | [32 empty] | 18 | 180
|  | 2 | [419 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [32 empty] | 12 | 120
51140 | Installation B_CRP Row 20: Remove Floor, clean, survey stands, adjust cables,Test cables,Prepare , install, and survey four B_CRP: CRP 77-80 | [7 empty] | 3 | [420 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [17 empty] | 51140 | 36 | 360
[8 empty] | 1 | [421 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | [18 empty] | 10 | 100
|  |  |  | 3 | [425 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [18 empty] | 36 | 360
|  | 2 | [427 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [18 empty] | 24 | 240
Step 5 05.04.03.05 | B_CRP Row 1-20 | [7 empty] | 3 | [252 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 5 | 5 | 5 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | [16 empty] | Bot CRP |  | 558 | 5580 | MT
[8 empty] | 1 | [253 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 1 |  |  | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 |  |  | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | B | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | O | T | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | T | O | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | M |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | C | R | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | P |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | [18 empty] | 141 | 1410 | SrMT
|  |  |  | 3 | [257 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 |  |  | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 |  |  | 2 | 0 | 2 | 0 | 2 | 0 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [18 empty] | 402 | 4020 | CRP
|  | 2 | [259 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 |  |  | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 |  |  | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [18 empty] | 276 | 2760 | B_Elec
50910 | Complete Install Field Cage Super Module 23/24 - West End wall: Install West Endwall SB23 section 3-4 Teams/Shift-Top Cryo 1 HV, 2 MT - Cryostat 1 HV, 1 SrMT, 3 MT | [7 empty] | 5 | [434 empty] | 5 | 5 | 5 | 5 | 5 | 5 | [8 empty] | 50910 |  | 30 | 300 | MT
[8 empty] | 1 | [435 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 6 | 60 | SrMT
[5 empty] | 1 | [438 empty] | 2 | 2 | 2 | 2 | 2 | 2 | [10 empty] | 12 | 120 | HV
[9 empty] | 5 | [440 empty] | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 30 | 300 | MT
[8 empty] | 1 | [441 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 6 | 60 | SrMT
[5 empty] | 2 | [444 empty] | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 12 | 120 | HV
Step3B 05.04.03.04 | Complete Installation of HV Field Cage | [7 empty] | 1 | [434 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  | HV FC |  | 60 | 600 | MT
[8 empty] | 1 | [434 empty] | H | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | V |  |  |  | 12 | 120 | SrMT
[5 empty] | 1 | [438 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 24 | 240 | HV
[22 empty] | Week 1 | [13 empty] | Week 2 | [13 empty] | Week 3 | [13 empty] | Week 4 | [13 empty] | Week 5 | [13 empty] | Week 6 | [13 empty] | Week 7 | [13 empty] | Week 8 | [13 empty] | Week 9 | [13 empty] | Week 10 | [13 empty] | Week 11 | [13 empty] | Week 12 | [13 empty] | Week 13 | [13 empty] | Week 14 | [13 empty] | Week 15 | [13 empty] | Week 16 | [13 empty] | Week 17 | [13 empty] | Week 18 | [13 empty] | Week 19 | [13 empty] | Week 20 | [13 empty] | Week 21 | [13 empty] | Week 22 | [13 empty] | Week 23 | [13 empty] | Week 24 | [13 empty] | Week 25 | [13 empty] | Week 26 | [13 empty] | Week 27 | [13 empty] | Week 27 | [13 empty] | Week 28 | [13 empty] | Week 29 | [13 empty] | Week 30 | [13 empty] | Week 31
[22 empty] | AM | PM | [12 empty] | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM | AM | PM
| Mechanical Tech - Total FTE shifts /week | [8 empty] | 8 | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 68 | 68 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | 72 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 78 | 78 | 16 | 16 | 17 | 17 | 17 | 17 | 14 | 14 | 14 | 14 | 13 | 13 | 91 | 91 | 13 | 16 | 13 | 16 | 13 | 16 | 13 | 16 | 13 | 16 | 13 | 16 | 78 | 96 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 84 | 84 | 14 | 11 | 14 | 11 | 11 | 8 | 11 | 8 | 11 | 8 | 11 | 8 | 72 | 54 | 13 | 12 | 13 | 12 | 13 | 12 | 13 | 12 | 13 | 12 | 13 | 12 | 78 | 72 | 13 | 12 | 13 | 12 | 13 | 12 | 13 | 12 | 13 | 12 | 13 | 12 | 78 | 72 | 14 | 13 | 14 | 13 | 16 | 13 | 16 | 13 | 9 | 13 | 16.6 | 6 | 85.6 | 71 | 9 | 6 | 9 | 6 | 12 | 6 | 12 | 6 | 12 | 6 | 12 | 6 | 66 | 36 | 12 | 6 | 12 | 6 | 10 | 6 | 12 | 6 | 12 | 6 | 10 | 6 | 68 | 36 | 12 | 10 | 12 | 10 | 10 | 10 | 12 | 10 | 12 | 10 | 10 | 10 | 68 | 60 | 12 | 10 | 12 | 10 | 10 | 10 | 12 | 10 | 12 | 10 | 10 | 10 | 68 | 60 | 16 | 10 | 16 | 10 | 14 | 10 | 12 | 6 | 12 | 6 | 10 | 6 | 80 | 48 | 10 | 5 | 10 | 5 | 8 | 5 | 10 | 5 | 10 | 5 | 8 | 5 | 56 | 30 | 10 | 5 | 10 | 5 | 8 | 5 | 10 | 5 | 10 | 5 | 8 | 5 | 56 | 30 | 10 | 5 | 10 | 5 | 8 | 5 | 10 | 5 | 10 | 5 | 8 | 5 | 56 | 30 | 9 | 4 | 9 | 4 | 7 | 4 | 11 | 6 | 11 | 6 | 9 | 6 | 56 | 30 | 11 | 6 | 11 | 6 | 9 | 6 | 11 | 6 | 11 | 6 | 9 | 6 | 62 | 36 | 11 | 6 | 11 | 6 | 9 | 6 | 14 | 9 | 14 | 9 | 12 | 9 | 71 | 45 | 13 | 8 | 13 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 58 | 48 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 48 | 48 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 48 | 48 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 48 | 48 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 48 | 48 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 48 | 48 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 44 | 44 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 24 | 24 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 24 | 24 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 24 | 24 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | Grand Total |  | 3592.6 | 35926 | MT | Cross Check Grand Total | 3568.6 | 35686 | MT
| Sr Mechanical Tech - Total FTE shifts/week | [8 empty] | 3 | 2 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 12 | 17 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 24 | 18 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | 18 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 21 | 21 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 18 | 24 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 18 | 24 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 14 | 14 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | 18 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 17 | 17 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 2 | 17 | 17 | 1 | 1 | 2 | 2 | 3 | 2 | 3 | 2 | 3 | 2 | 3 | 2 | 15 | 11 | 3 | 2 | 3 | 2 | 2 | 2 | 3 | 2 | 3 | 2 | 2 | 2 | 16 | 12 | 3 | 2 | 3 | 2 | 2 | 2 | 3 | 2 | 2 | 1 | 2 | 2 | 15 | 11 | 3 | 2 | 3 | 2 | 2 | 2 | 3 | 2 | 3 | 2 | 2 | 2 | 16 | 12 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 12 | 8 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 3 | 1 | 3 | 1 | 2 | 1 | 10 | 3 | 3 | 1 | 3 | 1 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 1 | 16 | 6 | 3 | 1 | 3 | 1 | 2 | 1 | 2 | 0 | 2 | 1 | 1 | 1 | 13 | 5 | 2 | 0 | 2 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 8 | 4 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 6 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 |  |  | 678 | 6780 | SrMT |  | 683 | 6830 | SrMT
| CRP Consortia - Total FTE shifts/week | [8 empty] | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 12 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 12 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | 18 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 24 | 24 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 30 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 4 | 2 | 24 | 12 | 4 | 2 | 4 | 2 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 16 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | 18 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 15 | 15 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | 18 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 15 | 15 | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 30 | 18 | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 2 | 0 | 5 | 3 | 27 | 15 | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 5 | 3 | 30 | 18 | 5 | 3 | 5 | 3 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 18 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 6 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 12 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 15 | 9 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | 18 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | 18 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | 18 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | 18 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | 18 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | 18 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | 18 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | 18 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | 18 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 938 | 9380 | CRP |  | 920 | 9200 | CRP
| HV Consortia - Total FTE Total FTE shifts/week | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 4 | 4 | 4 | 4 | 32 | 24 | 4 | 4 | 4 | 4 | 5 | 4 | 6 | 4 | 6 | 4 | 6 | 4 | 31 | 24 | 5 | 4 | 6 | 4 | 5 | 4 | 5 | 4 | 6 | 4 | 5 | 4 | 32 | 24 | 5 | 6 | 6 | 6 | 5 | 6 | 5 | 6 | 6 | 6 | 5 | 6 | 32 | 36 | 5 | 6 | 6 | 6 | 5 | 6 | 5 | 6 | 6 | 6 | 5 | 6 | 32 | 36 | 7 | 6 | 8 | 6 | 7 | 6 | 7 | 6 | 8 | 6 | 7 | 6 | 44 | 36 | 7 | 6 | 8 | 6 | 7 | 6 | 7 | 6 | 8 | 6 | 7 | 6 | 44 | 36 | 7 | 6 | 8 | 6 | 7 | 6 | 7 | 6 | 8 | 6 | 7 | 6 | 44 | 36 | 7 | 6 | 8 | 6 | 7 | 6 | 7 | 6 | 8 | 6 | 7 | 6 | 44 | 36 | 3 | 2 | 4 | 2 | 3 | 2 | 3 | 2 | 4 | 2 | 3 | 2 | 20 | 12 | 3 | 2 | 4 | 2 | 3 | 2 | 3 | 2 | 4 | 2 | 3 | 2 | 20 | 12 | 3 | 2 | 4 | 2 | 3 | 2 | 3 | 2 | 4 | 2 | 3 | 2 | 20 | 12 | 3 | 2 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 15 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 |  |  | 902 | 9020 | HV |  | 902 | 9020 | HV
| PD Consortia - Total FTE Total FTE shifts/week | [8 empty] | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 24 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 6 | 0 | 6 | 0 | 28 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 12 | 0 | 4 | 2 | 6 | 4 | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 | 38 | 18 | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 | 42 | 18 | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 | 42 | 18 | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 | 42 | 18 | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 | 42 | 18 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 30 | 18 | 8 | 2 | 6 | 4 | 8 | 2 | 6 | 4 | 6 | 0 | 2 | 0 | 36 | 12 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 6 | 0 | 0 | 2 | 0 | 2 | 3 | 2 | 0 | 2 | 0 | 2 | 3 | 2 | 6 | 12 | 0 | 2 | 0 | 2 | 3 | 2 | 0 | 2 | 0 | 2 | 3 | 2 | 6 | 12 | 2 | 2 | 2 | 2 | 5 | 2 | 2 | 2 | 2 | 2 | 5 | 2 | 18 | 12 | 2 | 2 | 2 | 2 | 5 | 2 | 2 | 2 | 2 | 2 | 5 | 2 | 18 | 12 | 2 | 2 | 2 | 2 | 5 | 2 | 2 | 2 | 2 | 2 | 5 | 2 | 18 | 12 | 2 | 2 | 2 | 2 | 5 | 2 | 2 | 2 | 2 | 2 | 5 | 2 | 18 | 12 | 2 | 2 | 2 | 2 | 5 | 2 | 2 | 2 | 2 | 2 | 5 | 2 | 18 | 12 | 2 | 2 | 2 | 2 | 5 | 2 | 2 | 2 | 2 | 2 | 5 | 2 | 18 | 12 | 2 | 2 | 2 | 2 | 5 | 2 | 2 | 2 | 2 | 2 | 5 | 2 | 18 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 868 | 8680 | PD |  | 792 | 7920 | PD
| TDE Consortia - Total FTE Total FTE shifts/week | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 12 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 12 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 114 | 1140 | T_Elec |  | 114 | 1140 | T_Elec
| B_Elec Consortia - Total FTE Total FTE shifts/week | [8 empty] | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 12 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 12 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 26 | 18 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 30 | 18 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 30 | 18 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 30 | 18 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 30 | 18 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 30 | 18 | 6 | 2 | 4 | 4 | 6 | 2 | 4 | 4 | 4 | 0 | 0 | 0 | 24 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 6 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 12 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 656 | 6560 | B_Elec |  | 644 | 6440 | B_Elec
| Average I&I and Consortia FTE in cryostat/shift | [20 empty] | 21.3333 | 14.1667 | [12 empty] | 24.6667 | 15 | [12 empty] | 23 | 21 | [12 empty] | 33.3333 | 28.6667 | [12 empty] | 33 | 31 | [12 empty] | 35 | 26 | [12 empty] | 31 | 18 | [12 empty] | 32 | 25 | [12 empty] | 29.3333 | 24.3333 | [12 empty] | 36.4333 | 26.6667 | [12 empty] | 22.8333 | 15.3333 | [12 empty] | 26.3333 | 16 | [12 empty] | 25.6667 | 23.3333 | [12 empty] | 26.3333 | 24 | [12 empty] | 29.1667 | 18.8333 | [12 empty] | 20.3333 | 13 | [12 empty] | 20.3333 | 13 | [12 empty] | 20.3333 | 13 | [12 empty] | 19.3333 | 9.5 | [12 empty] | 23.3333 | 11 | [12 empty] | 24.8333 | 14.8333 | [12 empty] | 20.5 | 17.6667 | [12 empty] | 18 | 17.6667 | [12 empty] | 18 | 17.6667 | [12 empty] | 18 | 17.6667 | [12 empty] | 18 | 17.6667 | [12 empty] | 18 | 17.6667 | [12 empty] | 15.3333 | 15 | [12 empty] | 10 | 9.6667 | [12 empty] | 10 | 9.6667 | [12 empty] | 10 | 9.6667 | [12 empty] | 8 | 8
[21 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE | [12 empty] | Tot | # FTE
[21 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr | [12 empty] | Shift | 40 hr
[21 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week | [12 empty] | Week | /Week
| Mechanical Tech - Total FTE Required to cover 40 hr weeks | [19 empty] | 136 | 34 | [12 empty] | 144 | 36 | [12 empty] | 156 | 39 | [12 empty] | 182 | 45.5 | [12 empty] | 174 | 43.5 | [12 empty] | 168 | 42 | [12 empty] | 126 | 31.5 | [12 empty] | 150 | 37.5 | [12 empty] | 150 | 37.5 | [12 empty] | 156.6 | 39.15 | [12 empty] | 102 | 25.5 | [12 empty] | 104 | 26 | [12 empty] | 128 | 32 | [12 empty] | 128 | 32 | [12 empty] | 128 | 32 | [12 empty] | 86 | 21.5 | [12 empty] | 86 | 21.5 | [12 empty] | 86 | 21.5 | [12 empty] | 86 | 21.5 | [12 empty] | 98 | 24.5 | [12 empty] | 116 | 29 | [12 empty] | 106 | 26.5 | [12 empty] | 96 | 24 | [12 empty] | 96 | 24 | [12 empty] | 96 | 24 | [12 empty] | 96 | 24 | [12 empty] | 96 | 24 | [12 empty] | 88 | 22 | [12 empty] | 48 | 12
| Sr Mechanical Tech - Total FTE Required to cover 40 hr weeks | [19 empty] | 24 | 6 | [12 empty] | 42 | 10.5 | [12 empty] | 36 | 9 | [12 empty] | 42 | 10.5 | [12 empty] | 42 | 10.5 | [12 empty] | 42 | 10.5 | [12 empty] | 28 | 7 | [12 empty] | 36 | 9 | [12 empty] | 34 | 8.5 | [12 empty] | 34 | 8.5 | [12 empty] | 26 | 6.5 | [12 empty] | 28 | 7 | [12 empty] | 26 | 6.5 | [12 empty] | 28 | 7 | [12 empty] | 20 | 5 | [12 empty] | 4 | 1 | [12 empty] | 4 | 1 | [12 empty] | 4 | 1 | [12 empty] | 13 | 3.25 | [12 empty] | 22 | 5.5 | [12 empty] | 18 | 4.5 | [12 empty] | 12 | 3 | [12 empty] | 10 | 2.5 | [12 empty] | 10 | 2.5 | [12 empty] | 10 | 2.5 | [12 empty] | 10 | 2.5 | [12 empty] | 10 | 2.5 | [12 empty] | 10 | 2.5 | [12 empty] | 10 | 2.5
| CRP Consortia - Total FTE Required to cover 40 hr weeks | [19 empty] | 12 | 3 | [12 empty] | 12 | 3 | [12 empty] | 21 | 5.25 | [12 empty] | 28 | 7 | [12 empty] | 35 | 8.75 | [12 empty] | 26 | 6.5 | [12 empty] | 16 | 4 | [12 empty] | 21 | 5.25 | [12 empty] | 18 | 4.5 | [12 empty] | 21 | 5.25 | [12 empty] | 18 | 4.5 | [12 empty] | 33 | 8.25 | [12 empty] | 30 | 7.5 | [12 empty] | 33 | 8.25 | [12 empty] | 18 | 4.5 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 6 | 1.5 | [12 empty] | 12 | 3 | [12 empty] | 18 | 4.5 | [12 empty] | 21 | 5.25 | [12 empty] | 21 | 5.25 | [12 empty] | 21 | 5.25 | [12 empty] | 21 | 5.25 | [12 empty] | 21 | 5.25 | [12 empty] | 21 | 5.25 | [12 empty] | 21 | 5.25 | [12 empty] | 21 | 5.25
| HV Consortia - Total FTE Required to cover 40 hr weeks | [19 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 36 | 9 | [12 empty] | 35 | 8.75 | [12 empty] | 36 | 9 | [12 empty] | 38 | 9.5 | [12 empty] | 38 | 9.5 | [12 empty] | 50 | 12.5 | [12 empty] | 50 | 12.5 | [12 empty] | 50 | 12.5 | [12 empty] | 50 | 12.5 | [12 empty] | 22 | 5.5 | [12 empty] | 22 | 5.5 | [12 empty] | 22 | 5.5 | [12 empty] | 17 | 4.25 | [12 empty] | 14 | 3.5 | [12 empty] | 14 | 3.5 | [12 empty] | 14 | 3.5 | [12 empty] | 14 | 3.5 | [12 empty] | 14 | 3.5 | [12 empty] | 6 | 1.5 | [12 empty] | 0 | 0
| PD Consortia - Total FTE Total FTE Required to cover 40 hr weeks | [19 empty] | 0 | 0 | [12 empty] | 28 | 7 | [12 empty] | 12 | 3 | [12 empty] | 42 | 10.5 | [12 empty] | 46 | 11.5 | [12 empty] | 46 | 11.5 | [12 empty] | 46 | 11.5 | [12 empty] | 46 | 11.5 | [12 empty] | 34 | 8.5 | [12 empty] | 36 | 9 | [12 empty] | 4 | 1 | [12 empty] | 6 | 1.5 | [12 empty] | 8 | 2 | [12 empty] | 8 | 2 | [12 empty] | 20 | 5 | [12 empty] | 20 | 5 | [12 empty] | 20 | 5 | [12 empty] | 20 | 5 | [12 empty] | 20 | 5 | [12 empty] | 20 | 5 | [12 empty] | 20 | 5 | [12 empty] | 14 | 3.5 | [12 empty] | 14 | 3.5 | [12 empty] | 14 | 3.5 | [12 empty] | 14 | 3.5 | [12 empty] | 14 | 3.5 | [12 empty] | 14 | 3.5 | [12 empty] | 6 | 1.5 | [12 empty] | 0 | 0
| TDE Consortia - Total FTE Total FTE Required to cover 40 hr weeks | [19 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 12 | 3 | [12 empty] | 12 | 3 | [12 empty] | 7 | 1.75 | [12 empty] | 7 | 1.75 | [12 empty] | 7 | 1.75 | [12 empty] | 7 | 1.75 | [12 empty] | 7 | 1.75 | [12 empty] | 7 | 1.75 | [12 empty] | 7 | 1.75 | [12 empty] | 3 | 0.75 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0
| B_Elec Consortia - Total FTE Total FTE Required to cover 40 hr weeks | [19 empty] | 12 | 3 | [12 empty] | 12 | 3 | [12 empty] | 14 | 3.5 | [12 empty] | 30 | 7.5 | [12 empty] | 34 | 8.5 | [12 empty] | 34 | 8.5 | [12 empty] | 34 | 8.5 | [12 empty] | 34 | 8.5 | [12 empty] | 34 | 8.5 | [12 empty] | 24 | 6 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 6 | 1.5 | [12 empty] | 12 | 3 | [12 empty] | 14 | 3.5 | [12 empty] | 14 | 3.5 | [12 empty] | 14 | 3.5 | [12 empty] | 14 | 3.5 | [12 empty] | 14 | 3.5 | [12 empty] | 14 | 3.5 | [12 empty] | 14 | 3.5 | [12 empty] | 14 | 3.5 | [12 empty] | 14 | 3.5
[22 empty] | Month 1 | [55 empty] | Month 2 | [55 empty] | Month 3 | [55 empty] | Month 4 | [55 empty] | Month 5 | [55 empty] | Month 6 | [55 empty] | Month 7
| Mechanical Tech - Average # FTE/month Required to cover 40 hr weeks | [35 empty] | 38.625 | [55 empty] | 38.625 | [55 empty] | 32.0375 | [55 empty] | 29.375 | [55 empty] | 22.25 | [55 empty] | 25.875 | [55 empty] | 21
| SRMechanical Tech - Average # FTE/month Required to cover 40 hr weeks | [35 empty] | 9 | [55 empty] | 9.25 | [55 empty] | 7.625 | [55 empty] | 4.875 | [55 empty] | 2.6875 | [55 empty] | 3.125 | [55 empty] | 2.5
| CRP Consortia - Average # FTE/month Required to cover 40 hr weeks | [35 empty] | 4.5625 | [55 empty] | 6.125 | [55 empty] | 5.625 | [55 empty] | 5.0625 | [55 empty] | 1.125 | [55 empty] | 5.0625 | [55 empty] | 5.25
| HV Consortia - Average # FTE/month Required to cover 40 hr weeks | [35 empty] | 0 | [55 empty] | 0 | [55 empty] | 6.6875 | [55 empty] | 11 | [55 empty] | 9 | [55 empty] | 4.1875 | [55 empty] | 2.625
| PDS Consortia - Average # FTE/month Required to cover 40 hr weeks | [35 empty] | 5.125 | [55 empty] | 11.5 | [55 empty] | 5 | [55 empty] | 3.5 | [55 empty] | 5 | [55 empty] | 3.875 | [55 empty] | 2.625
| TDE Consortia - Average # FTE/month Required to cover 40 hr weeks | [35 empty] | 0 | [55 empty] | 1.9375 | [55 empty] | 1.75 | [55 empty] | 1.0625 | [55 empty] | 0 | [55 empty] | 0 | [55 empty] | 0
| B_Elec Consortia - Average # FTE/month Required to cover 40 hr weeks | [35 empty] | 4.25 | [55 empty] | 8.5 | [55 empty] | 3.625 | [55 empty] | 0 | [55 empty] | 1.125 | [55 empty] | 3.5 | [55 empty] | 3.5
I & I Equipment
| JLG4045R | [8 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Genie-GS4655 | [10 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| JLG2632ES | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Custom-Lift Table | [64 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Note on B620: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: One sheet every 10 min and 14 sheets gives 140 min or 2.5hr

## Close_TCO_PrepforFilling
Summary | [5 empty] | SrMT | Tech | [44 empty] | 2025 | [51 empty] | 2026 | [51 empty] | 2027 | [51 empty] | 2028
| T0-AUP of North Cavern 17-Oct-2024 |  | I&I | [8 empty] | -4 |  |  |  |  | -5 |  |  |  | -4 |  |  |  | -3 |  |  |  |  | -2 |  |  |  | -1 |  |  |  |  | 1 |  |  |  | 2 |  |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  |  | 7 |  |  |  | 8 |  |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  |  | 12 |  |  |  | 13 |  |  |  | 14 |  |  |  |  | 15 |  |  |  | 16 |  |  |  | 17 |  |  |  | 18 |  |  |  |  | 19 |  |  |  | 20 |  |  |  |  | 21 |  |  |  | 22 |  |  |  | 23 |  |  |  |  | 24 |  |  |  | 25 |  |  |  |  | 26 |  |  |  | 27 |  |  |  | 28 |  |  |  |  | 29 |  |  |  | 30 |  |  |  | 31 |  |  |  | 32 |  |  |  |  | 33 |  |  |  | 34 |  |  |  | 35 |  |  |  |  | 36 |  |  |  | 37 |  |  |  |  | 38 |  |  |  | 39 |  |  |  | 40 |  |  |  |  | 41 |  |  |  | 42 |  |  |  | 43 |  |  |  | 44 |  |  |  |  | 45 |  |  |  |  | 46 |  |  |  |  | 47 |  |  |  |  | 48 |  |  |  |  | 49 |  |  |  |  | 50 |  |  |  |  | 51
WBS/Activity | Activity Description |  | SrT | Weld | MT | Hours | Hours | Weld | -31 | -30 | -29 | -28 | -27 | -26 | -25 | -24 | -23 | -22 | -21 | -20 | -19 | -18 | -17 | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225
 | time axis 2024-03-11 to 2029-01-29
05.04.03.06 | FinalInstallation,CloseTCO,PrepforFilling |  |  |  |  | 2040 | 2360 |  | 2028-09-18: Final Inspection, Close TCO, Prep for Filling
A10730 | Final cleaning, final test, install purity monitors Detector #2 | 5 |  |  | 5.8333 |  | 1400 |  | 2028-09-18: 5; 2028-09-25: 6; 2028-10-02: 6; 2028-10-09: 6; 2028-10-16: 6; 2028-10-23: 6
|  |  | 2.5 |  |  | 600 |  |  | 2028-09-18: 2.5; 2028-09-25: 2.5; 2028-10-02: 2.5; 2028-10-09: 2.5; 2028-10-16: 2.5; 2028-10-23: 2.5
A364992 | Support TCO Closing | 0 |  |  | 2.4 |  | 480 |  | 2028-10-23: 2.5; 2028-10-30: 3; 2028-11-06: 3; 2028-11-13: 3; 2028-11-20: 0.5
|  |  | 5.6 |  |  | 1120 |  |  | 2028-10-23: 6; 2028-10-30: 6; 2028-11-06: 6; 2028-11-13: 6; 2028-11-20: 4
A365012 | Remove installation infrastructure Detector #2 | 0 |  |  | 3 |  | 480 |  | 2028-11-20: 3; 2028-11-27: 3; 2028-12-04: 3; 2028-12-11: 3
|  |  | 2 |  |  | 320 |  |  | 2028-11-20: 2; 2028-11-27: 2; 2028-12-04: 2; 2028-12-11: 2
| MT - Total FTE hours | 2360 | [6 empty] | 2028-09-18: 200; 2028-09-25: 240; 2028-10-02: 240; 2028-10-09: 240; 2028-10-16: 240; 2028-10-23: 340; 2028-10-30: 120; 2028-11-06: 120; 2028-11-13: 120; 2028-11-20: 140; 2028-11-27: 120; 2028-12-04: 120; 2028-12-11: 120
| SrMT - Total FTE hours | 2040 | [6 empty] | 2028-09-18: 100; 2028-09-25: 100; 2028-10-02: 100; 2028-10-09: 100; 2028-10-16: 100; 2028-10-23: 340; 2028-10-30: 240; 2028-11-06: 240; 2028-11-13: 240; 2028-11-20: 240; 2028-11-27: 80; 2028-12-04: 80; 2028-12-11: 80
| B_Elec Consortia - Total FTE per shifts | 1280 | [6 empty] | 2028-09-18: 120; 2028-09-25: 120; 2028-10-02: 120; 2028-10-09: 120; 2028-10-16: 120; 2028-10-23: 120; 2028-10-30: 80; 2028-11-06: 80; 2028-11-13: 80; 2028-11-20: 80; 2028-11-27: 80; 2028-12-04: 80; 2028-12-11: 80
| PD Consortia - Total FTE hours | 1040 | [6 empty] | 2028-09-18: 80; 2028-09-25: 80; 2028-10-02: 80; 2028-10-09: 80; 2028-10-16: 80; 2028-10-23: 80; 2028-10-30: 80; 2028-11-06: 80; 2028-11-13: 80; 2028-11-20: 80; 2028-11-27: 80; 2028-12-04: 80; 2028-12-11: 80
| CRP Consortia - Total FTE hours | 1040 | [6 empty] | 2028-09-18: 80; 2028-09-25: 80; 2028-10-02: 80; 2028-10-09: 80; 2028-10-16: 80; 2028-10-23: 80; 2028-10-30: 80; 2028-11-06: 80; 2028-11-13: 80; 2028-11-20: 80; 2028-11-27: 80; 2028-12-04: 80; 2028-12-11: 80
| HV Consortia - Total FTE hours | 1040 | [6 empty] | 2028-09-18: 80; 2028-09-25: 80; 2028-10-02: 80; 2028-10-09: 80; 2028-10-16: 80; 2028-10-23: 80; 2028-10-30: 80; 2028-11-06: 80; 2028-11-13: 80; 2028-11-20: 80; 2028-11-27: 80; 2028-12-04: 80; 2028-12-11: 80
| TDE Consortia - Total FTE hours | 2400 | [6 empty] | 2028-09-18: 240; 2028-09-25: 240; 2028-10-02: 240; 2028-10-09: 240; 2028-10-16: 160; 2028-10-23: 160; 2028-10-30: 160; 2028-11-06: 160; 2028-11-13: 160; 2028-11-20: 160; 2028-11-27: 160; 2028-12-04: 160; 2028-12-11: 160
| Calci Consortia - Total FTE hours | 2080 | [6 empty] | 2028-09-18: 160; 2028-09-25: 160; 2028-10-02: 160; 2028-10-09: 160; 2028-10-16: 160; 2028-10-23: 160; 2028-10-30: 160; 2028-11-06: 160; 2028-11-13: 160; 2028-11-20: 160; 2028-11-27: 160; 2028-12-04: 160; 2028-12-11: 160