## Slide 1: 302.4.04 – Cryo-assemblies Horizontal Test Weekly status report
Guram Chlachidze
May 20th, 2024

## Slide 2: CA02 test preparations
Cryo-improvements at TS4 in progress, check work status here:
  TS4 action item list - 11_30_2023.xlsx (sharepoint.com)
Stand 4 ORC/Operation status
  APS-TD DSO will be contacted after the cryo-improvements are completed - at least one month before the expected date of CA02 cooldown
    New DSO was informed about expected CA-02 transportation early June
  Addendum to the electrical ORC has been initiated for the helium line heater operation
  Ready to initiate the Stand 4 cryogenic ORC renewal
    Need to obtain the cryo-panel recommendation (Jacob Kintner) and then then approval by the ALD (Sam Posen)
Magnetic probe orientation measurements with a single target
  LT measurements are in progress

## Slide 3: CA02 test preparations (2)
Helium line heater installation
  Total of 10 heaters are installed (both on the supply and return lines)
  Operating procedure has been developed
  Addendum to the electrical ORC has been initiated
  Installation of the shelves is complete
  Grounding all shelves

## Slide 4: More test preparations
Stand 4 documentation
  Test plan and Test readiness verification document have been updated
  Production traveler (464759) for LQXFA/B-02 will be released this week
Remaining components for CA-03 transportation and testing
  Return End Box – PO # 711063 awarded to Meyer Tools Inc.
    Regular Thursday meetings with Meyer Tools Inc.
    All material purchased
    Promised delivery - last week of May
  Interconnect components required for CM pressure test are ready
  Fabrication of the remaining interconnect components in progress at MW9 and IB1, see next slide
    Cryo-Operations group very busy

## Slide 5: Remaining Interconnect Components for CA-03