## Slide 1: OTE Building PMG Report February 25, 2013 Rhonda Merchut

## Slide 2: Agenda
Coordination
OTE Building Project
  State Activities
  Schedule & Fiscal
  Summary Action Items

## Slide 3
IASU Update (IGPP)
Phase 2 scope approximately 85% complete.
CDF Coordination
Demolition for 1st floor OTE/CDF entrance underway.
  CDF barrier to remain in place until OTE is environmentally enclosed & CDF protected from all dirt and dust.

## Slide 4: OTE Outfitting GPP G13-211
Project Request Approved 1/14/13.
FY 13: $2M for VoIP/networking & Contingency.
  Develop Plan for moving ahead with VoIP/Networking w/out tenant layouts.

## Slide 5: OTE Project Status:
Shop drawing review continues
More than 225 RFI’s rec’d from contractor have been responded to.
  RFI’s slowing down.
Schedule analysis, reporting, and cost curve on-going. Continue to work with contractor to provide coordinated information.
Safety procedures continue to be expanded as more subs come onto the project.

## Slide 6: OTE Project Status:
LEED procedures & Action Plan implemented.
  Contractor reporting 99% construction waste has been recycled.
  On track to meet goal of 20% (by cost) of regionally manufactured materials.
  On track to meet goal of 20% (by cost) of recycled content in materials used.

## Slide 7: OTE Building Construction Status:
14 sub-subs working on site.
30-40 workers daily.
  Exterior enclosure well underway.
    Weather barrier
    Window framing & glazing
    Roofing
  CDF 1st floor connection demo nearing completion.
  MEP & FP pipe hanging
  Polished Concrete
  Stairway installation
  Post Tensioning complete

## Slide 8: Exterior Enclosure

## Slide 9
Enclosure Mock-up

## Slide 10
Roofing

## Slide 11
Elevator Steel

## Slide 12
East Stair
Roof Hatch

## Slide 13: Polished Concrete Floor

## Slide 14: MEP, FP

## Slide 15
CDF Demo

## Slide 16: Two Week Look Ahead
Roofing continues on high roof.
Curtain wall framing.
Exterior panels 2nd & 3rd floor.
Glass installation 2nd & 3rd floor ribbon windows.
MEP, FP equipment & pipe runs
1st floor window steel.

## Slide 17: State DCEO Activities
Next DCEO quarterly report to State due 3/29/13 for quarter ending 2/28/13.
Project on schedule for grants to be 100% costed by 5/31/14 grant requirement.

## Slide 18: Schedule Adjustments
44 additional days for additional steel work (SA 16)
  MS 1 Bldg Shell Complete: 5/9/13
  MS 2 Substantial Completion: 11/5/13
    (Project is fully costed at MS 2, retention remains)
  MS 3, Project Complete: 1/29/14

## Slide 19: BMC Schedule

## Slide 20: Schedule

## Slide 21: Schedule

## Slide 22: Schedule Oversight
Weekly Construction Coordination meetings.
  Present status
  2-week look ahead
  Problems, changes effecting upcoming work
Weekly Fermi PM/BMC PM meetings.
  Contractor’s issues & priorities
  Work progress & schedule review, issues impact
Weekly PA change order meetings.
  Review status/priorities of MRFP’s, COR’s
Bi-weekly Design Team/Construction Team meetings.
  Discuss issues, expedite solutions
Monthly Updates.
  Construction Coordinator/Contractor review of as-built work progress percentage of completion

## Slide 23: Tracking Milestones
Project is fully costed at MS 2, retention remains

## Slide 24
BMC Construction BCWS & ACWP
39% costed
41% time
Monthly Average to date: $897,979.54
Required Monthly Average to complete: $1,012,196.95
Per BMC projected: 1 month @ $1.2M,
2 months @ $3M,
            8 months @ ~$0.5M

## Slide 25
BMC Monthly Costing
Monthly Average to date: $897,979.54
Required Monthly Average to complete: $1,012,196.95
Per BMC projected: 1 month @ $1.2M,
2 months @ $3M,
8 months @ ~$0.5M

## Slide 26
601 TSR Budget Balance
ALL Grant Costing w/ BMC Projection

## Slide 27: Financial – GPP Budget for Contingency

## Slide 28: Contingency Management
Sources available to fund change orders:
  IGPP;
  De-scope from anticipated T&M work;
  De-scope from A/E support work;
  DOE backstop (GPP Outfitting project);
  De-scope from main construction work (will not recover all funds);
  Value engineering main construction work

## Slide 29: Supplemental Agreements a/o 2-11-13
9% contingency remaining at SA 17 (incl IGPP, Grant, & GPP)

## Slide 30: Summary Action Items
Continue shop drawing & change order review, RFI responses
Continue construction coordination & oversight.
Initiate plan for engineering design Outfitting GPP including VoIP, networking, furnishings