## Slide 1: AUP DOE IPR July 23-35, 2024 General Instructions & Considerations
HL-LHC AUP DOE IPR – July 23rd–25th 2024

## Slide 2: Charges for AUP DOE IPR
No Surprises in Charges, “standard” Charges for an IPR DOE review
There will be no Director’s Review
First and foremost, we need to insure we are addressing and answering the Charges

## Slide 3: Timeline Status Review
DOE IPR Jul. 23rd – 25th
Posting Monday Jul 8th (after 4th)
Plenary/L2 Rehars. Week Jun 24th
  To accommodate “FNAL Low Tempo” period on Jul 1st – 5th
L3 Rehars. Weeks Jun. 10th & 17th
  EVMS Reports ready by ~13th–14th of June (for May closing)
  Preliminary versions on week of Jun 10th will miss EVMS Closing numbers
Decision: May ’24 Closing for DOE Review

## Slide 4: Agenda Considerations
Rebaseline/COVID related presentations can be dropped for the Jul. ‘24 IPR.
Activities in 302.2 (Magnets) are winding down in several L3s and talks can be consolidated
CryoAssemblies (302.4) and Cavities (302.3) are still at flat-top execution
Decisions:
  Limit Agenda to 2 Parallel Sessions (after 1st day morning Plenary)
  Consolidation of Management (302.1) and Magnets (302.2) talks.
  Include tour of facilities (suggested by DOE)
Highlighted in Red are
“Rebaseline Specific” talks
that we are dropping to
Consolidate the schedule

## Slide 5: Logistic
Agenda already shared with DOE and OPSS, as well as all L2/Deputy L2s.
  1st day:
    8:45 to 12:15: Plenary Session
    13:15 to 16:30: Breakout Sessions
  2nd day:
    9:00 to 10:00: Tour of FNAL Cryoassembly and Test Facilities
    10:00 to 14:50: Breakout Sessions
  2 parallel sessions:
    Magnets and CM/CA
    Crab Cavities and Management
    C&S Drilldown planned at the end of presentation, but will commit to accommodate any request from the Review team
OPSS taking care of multiple ZOOM-rooms (to be confirmed).

## Slide 6: Proposed Agenda@IPR (Jul. 2024)

## Slide 7: General Points
The AUP Rebaseline request was reviewed by DOE on Dec. 12th – 15th 2022, and approved on March 20th 2023.
There have been no DOE reviews since then.
This is a DOE “Independent Project Review” (IPR), and the purpose is to assess status and progress since the last DOE review.
There will not be a Director’s review in preparation for this review. It is important to allocate adequate time for documentation updates, presentation preparations, and rehearsals.
We need to conduct the annual CAM training and bottom-up ETC exercise prior to the review. Lorri will coordinate with CAMs.
We need to show that production is under control, highlight technical achievements and deliverables, and show that we are on track to complete the project within the cost and schedule contingency.
We should not hide that significant risks remain, but those are properly captured in the Risk Register.
We should also highlight major QA/QC issues and the prompt incorporation of Lessons Learned in the manufacturing flow.
We should take credit for ES&H safety record in many areas, and in areas where there were incidents, we need to own the event and show the Lessons Learned. Make sure to emphasize adequate “Work Planning and Control” practices.
See following slides on Presentation Template and additional guidance on L2/L3s presentation content.

## Slide 8: System or Sub-system 302.X.YY Please use these slides as template
Speaker - Lab
HL-LHC AUP DOE IPR – July 23rd–25th 2024

## Slide 9: Housekeeping
The title of the presentation, the name of the file and the agenda title shall be the same (modulo version #) !
Presentation Title
File Name
Agenda Title
!! Make the page
# white !!!

## Slide 10: Charges

## Slide 11: The following slides are “outline slides” for the various L2/L3/CAMs presentations

## Slide 12: Proposed Outline for L2/L3 Presentations
Lab
Logo
If all activities you are discussing are concentrated
in a Lab, you can use a Lab logo here
Charge #
If a slide is addressing a specific charge, write
the Charge # on the top of the slide.

## Slide 13: General Outline
Scope, Interfaces, Dependencies & Team
Achievements since Rebaseline Review
Procurement Status
Schedule
Cost and Schedule Performance & VAR Reports
BCRs since Rebaseline Review
Estimate at Completion and EAC Manual Adjustments
QA/QC
Risks
ES&H
Summary
Lab
Logo

## Slide 14: WBS 302.X.YY: Scope and Interfaces
List all CERN-approved FRS, Acceptance Criteria, Material Lists, Interfaces that allow you to define your WBS scope.
  Mention upcoming updates, if/when applicable
Use snapshots from WBS dictionary
  US-HiLumi-doc-39 (update your WBS entry if needed!)
Use picture/drawings of your scope (if they exist) and status (several L3 should be close to completion)
If applicable, highlight production yield assumptions, observation and deliverables quantities
Show Interface Matrix and List Interface Control Documents, mention any ICD reviews that took place
  Message: WBS scope remains clearly defined and well understood; Interfaces are defined and controlled
Charge #2, #3

## Slide 15: WBS 302.X.YY: External Dependencies
List any external dependencies (from CERN, FNAL, etc.), include agreements and status with links to documents if applicable
Mention changes after Rebaseline with Response actions (if any).
Describe how External Dependencies have impacted or have a potential to impact Cost and Schedule. Examples:
  Delivery of Kits/parts from CERN
  CERN Metrology approvals on Cavities parts
  Message: WBS understands its dependencies on outside resources, external dependencies are captured in the P6 RLS, risks associated with external dependencies are identified and understood.
Charge #3

## Slide 16: WBS 302.X.YY: Team
Organization chart including management and major subsystem, and your place in it.
Down to L3-L4, use official Org structure in US-HiLumi-Docdb 104, then expand to include Team members (available or needed) as you see fit
Lab
Logo
  Message: WBS team in place, there are clear roles and responsibilities
Charge #2

## Slide 17: WBS 302.X.YY: Achievements since Rebaseline
Describe your pre-series and series scope.
List of achieved technical milestones since Rebaseline review
  List any Design Review, PRR reviews, outcome, links to report, etc.
  Include infrastructure developments, fabrication status, test results
  For fabricated items, include actual vs planned production yield
  Include delivered items (e.g., LQXFA/B-01 to CERN, (hopefully) Dressed prototype cavity to TRIUMF
  For Magnets, highlight achievement such as “Fast Training” in #07b and #15 and demonstrated ability to repair magnets by swapping limiting coil(s). Also mentioned problems/solutions such as MQXFA17 splice, etc.
  Message: project has made adequate technical progress. Production is well underway and nearly complete for some WBS elements. Highlight achievements and problems/solutions.
If applicable, include summary Fabrication Status Pie Chart from the “Parts Status” Excel file in FermiPoint (update as needed, information there is from the last Review. CAM is responsible for updating the numbers in Fermipoint, and keep using the same format).
Charge #1

## Slide 18: WBS 302.X.YY: Procurement Status
List status of important WBS procurements:
  Completed and executed
  Upcoming
Mention exposure to Supply Chain Risks, Abnormal Escalation for upcoming procurements (if applicable) or issues with vendors (shipment?) with investigated solutions
  Message: WBS procurements are on-track and being managed successfully; WBS procurement plan is clear, risk due to world-situation are understood; most procurements are done with fixed-price contracts in place.
If applicable, include summary Procurement Status Pie Charts from the “Parts Status” Excel file in FermiPoint (update as needed, information there is from last Review)
Charge #4

## Slide 19: WBS 302.X.YY: Schedule
A “Schedule Cartoon” will be provided for the overall L2 activity (Magnets and Cavities). Highlight where your L3 activities fit in the overall schedule.
  Be prepared to defend critical dates
    Completion of Prototypes, Start of Production, Completion of Production, DOE milestones (CD-1, CD-3a, CD-2, CD-3b, CD-3, “Project” CD-4, DOE ”CD-4”)
  Be aware and highlight critical milestones (see next slide), show ownership and explain significant slippages.
Should you be part of the Critical Path (ask your L2) show that you know and understand the implications.
Lab
Logo
  Message: WBS schedule is clear and consistent with overall schedule. You are aware of Critical Path and major milestones and can explain slippages (if applicable).
Charge #2

## Slide 20: WBS 302.X.YY: Milestones
In L2 Presentations, mention any PEP T1/T2 Milestones that have been breached in the working schedule in your WBS (see table), explain reasons and expectations of further delays going forward.
  Remember, T2 Milestones are Federal Project Director Milestones and had a 6-month reporting float at the time of rebaseline. T1 Milestones are DOE Program Milestones and had a 12-month reporting float.
  Differentiate between delays due to activities added to the WBS (e.g., coils/magnet added for CA01 acceptance) and delays due to WBS execution performance (e.g., CM02 capillary reworks).
T1/T2 Remaining Milestones | PEP Date
T1:Shipment of 08 Dressed Cavities to CERN Completed | 15-Aug-25
T1:Shipment of 10 Dressed Cavities to CERN Completed | 26-Nov-25
T1:Shipment Q1/Q3 Cryo Ass'y 08 to CERN Completed | 12-Nov-26
T1:Shipment Q1/Q3 Cryo Ass'y 10 to CERN Completed | 13-Aug-27
T1:CD-4:Approve Project Completion | 04-Jan-28
T2:Receipt of Bare Cavity Series | 26-Jun-2024
T2:Bare Cavities Fab Complete | 26-Jun-2024
T2:Bare Cavities Processing & Test Complete | 18-Nov-2024
T2:Coil Production Complete | 10-Apr-2024
T2:Shipment of 08 Dressed Cavities to TRIUMF Completed | 17-Feb-2025
T2:Dressed Cavities Fab Complete | 17-Mar-2025
T2:Dressed Cavities Processing & Test Complete | 29-Apr-2025
T2:Shipment of 10 Dressed Cavities to TRIUMF Completed | 27-May-2025
T2:Magnet Production Complete | 3-Mar-2025
T2:Key Performance Parameters for Crab Cavities Achieved | 30-Jul-2025
T2:Cold Mass Production Complete | 7-Jul-2025
T2:Shipment Q1/Q3 Cryo Ass'y 08 to CERN Completed | 12-May-2026
T2:Cryo Ass'y Testing Complete | 17-Dec-2026
T2:Shipment Q1/Q3 Cryo Ass'y to CERN Completed | 15-Feb-2027
T2:Shipment Q1/Q3 Cryo Ass'y 10 to CERN Completed | 15-Feb-2027
T2:Key Performance Parameters for Q1/Q3 Cryo-Assemblies Achieved | 9-Apr-2027
T2:CD-4:Approve Project Completion | 6-Jul-2027
Charge #2

## Slide 21: WBS 302.X.YY: Cost and Schedule Performance & VAR Reports
Plot of historical control account CPI, SPI from FermiPoint Excel file. Example: CA 302.2.07:
Describe Variances (understand Yellow/Red Thresholds, list of VARs from CAM e-Toolbox) and your plan to bring back to ~ 1.0 (if applicable)
Standard Plots will be distributed by Project Office
  Message: Control Account/WBS cost and schedule historical performance is reasonable and under control; variances well understood and documented; plan to recover (if applicable) is sound and credible
CPI
SPI
Include cumulative
table from CAM e-Toolbox
Turn on “green” to show where you are doing fine !
Charge #2

## Slide 22: WBS 302.X.YY: BCRs Approved Since Baseline
BCR # | Description | Cost ($k) | Sch. (days)
348 | Magnet Spare Parts Order | 327k | 0
350 | Probe Orientation Measurement with a Single Mirror Target | 52k | 0
351 | IFS Bundle Rework on CM02, 03, and 3 magnets at FNAL and Associated Delays | 2,118k | 4 mos.
352 | Critical DR on MQXFA-17 and other Schedule Impacts to WBS 302.2 | 136k | 0
List the BCRs submitted and approved for this WBS since the Rebaseline. Briefly explain any major BCRs. Example:
  Message: Formal Change Control Process is strictly followed for any changes needed in WBS activities. Full traceability of changes.
Charge #2

## Slide 23: WBS 302.X.YY: Estimate at Completion
Talk about:
  Your CA Variance at Completion (BAC- EAC) and explain the difference
  Explain any manual EAC adjustment (see next slide)
  What is the impact on your EAC coming from other Control Accounts (e.g., production yield impact from other CAs), etc.
  In some cases an EAC table might help (use the information from the P6 Status Sheets “EAC” tab in FermiPoint)
  L2s should show credit for lessons learned, show how they have informed the updated BOEs/ETC. Include a slide summarizing remaining scope and any changes implemented based on actuals and lessons learned.
  Message: ETC is reasonably up-to-date, accurate, and credible. You are aware of how performance of other control accounts is impacting your ETC. Actuals and lessons learned have informed the ETC.
Include At Complete table from CAM e-Toolbox
Charge #2

## Slide 24: WBS 302.X.YY: EAC Manual Adjustments
WBS | EAC Manual Adjustment Description | Cost ($k)
302.1 | New FNAL charging practices, general training and conferences | $1,000k
302.1 | Additional Costs for Shipment of Assemblies to CERN ($67.5k for travel with each shipment, 10k for improvements to the shipping container, $36k for accelerometers) | $89.5k
302.1 | FNAL balance in CERN Exchange Document | $611k
List any EAC Manual Adjustment Entries for this WBS (if applicable). Explain why major adjustments have not been turned into BCRs yet. Example for 302.1:
  Message: Proactive use of EAC manual adjustments to assess realistic amount of EAC-based remaining contingency.
Charge #2

## Slide 25: WBS 302.X.YY: QA/QC
List any approved CERN MIPs with links for your WBS (show an example)
List any NCRs, for major ones explain root causes and corrective actions
  Important topic for Coils and Magnet Fabrication WBSs because of potential for lower yield than assumed
  Message: WBS follows project QA/QC processes; NCRs corrective actions are effective (problems are not repeated); lessons learned shared; etc.
DON’T MAKE THIS CHEESY !
DON’T REPEAT BOILERPLATE INFO
IT MIGHT APPLY ONLY TO SOME CA
Charge #1

## Slide 26: WBS 302.X.YY: Risks
List WBS risks, risks updates since Rebaseline
  Retired risks, realized risks (managed or closed), updated risks, new identified risk, etc
  Describe your WBS top risks
    Include a slide in each presentation detailing risks/challenges that are “keeping folks up at night”. Avoid perception of easy road ahead (if applicable)
    L2s should address the Estimate Uncertainty for the remaining scope to better communicate/address the remaining challenges. Include Estimate Type pie chart.
  Message: WBS risks are identified, up to date, and are being actively managed. In some WBSs, Significant challenges remain that require healthy contingency (EU, Discrete Risks).
Charge #6

## Slide 27: WBS 302.X.YY: ES&H
Any safety reviews? Any Safety incidents?
  If there were OPRs in your area of responsibility, demonstrate ownership and mention lessons learned.
  Highlight reporting promptness and “erring on the side of safety”
Take credit for great safety record if applicable. Mention number of worked hours without DARTs
For fabrication activities, include links to approved equipment ORCs, Hazard Analysis, etc.
For the ES&H breakout presentation, add more details and examples of implementation at the different sites (Work Planning and Control, Org Charts, Partner Lab summary of discussions and salient issues)
  Message: WBS ES&H is being handled appropriately; you are aware of ORPs/Lessons Learned in your area of responsibility
DON’T MAKE THIS CHEESY !
DON’T REPEAT BOILERPLATE INFO
SHOW SPECIFIC EXAMPLES (IF YOU HAVE ANY)
Charge #5

## Slide 28: WBS 302.X.YY: Summary
Summarize the main points you made before directly supporting the review charge.
Avoid too many details about numbers (“bureaucratic” stuff). Emphasize status and challenges of project.
Lab
Logo
  Message: Execution of this WBS is proceeding according to the baseline plan, adequate technical progress, cost and schedule are credible and in control, risks are understood and actively managed.

## Slide 29: Backup Slides
You should keep the pie-charts and tables from the CAM e-Toolbox as backup slides in case someone asks questions

## Slide 30: 302.2.03 Resource Type Breakdown
77% Labor, 23% M&S
M&S Includes contractors (braiding vendor), travel, shipment, etc.
Lab
Logo
Example from 302.2.03
Plots to be provided by PO
To be Updated
Charge #2

## Slide 31: 302.2.03 Estimate Quality
Conceptual is related to the RRR measurements
  FNAL has been measuring RRR up to earlier this year
  LBNL’s new system is undergoing benchmarking approval
Preliminary is mostly related to Insulation
  Master Agreement is being placed to lock down the price throughout AUP
The quality of estimate has been updated for CD-2/3b
Lab
Logo
Example from 302.2.03
Plots to be provided by PO
To be Updated
Charge #2

## Slide 32: 302.2.03 FTE Breakdown
From 5/31/18 forward
  Does not include FY18 Actuals
Lab
Logo
Example from 302.2.03
Plots to be provided by PO
To be Updated
Charge #2

## Slide 33: 302.2.03 Cost Performance Report
BAC = $5.658M
No thresholds crossed in Current Period Cost
No thresholds crossed in Cumulative to Date
Cumulative SPI = 0.9, CPI = 1.05
Example from 302.2.03
Plots to be provided by PO
To be Updated
Charge #2