## Slide 1: 302.4.05 - Q1(Q3) Cryo-Assembly Integration and Coordination
Sandor Feher – FNAL
L3/CAM - Q1/Q3 Cry-Assembly Integration and Coordination
HL-LHC AUP DOE IPR – July 23rd–25th 2024

## Slide 2: Outline
Scope, Interfaces, Dependencies & Team
Achievements since Rebaseline Review
Procurement Status
Schedule
Cost and Schedule Performance & VAR Reports
Estimate at Completion and EAC Manual
Risks
QA/QC
Summary

## Slide 3: WBS 302.4.05: Scope
Scope is defined in the WBS dictionary - US-HiLumi-doc-39
Charge #2, #3

## Slide 4: HL-LHC String Test
AUP participation is planned – this task is part of 302.4.05
WCC: Water-Cooled Cables
GMS: Gas Management System
SQXL: String Cryogenic Line
DFHX/DFX: HTS/LTS Electrical Feedbox
SC link: Superconducting Link
CDB: Circuit Disconnector Boxes
String Mezzanine (~ part of HL-LHC UR Gallery)
Charge #2, #3

## Slide 5: WBS 302.4.05: Interfaces
  Q1/Q3 Cryo-assembly Interface Control Matrix
  Reference to Interface Control Document for each interface
  In each ICD we have identified and list all the interfaces
  Integration and coordination has interfaces with all the L3 elements and with CERN
Interface Matrix US-HiLumi-doc-219
Charge #2, #3

## Slide 6: WBS 302.4.05: External Dependencies
This part of the project is dealing with most of 302.4 interfaces
Interfaces Internal to AUP
  Magnet Fabrication; magnet delivery schedule and magnet non-conformities that are repaired by 302.4
  Change in the Magnet-Cold Mass Interface induced schedule delay and cost overrun
Interfaces External to AUP mainly related to CERN but also to procurement. Past examples:
  CERN introduced a new Pressure Wave requirement
  There were several other minor changes in the specifications as well (like alignment and survey specs)
  Several nonconformities discovered in the delivered products from CERN as part of the parts exchange
Charge #2, #3

## Slide 7: WBS 302.4.05: Organization
302.4
Q1/Q3 Cryo-assemblies Fabrication
L2: S. Feher
(T. Strauss)
302.4.02
Cold Mass Assemblies Fabrication
L3/CAM: F. Nobrega (A. Vouris)
302.4.03
Cryo-Assemblies Fabrication
L3-CAM: F. Nobrega (R. Rabehl)
302.4.04
Cryo-Assemblies Horizontal Test
L3/CAM: G. Chlachidze
(S. Stoynev)
302.4.01
Magnets Vertical Test
L3/CAM: P. Joshi (F. Kurian)
302.4.05
Q1/Q3 Cryo-assembly Integration and Coordination
L3/CAM S. Feher (T. Strauss)
302.4.04.03
Horizontal Test Stand Operations
L4: G. Chlachidze (S. Stoynev)
302.4.04.02
Instrumentation and Mechanical Horizontal Test Stand Upgrade
L4: G. Chlachidze (S. Stoynev)
302.4.04.01
Cryo-Mechanical Horizontal Test Stand Upgrade
L4: R. Rabehl
302.4.04.99
L3 Management Cryo-assemblies Horizontal Test
L3: G. Chlachidze (S. Stoynev)
Control Account
Sandor Feher L3/CAM
Thomas Strauss L3 Deputy
Experienced Team from
BNL and FNAL
Fermilab and BNL provide the appropriate support and infrastructure
Charge #2

## Slide 8: WBS 302.4.05: Achievements since re-baseline
Worked on the pre-series and first series CM and Cryo-assembly production
Several magnet, Cold Mass and Cryo-assembly related DRs and NCRs have been worked on and resolved
Documentation - drawing and traveler updates; developed combination pressure and leak check procedure
Several studies related to Cryo-assembly safety have been updated as the procedures have been improved
Charge #1

## Slide 9: WBS 302.4.05: Procurement Status
Charge #4
Remaining Procurements are mostly travel to and from CERN and travel to Collaboration Meetings.
Chart: 302.4.05 Integration
| PO received | With PO, not received yet | Not ordered yet
302.4.05 Integration | 198 | 0 | 27

## Slide 10: WBS 302.4.05: Schedule
Charge #2

## Slide 11: WBS 302.4.05: Cost and Schedule Performance & VAR Reports
  Cost variance fluctuates depending on which phase the project is in.
  CPI is expected to fluctuate around 1.
Charge #2
Chart: 302.4.05 SPI and CPI

## Slide 12: WBS 302.4.05: Estimate at Completion and EAC Manual
VAC ($137.9k) is from current cost variance
No manual adjustment
Charge #2

## Slide 13: WBS 302.4.05: Risks
RT-302-4-05-002 | Issues with untrained magnet in a cryo-assembly during horizontal testing | High
RT-302-4-05-003 | Damage to Cryo-assembly in shipping from FNAL to CERN | Medium
Risks are updated regularly – Risk Management Board
Since re-baseline, we have retired/closed 2 risks
The highest risk (threat) is RT-302-4-05-002
Charge #6

## Slide 14: WBS 302.4.05: Summary
This control account covers the necessary coordination and integration part of the WBS 302.4 sub-project
The tasks covered by this CA have been executed as planned
Risks are actively managed

## Slide 15: Backup Slides

## Slide 16: 302.4.05: Resource Type Breakdown
96% Labor, 4% M&S
M&S Includes travel
Charge #4

## Slide 17: 302.4.05: Estimate Quality
This is a pure LOE account
Charge #4

## Slide 18: 302.4.05: FTE Breakdown
Charge #4

## Slide 19: 302.4.05: Cost Performance Report
BAC = $6.017M
No thresholds crossed in Current Period Cost
Cost thresholds crossed in Cumulative to Date
Cumulative SPI = 1.0, CPI = 0.97
The progress is as anticipated
Charge #4