## Slide 1: Muon Campus Operation Report
Jim Morgan
Friday 09:00 Operations Meeting
May 24, 2024

## Slide 2: Muon Campus status
Study – Alternative M5 optics
Study – M1-M3 Optics
Received permission for beam operation
  Signing “party” Tuesday afternoon
Delivery Ring access period in progress, driven by ESS1 installation
  Still have one more significant LCW leak on a Delivery Ring header
  Quad shunt problems on QS219 and QS319 traced to CAMAC card connection
  Most remaining Muon tunnel enclosures put into Supervised Access Monday
  Needed to secure Delivery Ring Enclosure last night, related to PESD D:IB LOTO for repairs performed May 15 and desire to turn on next week
ESS1 Electrostatic Septum installation
  ESS1 moved from NWA to Delivery Ring on Wednesday
  Installation into Delivery Ring was on Thursday
  Alignment Crew defined D30 centerline Wednesday, aligned septum on Thursday
  Upstream vacuum spool fabricated and leak-checked Thursday afternoon
  Surge resistor support installed Thursday afternoon
ESS2 subassembly work continues at A0 Clean Room
  Cathode straightened by Machine Shop, gets sent out for polishing next
AP-0 A/C work continues to be stalled (now at 57 weeks)
  Waiting for controls sub-contractor to be badged and then show up

## Slide 3: Remaining significant LCW leak in Delivery Ring Enclosure
Leaking header fitting behind H619

## Slide 4: ESS1 installed in Delivery Ring
ESS1
ESS2

## Slide 5: ESS1 view through upstream quartz window

## Slide 6: Upcoming work
ESS1 installation
  Expect to install vacuum spool and begin pumping down today
  Vacuum leak check next week
  Some power supply work today, hope to have ORC next week
  Motion-control check-out on Tuesday
ESS2
  ESS2 cathode polishing (outside vendor), followed by assembly into tank
Additional issues and tunnel work
  LCW leak on header fitting near H619
  Two closed vacuum valves in M4 Line have control cables disconnected
AP-0 A/C work paused while awaiting controls sub-contractor
  Will need access to AP-0 Water Cage and rad fence area, turns off beam to Muon
  Purchasing is being asked to encourage contractor to finish work
  Estimate six days of work needed for system to be operational
  Expect to resume use of portable A/C unit in near future