## Slide 1: 302.4.04 – Cryo-assemblies Horizontal Test Weekly status report
Guram Chlachidze
Jun 3rd, 2024

## Slide 2: CA02 test preparations
Cryo-improvements at TS4 in progress, check work status here:
  TS4 action item list - 11_30_2023.xlsx (sharepoint.com)
Stand 4 ORC/Operation status
  New DSO was informed about expected CA-02 transportation early June
  Stand 4 cryogenic ORC renewal
    Cooldown approval received from Jacob Kintner
    Need approval from the ALD (Sam Posen)
  Addendum to the electrical ORC has been initiated for the helium line heater operation
Stand 4 documentation
  LQXFA/B-02 horizontal test traveler (464759) has been released
  Test plan will be updated this week

## Slide 3: CA02 test preparations (2)
Helium line heater installation
  All 10 heaters are installed (both on the supply and return lines)
  All shelves installed, AC power cables routed and ready to plug in
  Shelves will be grounded today, final checkout by Wed. Jun. 5
  Operating procedure has been developed
  Addendum to the electrical ORC has been initiated

## Slide 4: CA-03 test preparations
CA components required for CA-03 transportation and testing
  Return End Box – PO # 711063 awarded to Meyer Tools Inc.
    Leak Test today afternoon
    Will be shipped soon after the leak test is confirmed successful
  Interconnect components required for CM pressure test are ready
  Fabrication of the remaining interconnect components in progress at MW9 and IB1, see next slide

## Slide 5: Remaining Interconnect Components for CA-03