## Slide 1
FAST / IOTA Shutdown 2023-2024
Enclosure STATUS: ODH-0 & Supervised Access (“same as it ever was”)
General: -IOTA Bake GFCI (AD/Web 57570).
-ESB Laser Lab electrical Req “in Procurement” ™ (357980).
ES&H: -OSC Mode in LL. New South Gate. Interlock Test.
IPI: -ESB 480/120VAC Electric Req being generated.
  -DON’T TOUCH beamline stuff.
  -Exciting IPI updates to follow (Chip)
Water: -Chiller needs repair. Waiting on Req.
-Reminder” Fluids Engineer for us is Mike Hanson
AD Shutdown’24 starts July 12 (5 weeks away)
— Contact FAST RunCo with any work or access requests —

## Slide 2: ISD/CFM Report on NML Status
HiBay LEDs: Completed™. North row needs boom-lift. (Date?)
Exterior lighting: RFQ to contractors, still!
Emergency lights: fix in progress
Bathroom Lights: fixed.
ICW: flushing this Spring. (Date being worked out with CMTF)
ESB HVAC: installation – Waiting on NTP (Summer??)
Mechanical Rooms: Cleanup in progress.
Entrance Striping: Needs our P/T.
R&G: Gravel work done. Turf grading in progress
Pipe connections checked for galvanic activity
Building HVAC chiller fixed (again).

## Slide 3
FAST shutdown continues til summer for the installation of the IOTA Proton Injector. Thanks to support groups helping us.
  (PESD, HLRF, Instrumentation, MSD, ISD, ect..)
IPI source running up to 51kV. Commissioning.
  We made 10kV Protons issues.
IPI electrical work waiting on subcontractor schedule.
LCW chiller repair waiting on subcontractor PO.
ICW strainer developed a small leak. ISD responded promptly.
Thanks to OPS for helping with installations & being vigilant on ACNET alarms.
— Contact FAST RunCo with any work or access requests —
FAST / IOTA 9:00 Report