## Slide 1: Cryo Assembly, Cold Mass Status
A. Vouris
Cryo Assy L2 Meeting
June 10, 2024

## Slide 2: Cold Mass Tooling & Design Status
WorkStation Equipment
  Status
    End Can
      Lead End – Pallet jack cart drawings and note for 2nd unit
      Order additional pallet jack w/ extended forks
    Cold Mass drawings
      Working through redlines for next batch of drawing mods
        dwg for revisions: Magnet Model updated in all drawings
          F10103605 – Released/printed
          F10151260 – Released/printed
          F10178090 – Capillary tube install update – waiting for print to chk
          F10172809 – Pressure test drawing default updates from lower dwg
          Update Drawing tree - as needed after final revisions
    Additional tooling:
      Metrology: adjust/re-survey Welding Station – Rails adjusted and now w/in +/- .04

## Slide 3: Cold Mass Tooling & Design Status
Cold Mass
  Engr Analysis & Note:
    Detailed procedures complete
    Cold Mass Rework Plan – draft in process
  Cold Mass Welds
    Welding:
      Fronius – adding power cut off at machine per safety requirements
      Calibration plates RT’d complete (passed) – forwarded to J. Seyl
      Welder Qualification plates: passed – new welder (Tyler qualified)
      Borescope - Rental quote received from 1st vendor (380.00 +50/day, 1520.00 +200/wk, 3800 + 500/mo)
      Borescope – Ordered last week (WeldStar PO 715095) – should see in a week
      Need to qualify more welders (Riley, Austin)

## Slide 4: Cold Mass Tooling & Design Status
Cold Mass
  CM-02 – CA-02 - See R. Rahbel talk
  CM-03
    Electrical Check complete - End covers fit/tack complete
    Circ weld grinding
    Elbow welding complete
    SSW complete and results reviewed
    Saddles – welding complete
    Welds – dressing on high spots on welds – finishing up today
    UT vendor – scheduling for Tuesday (11-June-2024)
    FSI targets welding complete, N line saddles – welding in process
    Fitting/mach/weld flare fittings – (HT-X flares 4x welded complete) Beam tube ring mach
  CM-04 (MQXFA-08b & MQXFA-14b)
    Beam tube & Ht-X’s installed complete
    Buss/Loop installed & movement confirmed - bus lock length to be milled
    Magnet alignment: SSW verified – Metrology Survey complete and matches
  CM-05/CM-06 Alignment Station set up
    Received MQXFA07b Survey complete. Receiving work in progress: wire spilces and RTD install
    Expecting MQXFA15 Survey complete. Receiving work in progress

## Slide 5: Cold Mass Tooling & Design Status
Cold Mass (cont)
  Production Series
    Final 2 items for procurement:
      Tack Blocks – in QCR reviewed and dispositioned – Reviewed rework of first few and passed. Vendor will proceed to repair the balance including second batch returned
      Lower Saddles, cold mass – reviewing QCRs
      Production N-lines - leak test 100% complete
      Formed Plates in stock at FNAL for CM-05, CM-06 and CM-07
      CM-06 thru CM-10 & Spare Shell Plate Machining PO (REQ #355609)
        CM-05 shells Rec’d
        CM-06 shells at machining vendor
      Shell Plate Forming: CM-10 Pick up scheduled for Tue. (11 June)
      CM-05 – CM-10 & Spare Saddle –
        receiving 1 pc for inspection prior to balance rework.
        Adding thread check on all parts (100%)
      CM-05 – CM-10 & Spare Tack blocks – received and in stock
    Magnet 16
      In temp storage (ICB)
    Q1-Q3 Bus production
      Units up to CM-10 plus 1 spare are complete
      1 Spare Buss – waiting for housing parts