## Slide 1: ICARUS Plans for 2024 Summer Shutdown
C. Montanari
FNAL – INFN Pavia
ICARUS Technical Board Meeting – June 14, 2024

## Slide 2: Working Groups Activities
  Beam off on July 12, 2024 - Beam on at the beginning of October 2024
  TPC WG
    Onsite activities during the second half of August
  Trigger WG
    Several hardware tests and upgrades (see slides) happening in August and September
  DAQ, Networking, Slow Controls
    Slow controls: possible upgrades (to be checked, activity with little or no impact on other activities)
    Networking checks (to be checked, activity with little or no impact on other activities)
  PMT WG
    Calibration and synchronization at least 3 weeks before the return of neutrino beams
    Fine calibration and synchronization done one week before the return of neutrino beams
    Arrangement of racks cabling happening sometime during the summer shutdown (see slides)
    Laser activities immediately after the shutdown (see slides)
  CRT WG
    …

## Slide 3: Working Groups Activities (cont.) (See slides)
  Beam off on July 12, 2024 - Beam on at the beginning of October 2024
  Calibrations WG
    …
  Drift HV WG
    Test backup desktop, replace UPS batteries, test emergency power down sequence (see slides)
  Cryogenics
    LN2 pump maintenance
    East LAr pump regular maintenance
    West LAr pump regular maintenance
    LAr refill (TBD)
  DAQ
    Transition of servers to Linux AL9 . Variance for using SL7 (on some servers) granted for Icarus while transition to AL9 is taking place. Test of new operating system requires 3 weeks (8 hrs working days) (end of July to mid August)
    Upgrades of A3818 boards drivers (see slides)
    Replacement of obsolete servers (ongoing activity, see slides)

## Slide 4: July 2024
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
23 | 24 | 25 | 26 | 27 | 28 | 29
30 | 1 | 2 | 3 | 4 | 5 | 6
7 | 8 | 9 | 12 | 13 | 12 BEAM OFF | 13
14 | 15 WEST LAr pump Maintenance Laser activities | 16 WEST LAr pump Maintenance Laser activities | 17 WEST LAr pump Maintenance Laser activities | 18 Laser activities | 19 Laser activities | 20
21 | 22 EAST LAr pump Maintenance Laser activities | 23 EAST LAr pump Maintenance Laser activities | 24 EAST LAr pump Maintenance Laser activities | 25 Laser activities | 26 No data (7 am – 4 pm) | 27
28 | 29 PU4300 LN2 pump maintenance Start transition of production servers to AL9 | 30 PU4300 LN2 pump maintenance | 31 PU4300 LN2 pump maintenance | 1 | 2 | 3

## Slide 5: August 2024
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
28 | 29 | 30 | 31 | 1 | 2 | 3
4 | 5 | 6 | 7 | 8 Power cut (8 hr) Install backup drift HV desktop | 9 Replacement of drift HV UPS battery | 10
11 | 12 | 13 | 14 | 15 | 16 | 17
18 | 19 TPC works | 20 TPC works | 21 TPC works | 22 TPC works End of testing of servers with AL9 | 23 TPC works | 24
25 | 26 TPC works | 27 TPC works | 28 TPC works | 29 TPC works | 30 TPC works | 31

## Slide 6: September 2024
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
1 | 2 | 3 Power cut (7-7:30am) Removal of backup drift HV desktop | 4 | 5 | 6 | 7
8 | 9 | 10 | 11 | 12 | 13 | 14
15 | 16 Power cut (7-7:30am) | 17 | 18 | 19 | 20 | 21
22 | 23 Grace period for testing readiness for neutrino beams | 24 Grace period for testing readiness for neutrino beams | 25 Grace period for testing readiness for neutrino beams | 26 Grace period for testing readiness for neutrino beams | 27 Grace period for testing readiness for neutrino beams | 28
29 | 30 | 1 BEAM ON | 2 | 3 | 4 | 5

## Slide 7: Summary of present requirements