## Slide 1: 302.4.04 – Cryo-assemblies Horizontal Test Weekly status report
Guram Chlachidze
Jun 17th, 2024

## Slide 2: CA02 test preparations
Cryo-improvements at TS4 are complete, check details here:
  TS4 action item list - 11_30_2023.xlsx (sharepoint.com)
Stand 4 ORC/Operation status
  Stand 4 cryogenic ORC has been refreshed
    Cooldown permit is obtained
  Addendum to the electrical ORC has been initiated for the helium line heater operation, still to be approved
Helium line heater installation is complete
  Without insulation, providing access for inspection
Stand 4 documentation
  LQXFA/B-02 horizontal test traveler (464759) has been released
  Test plan is ready for approval

## Slide 3: CA02 transportation from ICBA to IB1
CA transportation was uneventful, the procedure has been established (as described in DocDB# 4352)
  Accelerometer data to be analyzed
Loading on the trailer in ICBA

## Slide 4: CA02 transportation from ICBA to IB1 (2)

## Slide 5: Preparation work at Staging area
Power leads trimmed to the required length; voltage taps installed on the leads
Verified location of sealing surfaces in the interconnect area
  No spacers - double-side CF flanges are required in CA-02
Verified vacuum around the warm finger
Final electrical checkout, includes Hi-potting test at room temperature, checkout of the voltage taps, RTDs, protection heaters
Vacuum sleeve installed

## Slide 6: Installation on Stand 4

## Slide 7: Installation on Stand 4 (2)

## Slide 8: Next Steps
Final alignment at Stand 4 – Today, Jun. 17
Splicing leads, closing interconnect joints, installation of the thermal shields, closing insulating vacuum
Final electrical checkouts at room temperature
Quench Detection and Monitoring setup
Pump out of the insulation vacuum
Room temperature magnetic measurements
Controlled cooldown