## Slide 1: ICARUS Plans for 2024 Summer Shutdown
C. Montanari
FNAL – INFN Pavia
ICARUS Technical Board Meeting – June 28, 2024

## Slide 2: Working Groups Activities
  Beam off on July 12, 2024 - Beam on at the beginning of October 2024
  TPC WG
    Onsite activities during the second half of August
  Trigger WG
    Several hardware tests and upgrades (see slides) happening in August and September
  DAQ, Networking, Slow Controls
    Slow controls: possible upgrades (to be checked, activity with little or no impact on other activities)
    Networking checks (to be checked, activity with little or no impact on other activities)
  PMT WG
    Calibration and synchronization at least 3 weeks before the return of neutrino beams
    Fine calibration and synchronization done one week before the return of neutrino beams
    Arrangement of racks cabling happening sometime during the summer shutdown (see slides)
    Laser activities immediately after the shutdown (see slides)
  CRT WG
    Timing and DAQ

## Slide 3: Working Groups Activities (cont.) (See slides)
  Beam off on July 12, 2024 - Beam on at the beginning of October 2024
  Calibrations WG
    …
  Drift HV WG
    Test backup desktop, replace UPS batteries, test emergency power down sequence (see slides)
  Cryogenics
    LN2 pump maintenance
    East LAr pump regular maintenance
    West LAr pump regular maintenance
    LAr refill (TBD)
  DAQ
    Transition of servers to Linux AL9 . Variance for using SL7 (on some servers) granted for Icarus while transition to AL9 is taking place. Test of new operating system requires 3 weeks (8 hrs working days) (end of July to mid August)
    Upgrades of A3818 boards drivers (see slides)
    Replacement of obsolete servers (ongoing activity, see slides)

## Slide 4: July 2024
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
23 | 24 | 25 | 26 | 27 | 28 | 29
30 | 1 | 2 | 3 | 4 | 5 | 6
7 | 8 | 9 | 10 | 11 | 12 BEAM OFF LAr pumps off Calibrations | 13 Calibrations
14 | 15 WEST and EAST LAr pump maintenance Laser activities Calibrations | 16 WEST and EAST LAr pump maintenance Laser activities Drift HV down | 17 WEST and EAST LAr pump maintenance Laser activities Drift HV up | 18 Laser activities | 19 Laser activities Calibrations | 20
21 | 22 Laser activities Calibrations Trigger (overnight) | 23 Laser activities Calibrations Trigger (overnight) | 24 Laser activities Calibrations Trigger (overnight) | 25 Laser activities Calibrations Trigger (overnight) | 26 Trigger (overnight) | 27
28 | 29 PU4300 LN2 pump maintenance Start transition of production servers to AL9 Calibrations | 30 PU4300 LN2 pump maintenance Calibrations | 31 PU4300 LN2 pump maintenance Calibrations | 1 Calibrations | 2 Calibrations | 3 Calibrations

## Slide 5: August 2024
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
28 | 29 Calibrations | 30 Trigger Calibrations | 31 Trigger Calibrations | 1 Trigger Calibrations | 2 Trigger Calibrations | 3
4 | 5 Trigger Calibrations | 6 Trigger Calibrations | 7 Trigger HV off Calibrations (with all HV off) Everything OFF | 8 Power cut (8 hr) Install backup drift HV desktop | 9 Replacement of drift HV UPS battery Everything ON | 10
11 | 12 Trigger Calibrations | 13 Trigger Calibrations | 14 Trigger Calibrations | 15 Trigger | 16 Trigger | 17
18 | 19 Trigger | 20 Trigger | 21 Trigger | 22 End of testing of servers with AL9 Trigger | 23 Trigger | 24
25 | 26 TPC works Calibrations | 27 TPC works Calibrations | 28 TPC works Calibrations | 29 TPC works Calibrations | 30 TPC works Calibrations | 31

## Slide 6: September 2024
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
1 | 2 Calibrations Everything OFF | 3 Power cut (7-7:30am) Removal of backup drift HV desktop Everything ON | 4 Calibrations | 5 Calibrations | 6 Calibrations | 7
8 | 9 Calibrations Additional PMT server Installation | 10 Calibrations Additional PMT server test | 11 Calibrations Additional PMT server test | 12 Calibrations Additional PMT server test | 13 Calibrations Additional PMT server test | 14
15 Everything OFF | 16 Power cut (7-7:30am) Everything ON | 17 Calibrations | 18 Calibrations | 19 Calibrations | 20 Calibrations | 21
22 | 23 Grace period for testing readiness for neutrino beams | 24 Grace period for testing readiness for neutrino beams | 25 Grace period for testing readiness for neutrino beams | 26 Grace period for testing readiness for neutrino beams | 27 Grace period for testing readiness for neutrino beams | 28
29 | 30 | 1 BEAM ON? | 2 | 3 | 4 | 5

## Slide 7: Summary of present requirements