## Slide 1
Project Activities for MSD
Mayling Wong-Squires
AD Operations Friday 9am Meeting
21 June 2024

## Slide 2: PIP-II Vacuum Systems Updates Lucy Nobrega (L3/CAM), Sherese Humphrey (Interim CAM), Alex Chen (Lead Vacuum Engineer), Rich Andrews (Chamber design), Eric Pirtle (Design)
Working on
Procurement of Warm Front End and Superconducting Linac vacuum equipment
Writing travelers and finalizing handoff documentation
Final design for Beam Transfer Line and Beam Absorber line
  Detail BTL/BAL Vacuum CAD model and magnets interspaces configurations with input from stakeholders: MagPS, BI, BTL/BAL Installation
  Vacuum chamber design for dipole magnets (quantity 40) in coordination with MagPS
  Final design of interfaces with Beam Instrumentation devices, Booster vacuum, Beam Absorber Line
  Validation of equipment selection with vacuum pressure and structural simulations
Addressing review recommendation: review of vacuum analysis (K Duel)
Finalizing designs of laserwire UHV chamber, commissioning cart, wide aperture BPM’s (D Krokosz)
Finalizing design of laserwire optics and adjustment stages (T Price)
Department resources needed
Vacuum technician for acceptance testing and vacuum cart assembly (starting October)
Fabrication Procurement: BTL dipole & septum chambers
Design/Drafting: BTL design & integration (E Pirtle)

## Slide 3: PIP-II Vacuum Systems Updates (cont’d)
Vacuum Systems, Machine Protection, LLRF, and HPRF System Interfaces Signal Diagram from Integrated Vacuum Systems Final Design Review (completed May 7, 2024)

## Slide 4: PIP-II BTL Collimators
MSD personnel involved
  Bob Donahue – engineering
  JP Walano – drafting
  Kevin Duel – drawing approver
  Christine Ader – engineering note reviewer
PRR deliverables are complete
  Engineering note approved and released
  All drawings released
Upcoming:
  PRR in July
  Initiate procurements/fabrications after PRR complete
Horizontal collimator
Vertical collimator

## Slide 5: LBNF Primary Vacuum and Magnet Installation Kevin Duel, Ty Funk, Monika Sadowski, Jason Morin, Matthew Volante, Peggy Jones, James Williams
Primary Vacuum
  Beamline vacuum drawings released and working on magnet beam tube drawing releasing and assembly structure
  Kicker ceramic beam tube TiN coating outgassing tests completed in May and results are acceptable
    Coating specific outgassing rate determined to be 3x10-10 Torr-L/s/cm2
    Waiting for 12” long tube samples from vendor
    Vendor tested process with glass tubes and results were satisfactory
  Meeting with MI again soon to finalize relocation of components the LBNF beamline interferes with at MI-10
Magnet Installation
  Multiwire stand drawings and engineering note approved and released
  Quad installation procedure writing in process
  Corrector magnet installation fixture design engineering note writing in process