## Slide 1: Cryo Assembly, Cold Mass Status
A. Vouris
Cryo Assy L2 Meeting
July 08, 2024

## Slide 2: Cold Mass Tooling & Design Status
WorkStation Equipment
  Status
    End Can
      Lead End – Pallet jack cart drawings and note for 2nd unit
      Order additional pallet jack w/ extended forks
    Cold Mass drawings
      Working through redlines for next batch of drawing mods
        dwg for revisions: Magnet Model updated in all drawings
          F10103605 – Released/printed
          F10151260 – Released/printed
          F10178090 – Capillary tube install update – reviewed and redlined, new updated drawings received this morning
          F10172809 – Pressure test drawing default updates from lower dwg
          Update Drawing tree - as needed after final revisions
          Fixture for Beam Tube – completed, released and in machining
    Additional tooling:
      Metrology: adjust/re-survey Welding Station – Rails adjusted and now w/in +/- .04

## Slide 3: Cold Mass Tooling & Design Status
Cold Mass
  Engr Analysis & Note:
    Detailed procedures complete
    Cold Mass Rework Plan – minor edits in progress DocDb-5158
  Cold Mass Welds
    Welding:
      Fronius – adding power cut off at machine per safety requirements
      Calibration plates RT’d complete (passed) – forwarded to J. Seyl
      Welder Qualification plates: passed – new welder (Tyler qualified)
      Borescope - Rental quote received from 1st vendor (380.00 +50/day, 1520.00 +200/wk, 3800 + 500/mo)
      Borescope – Ordered (WeldStar PO 715095) – received
      Qualify more welders (Riley, Austin) – Coupon complete from Riley. PO in progress and will drop off in next 1-2 days.

## Slide 4: Cold Mass Tooling & Design Status
Cold Mass
  CM-02 – CA-02 at test stand (IB1)- See R. Rahbel talk
  CM-03
    UT vendor – PAUT completed (11-June-2024) passed
    Capillary Work – IFS wiring hypot complete, wires dried and tube installation complete
    Post IFS capillary bending/ electrical testing complete
    Weld inspection – waiting for borescope delivery (on site) to complete internal weld insp.
    CLIQ/Kmod capillary tube after inspection
    Cold Mass Nozzle length measurement complete – determining ext lengths for machining
    Cryo piping saddles fit up and ready for welding
    Beam tube ring – heat sink fixture machining in process
  CM-04 (MQXFA-08b & MQXFA-14b)
    Buss/Loop installed & movement confirmed - bus lock length to be milled
    Magnet alignment: SSW verified – Metrology Survey complete and matches
    Back up strip fit-up & welding complete.
    Lower Shell fit up/tacked & rolled - 2nd Shell Fit up/tacking in process today
    Pi-tape & install weld gap measurement pins – prepare for Metrology Survey (pre-weld)
  CM-05 Alignment Station set up (MQXFA07b & 15)
    SSW complete & metrology survey expected this week
    Bus Installation and expansion loop next
    Shells pressure washed and inspected – starting shim layout next

## Slide 5: Cold Mass Tooling & Design Status
Cold Mass (cont)
  Production Series
    Final 2 items for procurement:
      Tack Blocks – in QCR reviewed and dispositioned – Reviewed rework of first few and passed. Vendor will proceed to repair the balance including second batch returned
      Lower Saddles, cold mass – reviewing QCRs
      Production N-lines - leak test 100% complete
      Formed Plates in stock at FNAL for CM-07, -08, -09 and -10 (ready for machining)
      CM-05 – CM-10 & Spare Tack blocks – received and in stock
      CM-06 thru CM-10 & Spare Shell Plate Machining PO (REQ #355609)
        CM-06 shells at machining vendor expected completion - July 24th
        New Shell pair Drop off and machined pair shell pick up planned for July 29th.
      Shell Plate Forming: CM-10 Picked up & back in storage
        Next 4 plates for forming due August 1st (need plates from CERN)
      CM-05 – CM-10 & Spare Saddle –
        received 1 pc for inspection last week (first article). QC inspection complete & need to review
        Added thread check on all parts (100%)
    Magnet 16
      In temp storage (ICB)
    Q1-Q3 Bus production
      Units up to CM-10 plus 1 spare are complete
      1 Spare Buss – waiting for housing parts