## RAW input from survey
|  |  |  | Period 1 |  | Period 2 |  |  | Period 3
Main Activity Areas | Institute(s) | Current Effort from community | Ask | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | Total
Algorithms & Software
Frameworks: Period 1: contribute to existing framework key4hep with general expertise Period 2: establish accelerators (GPUs) in framework Period 3: modernize the framework for the 2040s, if needed change programming model and language | FNAL |  |  | 0.1 FTE scientist and 0.5 FTE computing professional | 0.1 FTE scientist and 0.5 FTE computing professional | 0.5 FTE scientist and 1 FTE computing professional | 0.5 FTE scientist and 1 FTE computing professional | 0.5 FTE scientist and 1 FTE computing professional | 0.5 FTE scientist and 2 FTE computing professional | 0.5 FTE scientist and 2 FTE computing professional | 0.5 FTE scientist and 2 FTE computing professional | 0.5 FTE scientist and 2 FTE computing professional | 0.5 FTE scientist and 2 FTE computing professional
Simulation Software: Period 1: support Geant4 for feasibility studies Period 2: move to GPU-base simulation Period 3: R&D for the future of simulation | FNAL |  |  | 0.5 FTE computing professional | 0.5 FTE computing professional | 1 FTE computing professional | 1 FTE computing professional | 1 FTE computing professional | 1 FTE computing professional | 1 FTE computing professional | 1 FTE computing professional | 1 FTE computing professional | 1 FTE computing professional
Infrastructure
Active Archive Facility: Period 1: support studies with disk and tape storage Period 2: enlarge the support to provide access to more storage Period 3: R&D for the future of data management for the 2040s | FNAL |  |  | 0.25 FTE computing professional | 0.25 FTE computing professional | 0.5 FTE computing professional | 0.5 FTE computing professional | 0.5 FTE computing professional | 1 FTE computing professional | 1 FTE computing professional | 1 FTE computing professional | 1 FTE computing professional | 1 FTE computing professional
HEPCloud: Period 1: provide access to HTC and HPC sites Period 2: add accelerator access for production workflows Period 3: evolve the access to latest HTC and HPC resources | FNAL |  |  | 0.25 FTE computing professional | 0.25 FTE computing professional | 0.5 FTE computing professional | 0.5 FTE computing professional | 0.5 FTE computing professional | 1 FTE computing professional | 1 FTE computing professional | 1 FTE computing professional | 1 FTE computing professional | 1 FTE computing professional
Elastic Analysis Facility: Period 1: support FCC community on shared infrastructure and columnar analysis tools Period 2: add support access to specialized hardware for analysis Period 3: evolve analysis paradigm for the 2040s an continue community support | FNAL |  |  | 0.25 FTE computing professional and 0.1 FTE scientist | 0.25 FTE computing professional and 0.1 FTE scientist | 0.5 FTE computing professional and 0.25 FTE scientist | 0.5 FTE computing professional and 0.25 FTE scientist | 0.5 FTE computing professional and 0.25 FTE scientist | 0.5 FTE Scientist and 0.5 FTE computing professional | 0.5 FTE Scientist and 0.5 FTE computing professional | 0.5 FTE Scientist and 0.5 FTE computing professional | 0.5 FTE Scientist and 0.5 FTE computing professional | 0.5 FTE Scientist and 0.5 FTE computing professional
AI/ML
Efficient algorithm training and design and coprocessor acceleration; integration into experimental workflows - Period 1: adapt common popular algorithm for FCC use-cases - Period 2: integrate into FCC software workflows and test | FNAL |  |  | Period 1 FY24: 0.1 FTE Scientist, 0.5 FTE Postdoc, 0.25 FTE computing professional; Period 1 FY25: 0.1 FTE Scientist, 0.5 FTE Postdoc, 0.25 FTE computing professional; Period 2 FY26: 0.1 FTE Scientist, 0.5 FTE Postdoc, 0.25 FTE computing professional; Period 2 FY27: 0.1 FTE Scientist, 0.5 FTE Postdoc, 0.25 FTE computing professional; Period 2 FY28: 0.1 FTE Scientist, 0.5 FTE Postdoc, 0.25 FTE computing professional
Generative models and fast simulation to accelerate particle and detector level simulations - Period 1: develop training samples, workflow, performance metrics and define baseline models - Period 2: Explore novel algorithms and compare different approaches | FNAL |  |  | Period 1 FY24: 0.1 FTE Scientist, 0.5 FTE Postdoc; Period 1 FY25: 0.1 FTE Scientist, 0.5 FTE Postdoc; Period 2 FY26: 0.1 FTE Scientist, 0.5 FTE Postdoc; Period 2 FY27: 0.1 FTE Scientist, 0.5 FTE Postdoc; Period 2 FY28: 0.1 FTE Scientist, 0.5 FTE Postdoc
High precision and high performance reconstruction with physics-inspired models (include graph NNs for clustering) - Period 1: develop training samples, workflow, performance metrics and define baseline models - Period 2: Explore novel algorithms and compare different approaches | FNAL |  |  | Period 1 FY24: 0.1 FTE Scientist, 0.5 FTE Postdoc; Period 1 FY25: 0.1 FTE Scientist, 0.5 FTE Postdoc; Period 2 FY26: 0.1 FTE Scientist, 0.5 FTE Postdoc; Period 2 FY27: 0.1 FTE Scientist, 0.5 FTE Postdoc; Period 2 FY28: 0.1 FTE Scientist, 0.5 FTE Postdoc
|  |  | Postdocs | Period 1 FY24: 7
|  |  | Scientists | Period 1 FY24: 1.1
|  |  | Staff | Period 1 FY24: 5.5

## FCC survey Effort plan
|  |  | Period 1 |  | Period 2 |  |  | Period 3
Main Activity Areas | Institute(s) | Job Category | FY24 [FTE] | FY25 [FTE] | FY26 [FTE] | FY27 [FTE] | FY28 [FTE] | FY29 [FTE] | FY30 [FTE] | FY31 [FTE] | FY32 [FTE] | FY33 [FTE]
Algorithms & Software
Framework (I/O, storage and metadata, basic): Period 1: contribute to key4hep Period 2: Establish accelerators Period 3: modernize framework for the 2040s | ANL, FNAL | Scientist / Faculty | 0.1 | 0.1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Engineer / Technician | 0.5 | 0.5 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2
|  | Postdoc / Student | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Event generator support | ANL | Scientist / Faculty | 0.1 | 0.1 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Engineer / Technician | 0.1 | 0.1 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Postdoc / Student | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Simulation (Fast, Geant, Celeritas): Period 1: support Geant4 for feasibility studies and complete exploration of GPU-enabled detector simulation Perido 2: transition to new production quality GPU simulation Period 3: R&D for the future of simulation | LBNL, FNAL, ORNL, ANL | Scientist / Faculty | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
|  | Engineer / Technician | 1.5 | 1.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | Postdoc / Student | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Reconstruction software and MC production operations support Period 1: release integration and management Period 2: release integration and management Perido 3: release integration and management | MIT | Scientist / Faculty | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
|  | Engineer / Technician | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Postdoc / Student | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
Total |  | Scientist / Faculty | 0.6 | 0.6 | 1.15 | 1.15 | 1.15 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4
|  | Engineer / Technician | 2.6 | 2.6 | 3.75 | 3.75 | 3.75 | 5 | 5 | 5 | 5 | 5
|  | Postdoc / Student | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4
Infrastructure
HTC and HPC resource provisioning and management: Period 1: provide access to HTC and HPC sites Period 2: add accelerator access for production workflows Period 3: evolve the access to latest HTC and HPC resources | ANL, FNAL | Scientist / Faculty | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
|  | Engineer / Technician | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1
|  | Postdoc / Student | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Storage resources and management: Period 1: support studies with disk and tape storage Period 2: enlarge the support to provide access to more storage Period 3: R&D for the future of data management for the 2040s: XRootD, Distributed Computing, Content Delivery Networks, Software Defined Networking, effective use of multi-Tb high speed networks for data transfer, Remote Directory Memory Access | SLAC, FNAL | Scientist / Faculty | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
|  | Engineer / Technician | 0.75 | 0.75 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
|  | Postdoc / Student | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
Analysis Facilty: Period 1: support FCC community on shared infrastructure and columnar analysis tools Period 2: add support access to specialized hardware for analysis Period 3: evolve analysis paradigm for the 2040s an continue community support | MIT, FNAL | Scientist / Faculty | 0.1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Engineer / Technician | 0.5 | 0.5 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
|  | Postdoc / Student | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Total |  | Scientist / Faculty | 0.3 | 0.45 | 0.45 | 0.45 | 0.45 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85
|  | Engineer / Technician | 1.5 | 1.5 | 2.25 | 2.25 | 2.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25
|  | Postdoc / Student | 0.95 | 1.2 | 1.2 | 1.2 | 1.2 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
AI/ML
Efficient algorithm training and design and coprocessor acceleration; integration into experimental workflows - Period 1: adapt common popular algorithm for FCC use-cases - Period 2: integrate into FCC software workflows and test | FNAL | Scientist / Faculty | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
|  | Engineer / Technician | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
|  | Postdoc / Student | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
High precision and high performance reconstruction with physics-inspired models (include graph NNs for clustering, generalized GNN tracking) - Period 1: develop training samples, workflow, performance metrics and define baseline models - Period 2: Explore novel algorithms and compare different approaches | FNAL, LBNL, SLAC | Scientist / Faculty | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
|  | Engineer / Technician | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Postdoc / Student | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Generative models and fast simulation to accelerate particle and detector level simulations - Period 1: develop training samples, workflow, performance metrics and define baseline models - Period 2: Explore novel algorithms and compare different approaches | FNAL | Scientist / Faculty | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
|  | Engineer / Technician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Postdoc / Student | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
High precision and high performance reconstruction with physics-inspired models (include graph NNs for clustering) - Period 1: develop training samples, workflow, performance metrics and define baseline models - Period 2: Explore novel algorithms and compare different approaches | FNAL | Scientist / Faculty | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
|  | Engineer / Technician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Postdoc / Student | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
deployment of federated AI networks for analysis and production at experimental facilities integrated through training feedback loops at central facilities | ORNL | Scientist / Faculty | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
|  | Engineer / Technician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Postdoc / Student | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Total |  | Scientist / Faculty | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65
|  | Engineer / Technician | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25
|  | Postdoc / Student | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Total Total |  | Scientist / Faculty | 1.55 | 1.7 | 2.25 | 2.25 | 2.25 | 2.9 | 2.9 | 2.9 | 2.9 | 2.9
|  | Engineer / Technician | 5.35 | 5.35 | 7.25 | 7.25 | 7.25 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5
|  | Postdoc / Student | 7.35 | 7.6 | 7.6 | 7.6 | 7.6 | 7.7 | 7.7 | 7.7 | 7.7 | 7.7
Total Total Total |  |  | 14.25 | 14.65 | 17.1 | 17.1 | 17.1 | 20.1 | 20.1 | 20.1 | 20.1 | 20.1

## FCC survey Effort plan (new for
R&D Topic | Priority | FTE Type | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | Institutes
|  |  | Pre-approval of the collider stage |  |  |  | Post-Approval/Pre-CD-0 |  |  | Post CD-0 Stage
Algorithms & Software
Framework (I/O, storage and metadata, basic): Period 1: contribute to key4hep Period 2: Establish accelerators Period 3: modernize framework for the 2040s |  | Scientific | 0.1 | 0.1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | ANL, FNAL
|  | Technical Lab | 0.5 | 0.5 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Event generator support |  | Scientific | 0.1 | 0.1 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | ANL
|  | Technical Lab | 0.1 | 0.1 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Simulation (Fast, Geant, Celeritas): Period 1: support Geant4 for feasibility studies and complete exploration of GPU-enabled detector simulation Perido 2: transition to new production quality GPU simulation Period 3: R&D for the future of simulation |  | Scientific | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | LBNL, FNAL, ORNL, ANL
|  | Technical Lab | 1.5 | 1.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reconstruction software and MC production operations support Period 1: release integration and management Period 2: release integration and management Perido 3: release integration and management |  | Scientific | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | MIT
|  | Technical Lab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Technical Univ | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Total |  | Scientific | 3 | 3 | 3.55 | 3.55 | 3.55 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8
|  | Technical Lab | 2.1 | 2.1 | 3.25 | 3.25 | 3.25 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5
|  | Technical Univ | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Infrastructure
HTC and HPC resource provisioning and management: Period 1: provide access to HTC and HPC sites Period 2: add accelerator access for production workflows Period 3: evolve the access to latest HTC and HPC resources |  | Scientific | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | ANL, FNAL
|  | Technical Lab | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Storage resources and management: Period 1: support studies with disk and tape storage Period 2: enlarge the support to provide access to more storage Period 3: R&D for the future of data management for the 2040s: XRootD, Distributed Computing, Content Delivery Networks, Software Defined Networking, effective use of multi-Tb high speed networks for data transfer, Remote Directory Memory Access |  | Scientific | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | SLAC, FNAL
|  | Technical Lab | 0.75 | 0.75 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Analysis Facilty: Period 1: support FCC community on shared infrastructure and columnar analysis tools Period 2: add support access to specialized hardware for analysis Period 3: evolve analysis paradigm for the 2040s an continue community support |  | Scientific | 0.35 | 0.75 | 0.75 | 0.75 | 0.75 | 1 | 1 | 1 | 1 | 1 | MIT, FNAL
|  | Technical Lab | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Technical Univ | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Total |  | Scientific | 1.25 | 1.65 | 1.65 | 1.65 | 1.65 | 2.15 | 2.15 | 2.15 | 2.15 | 2.15
|  | Technical Lab | 1.25 | 1.25 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3
|  | Technical Univ | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
AI/ML
Efficient algorithm training and design and coprocessor acceleration; integration into experimental workflows - Period 1: adapt common popular algorithm for FCC use-cases - Period 2: integrate into FCC software workflows and test |  | Scientific | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | FNAL
|  | Technical Lab | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
High precision and high performance reconstruction with physics-inspired models (include graph NNs for clustering, generalized GNN tracking) - Period 1: develop training samples, workflow, performance metrics and define baseline models - Period 2: Explore novel algorithms and compare different approaches |  | Scientific | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | FNAL, LBNL, SLAC
Technical Lab | bar: FY24 to FY33
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Generative models and fast simulation to accelerate particle and detector level simulations - Period 1: develop training samples, workflow, performance metrics and define baseline models - Period 2: Explore novel algorithms and compare different approaches |  | Scientific | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | FNAL
|  | Technical Lab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
High precision and high performance reconstruction with physics-inspired models (include graph NNs for clustering) - Period 1: develop training samples, workflow, performance metrics and define baseline models - Period 2: Explore novel algorithms and compare different approaches |  | Scientific | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | FNAL
|  | Technical Lab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
deployment of federated AI networks for analysis and production at experimental facilities integrated through training feedback loops at central facilities |  | Scientific | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | ORNL
|  | Technical Lab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | Scientific | 4.65 | 4.65 | 4.65 | 4.65 | 4.65 | 4.65 | 4.65 | 4.65 | 4.65 | 4.65
|  | Technical Lab | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Total |  | Scientific | 8.9 | 9.3 | 9.85 | 9.85 | 9.85 | 10.6 | 10.6 | 10.6 | 10.6 | 10.6
|  | Technical Lab | 4.6 | 4.6 | 6.5 | 6.5 | 6.5 | 8.75 | 8.75 | 8.75 | 8.75 | 8.75
|  | Technical Univ | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
Total Total Total |  |  | 14.25 | 14.65 | 17.1 | 17.1 | 17.1 | 20.1 | 20.1 | 20.1 | 20.1 | 20.1

## FTE Template
R&D Topic | Priority | FTE Type | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | Institutes
|  |  | Pre-approval of the collider stage |  |  |  | Post-Approval/Pre-CD-0 |  |  | Post CD-0 Stage
Core Software
Support and Evolution of core software framework | 1 | Scientific | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | ANL, FNAL
|  | Technical Lab | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 2 | 2 | 2
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maintenance and Evolution of Community Simulation Software | 1 | Scientific | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 2 | 2 | 2 | LBNL, FNAL, ORNL, ANL
|  | Technical Lab | 1 | 1 | 1.5 | 1.5 | 2 | 2 | 2 | 2 | 2 | 2
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | Scientific | 1.25 | 1.25 | 1.25 | 1.25 | 2 | 2 | 2 | 2.5 | 2.5 | 2.5
|  | Technical Lab | 1.5 | 1.5 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure
Evolution and Operation of Resource Provisioning and Workflow Management | 2 | Scientific | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.75 | 0.75 | 0.75 | ANL, FNAL, <university>
|  | Technical Lab | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1
|  | Technical Univ | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1
Evolution and Operation of Storage Management | 2 | Scientific | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.75 | 0.75 | 0.75 | SLAC, FNAL, <university>
|  | Technical Lab | 0.25 | 0.25 | 0.5 | 0.5 | 0.75 | 0.75 | 0.75 | 1 | 1 | 1
|  | Technical Univ | 0.25 | 0.25 | 0.5 | 0.5 | 0.75 | 0.75 | 0.75 | 1 | 1 | 1
Evolution and Operation of Analysis Infrastructure | 1 | Scientific | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | MIT, FNAL
|  | Technical Lab | 0.25 | 0.25 | 0.5 | 0.5 | 0.75 | 0.75 | 0.75 | 1 | 1 | 1
|  | Technical Univ | 0.25 | 0.25 | 0.5 | 0.5 | 0.75 | 0.75 | 0.75 | 1 | 1 | 1
Integration, Deployment and Operation of Large Scale AI/ML Training Workflows | 3 | Scientific | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | ORNL, <university>
|  | Technical Lab | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.75 | 0.75 | 0.75
|  | Technical Univ | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.75 | 0.75 | 0.75
Total |  | Scientific | 1 | 1 | 1.25 | 1.25 | 1.75 | 1.75 | 1.75 | 3 | 3 | 3
|  | Technical Lab | 1 | 1 | 1.5 | 1.5 | 2.5 | 2.5 | 2.5 | 3.75 | 3.75 | 3.75
|  | Technical Univ | 1 | 1 | 1.5 | 1.5 | 2.5 | 2.5 | 2.5 | 3.75 | 3.75 | 3.75
Physics Software including AI&ML
Optimization and Evolution of Physics Generators | 2 | Scientific | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | ANL, <university>
|  | Technical Lab | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Technical Univ | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Support Detector R\&D domain experts to implement reconstruction algorithms | 1 | Scientific | 0.75 | 0.75 | 0.75 | 0.75 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | FNAL, <university>
|  | Technical Lab | 0.75 | 0.75 | 1 | 1 | 1.5 | 1.5 | 1.5 | 2.5 | 2.5 | 2.5
|  | Technical Univ | 0.75 | 0.75 | 1 | 1 | 1.5 | 1.5 | 1.5 | 2.5 | 2.5 | 2.5
Generative models and fast simulation to accelerate particle and detector level simulations | 3 | Scientific | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | FNAL, <university>
|  | Technical Lab | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.75 | 0.75 | 0.75
|  | Technical Univ | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.75 | 0.75 | 0.75
Reconstruction and Monte Carlo Software Release Operations Support | 2 | Scientific | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | MIT
|  | Technical Lab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Technical Univ | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Total |  | Scientific | 1.5 | 1.5 | 1.5 | 1.5 | 2.5 | 2.5 | 2.5 | 3 | 3 | 3
|  | Technical Lab | 1.25 | 1.25 | 1.5 | 1.5 | 2.5 | 2.5 | 2.5 | 3.75 | 3.75 | 3.75
|  | Technical Univ | 1.5 | 1.5 | 1.75 | 1.75 | 3 | 3 | 3 | 4.25 | 4.25 | 4.25
S&C Coordination
International S&C Coordination | 2 | Scientific | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Technical Lab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Coordination of U.S. S&C Activities | 2 | Scientific | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Technical Lab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | Scientific | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1
|  | Technical Lab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Support
User support of US R&D groups | 3 | Scientific | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Technical Lab | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | Scientific | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Technical Lab | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1
|  | Technical Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Total |  | Scientific | 4.25 | 4.25 | 4.5 | 4.5 | 7.25 | 7.25 | 7.25 | 9.5 | 9.5 | 9.5
|  | Technical Lab | 4.25 | 4.25 | 5.5 | 5.5 | 8.5 | 8.5 | 8.5 | 12.5 | 12.5 | 12.5
|  | Technical Univ | 2.5 | 2.5 | 3.25 | 3.25 | 5.5 | 5.5 | 5.5 | 8 | 8 | 8
Total Total Total |  |  | 11 | 11 | 13.25 | 13.25 | 21.25 | 21.25 | 21.25 | 30 | 30 | 30
M&S |  | k$ | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375 | 375