## Slide 1
2024 Summer Shutdown
7/12/24

## Slide 2: Enclosures
RSO group will be surveying enclosures starting Sunday July 14th.
Areas will remain secured until RWP and Maps have been posted in the MCR.
Long term keys will be issued for Main Injector, Booster, Numi, and Muon Campus once the areas are surveyed and released as Supervised Access.

## Slide 3: Power Outages
  Week of (July 15th - July 19th )
    Monday July 15th
      Feeder 82/85 Pulse Power, MI60
      Spans: 08:20-16:00 hrs
    Tuesday July 16th
      MI40 Conventional Power, and FDR62 (MI40 pulse power)
      Spans 08:20 - 16:00 hrs
    Wednesday July 17th
      Muon Campus Feeder 24, Mu2e area, AP0, AP10, AP30, AP50, F27, MC1, MC2
      Spans 08:20 - 16:00 hrs
    Thursday July 18th
      Feeder 46A, A0 Cryo
      Spans: 08:20 - 12:00 hrs.
See power outage schedule at :
www-bd.fnal.gov/ops/calendar/

## Slide 4: Linac
Beam studies will end on Sunday July 21rd
  Turn off RF stations
  Configuration control and LOTO
  Opening RSO survey Monday 0900 July 22nd
  Supervised access mode Tuesday July 23th

## Slide 5: Booster 7/15-7/19
RSO will survey Booster on Sunday 7/14 and hopefully will be able to get Supervised Access wipe results by Monday 7/15. Once the area is Supervised we will request a recore of the area and issue keys.
Start of Major Job
  Booster Collimator installation. The drop area in the Cross Gallery high bay will be limited at times due to truck traffic and crane operations.

## Slide 6: MI/RR/MI8 7/15-7/19
  MI/RR Ring
  Hope to have the area available for Supervised Access and recore by Wednesday afternoon 7/17. If not we will recore on Thursday 7/18.
  LCW turn off 7/19.
  Dual PA cable pulls will begin 7/17.
  Tunnel tours
    Mechanical assessment
      Water/Vacuum issues
  MI-8
  Supervised Access by Monday afternoon 7/15. Recore after RWP is available.
  Stage equipment as found surveys of components. Be aware in the MI 8 area for crane operations.
Fire Protection System
Will be performing PM’s on Tuesday morning 7/16. Please have at least 1 golf cart available.

## Slide 7: NuMI – TSD 7/15-7/19
  Hope to have the area available for Supervised Access and recore by Wednesday afternoon 7/17. If not we will recore on Thursday 7/18.
  Tuesday 7/16 Fire protection will be performing PM’s in the afternoon.
  Switch over to local cooling on or before 7/18 due to LCW turn off on 7/19.
  Inspections of the area preparing for work next week.

## Slide 8: External Beam Delivery Department
Muon Campus/Switchyard
- RSO surveys of Muon Campus, SY and Transfer hall on 7/16.
- RSO surveys of Meson on 7/17.
- The goal is to have all enclosures in Supervised Access by the end of the week.

## Slide 9: 9 am meetings
- Moving to the traditional Tuesday/ Friday schedule starting next week 7/16.
- Huddle for Tuesday and 1 West for Fridays.
- I will be looking at a time to meet with the machine shutdown coordinators.
Any Questions??