## Slide 1
FAST / IOTA Shutdown 2023-2024
Enclosure STATUS: ODH-0 & Supervised Access (“same as it ever was”)
General: -IOTA Bake GFCI (AD/Web 57570). No movement
-ESB Laser Lab electrical Req “in progress”
ES&H: -OSC Mode in LL. New South Gate. Interlock Test.
IPI: -ESB 480/120VAC Electric Req being generated.
  -DON’T TOUCH beamline stuff.
  -Exciting IPI updates to follow (Chip)
Water: -Chiller needs repair. Waiting on PO. (Req 360865)
-Reminder” Fluids Engineer for us is Mike Hanson
AD Shutdown’24: Power outages: NML=none, MSS=postponed
— Contact FAST RunCo with any work or access requests —

## Slide 2: ISD Updates for NML
E-Lights – In Progress (166735 being re-Scheduled)
Carpeting – Carpet Tile Loose – In Progress (181604 looking into attic stock, assigned to Emil) still looking – need to follow up. May be some in the control room closet
South Stair Lighting – (182156) Complete ✅
Roll Up Door - In Progress (168986) assigned to the Schedule Planner.
Clean Y-Strainer – Hold (181072) due to Abatement – the project is not going well for the mechanic, not able to get the old bolt out, calling in a contractor possibly.
Loading dock weight capacity – Approved for Arial Lift use. FPC is aware of the progress. In Progress – Amy is working the back side for ComEd Credits. So hopefully this will get it moving. Related to High Bay Lighting LED Upgrade (163677).

## Slide 3: ISD Updates for NML (cont.)
Data Center Carpet Tile – Will Be getting a one from Rich White shortly to replace the one with the hole in it.
Electrical Receptacle Changeouts – In Progress (189398) Placed WO and NML taped near the outlets.
ESB Lights Out – In Progress (189694)
ESB – waiting on NPT to start. In Progress – I’m told about 6 weeks for equipment then may be starting. “We have received and reviewed the unit submittal for this project, and it has been requested that the PO date be pushed back to 01/27/2025 as it was coming close to expiring. The reason for this pushback is the 6-8 week lead time on the units.” - Noah
Strips on driveway – R & G needs a task code. In Progress
HVAC in control room – this has been passed to Tim Burger to look at.

## Slide 4: ISD Updates for NML (cont.)
Cleanup in mech rooms – Working with JP & his team to tag items to keep. Anything else ISD will get Clorica to clean up. In Progress (still some stuff)
Tire Marks from lift – Electrical group to pay for this? In Progress
Other outside work – Cleanout the front forest under the grates. DONE
Mechanical Checks on critical water connections – In Progress
Ejector Pit piping system tightening work – In Progress. I believe this is done.
Window Cleaning - In Discussion. FY2025
Exterior Lights (both inground and canopy) - waiting on quote. On Hold

## Slide 5
FAST shutdown continues through fall for the installation of the IOTA Proton Injector. Thanks to support groups helping us
  (PESD, HLRF, Instrumentation, MSD, ISD, etc...)
IPI source conditioned up to 51kV
  We continue conditioning and are up to 12mA of 50kV Protons
IPI electrical work waiting on subcontractor schedule
LCW chiller repair waiting on PO (Req 360865)
ISD responding promptly to our requests. THANKS!
Had an impromptu DOE/SC visit. It turned out very well
Thanks to OPS for being vigilant on ACNET alarms
— Contact FAST RunCo with any work or access requests —
FAST / IOTA 9:00 Report