## Slide 1
Tony Busch
2024 Summer Shutdown Planning
7/19/24

## Slide 2: Long term shutdown keys
Areas on long term keys
  Booster
  MI
    MI-8 line
    MI10
    MI20-62
  Muon Campus
    Delivery Ring
    Extraction
    M4/5 line
  NuMI
    Pre-Target
    Target Hall
  Long term keys will only be issued from approved list.

## Slide 3: Power Outages upcoming week
  (July 22nd – July 26 th )
    Wednesday July 24th
      MI60 Conventional Power
      MI60 Pulse Power (Feeder 71)
        Spans: 08:20 - 16:00 hrs.
    Thursday July 25th
      Feeder 40, X-Gallery, L4, L5, All Linac, MCR, Computer Room, BSTR Portakamps
        X-Gallery, L4, L5, All Linac, MCR, Computer Room, BSTR Portakamps, DSTR-A04, A05, DSTR-CG, Feeder 40
          Spans: 07:00 - 16:00 hrs.
    Friday, July 26th
      Feeder 42 –CUB
      Spans: 07:00-16:00 hrs
We are currently looking at moving to weekend and will know more by Tuesday.

## Slide 4: Power Outage Detail Plan
Thursday July 25th
AD Computer Room, networks, computers turned off: 0500 (no controls)
Feeder 40 off for PM, X-Gallery, MCR, Linac, Computer Room: 0700-1600
Friday July 26th
Feeder 42 off for PM, CUB power goes down: 0700-1600
CUB, no cooling, remains down for PM: 0700-1600
CUB cooling slowly resumes ~1700
Notes:
If there are any problems encountered with any of the PMs, expect delays.
MCR and Mac room require portable cooling and a generator for the duration of the power outage.

## Slide 5: Linac 7/22-7/26
Studies will complete this evening, possibly tomorrow.
  Once studies are complete we will perform Config control and LOTO.
  Monday 7/22 RSO surveys.
  Tuesday Supervised Access.
RF Maintenance
Water System Maintenance
  Grease Motor
  Change filter
  Back wash sand filter
  Change oxy Soak and Algae cartridge.
  Change DI bottle

## Slide 6: Booster 7/22-7/26
  Begin moving collimator stands and steel into the cross gallery high bay area.
    Be alert for possible rerouting of pedestrian area walkways.
    Truck traffic behind the cross gallery.
  Once steel workers are on site will begin moving collimator stands into place in the tunnel.
  General Maintenance
    Work on chokes.
    Gallery and Tunnel.

## Slide 7: MI/RR/MI8 7/22-7/26
  218 sump excavation
  Tunnel
    Work on water leaks and hoses.
  MI-8
    Stage equipment
    Begin moving steel for collimators
    Install baseplates and survey
  Ring
    Cable pulls for dual PA upgrades.
    Heat exchanger cleaning starting at MI 62.
    Ring LCW shutdown today.
ISD Maintenance (MI8 & ring)
  Lighting
  MI 40 power panel

## Slide 8: NuMI – TSD 7/22-7/26
  Target Hall
    Opening of rollup door/ shield wall.
    Crane installation.
    Track and train car installation.
    Install scaffolding.
    Work on stack of 5.

## Slide 9: External Beam Delivery Department
Muon Campus
  Preparing for upcoming work and planning.
Switchyard
  Vacuum Maintenance.
  Water leak repairs and inspections.
  Waiting on shipment of magnet for replacement.

## Slide 10: Thank you..
Not all inclusive:
  Operations and PESD for all of the LOTO and Config controls.
  Interlocks for all of their help in re-coring.
  RSO for all of the surveys performed over the past week.
  Everyone that has come into my office or talked to me in the hall and provided me with information to keep the shutdown moving forward.