## Slide 1
Tony Busch
2024 Summer Shutdown Planning
7/26/24

## Slide 2: Weekend power outages
Saturday, July 27 AD Computer Room, networks, computers turned off: 0500 (no controls) CUB turning off cooling: 0630 Feeder 42 off for PM, CUB power goes down: 0700-1600 No cooling all day for electrical PM transitioning to mechanical PM on Sunday Sunday, July 28 CUB, no cooling, remains down for mechanical PM: 0700-1600 Feeder 40 off for PM, X-Gallery, MCR, Linac, Computer Room: 0700-1600 CUB cooling slowly resumes ~1700 Notes: If there are any problems encountered with any of the PMs, expect delays. MCR and Mac room require portable cooling and a generator on Sunday for the duration of the power outage. FYI: Feeder 42 - CUB, DSTR-A01, All CUB Feeder 40, X-Gallery, L4, L5, All Linac, MCR, Computer Room, Booster Porta-kamps

## Slide 3: Power Outages upcoming week
  (July 29 th – August 2 nd )
    Monday July 29th
      MI50 Conventional Power, and FDR63 (MI50 pulse power)
      Spans: 08:20 - 16:00 hrs.
    Tuesday July 30th
      Booster Feeder 41, Booster East & West (Galleries & Towers), MTA
      Spans: 08:20 - 16:00 hrs.
    Wednesday July 31st
      1/2 Meson Cryo (Day 1 of 2), LLRW Site 40, Feeder 31
      Spans: 08:20 - 16:00 hrs.
    Thursday August 1st
      - 1/2 Meson Cryo,(Day 2 of 2) Meson West, MS4, M04, Feeder 30
      - Spans: 08:20 - 16:00 hrs.

## Slide 4: Linac 7/29-8/2
Source B cesium boiler fill
Klystron LOTO test point installation continues
LE maintenance
Klystron maintenance
Water System Maintenance
  Grease Motor
  Change filter
  Back wash sand filter
  Change oxy Soak and Algae cartridge.
  Change DI bottle

## Slide 5: Booster 7/22-7/26
  Steel workers and technicians will begin moving collimator stands into place in the tunnel.
  General Maintenance
    Work on chokes.
    Gallery and Tunnel.
  ISD Maintenance
    Lighting/ Sumps
    Will possibly need escorts.

## Slide 6: MI/RR/MI8 7/29-8/2
  218 sump excavation continues
  Tunnel
    Work on water leaks and white hoses.
  MI-8
    Leveling plate grouting
    Moving steel for collimators
    Finish installing baseplates and survey
  Ring
    Dual PA upgrade work.
    Heat exchanger cleaning at MI 8 and 10.
ISD Maintenance (MI8 & ring)
  Lighting/ Sumps
  Will finish on Monday

## Slide 7: NuMI – TSD 7/22-7/26
  Pre target area.
    Multiwire 121 replacement
  Target Hall
    Work on stack of 5
    General maintenance

## Slide 8: External Beam Delivery Department
Muon Campus
  Preparing for upcoming work and planning.
Switchyard
  Water leak repairs and inspections.
  H202-5 removal once the magnet is available.