## Slide 1: 302.02.07 Structures Status
Magnet | Status | Notes
Pre-Series |  | 
MQXFA03 | Complete; report released | 
MQXFA04 | Complete; report released | 
MQXFA05 | Complete; report released | 
MQXFA06 | Complete; report released | 
MQXFA07b | Complete | 
Series |  | 
MQXFA08b | Complete; report released | No coil SG data with 2nd thermal cycle
MQXFA10 | Complete; report released | 
MQXFA11 | Complete; report released | 
MQXFA14b | Test complete | Fab & Test report drafts completed
MQXFA15 | Complete | At FNAL
MQXFA16 | Direct to FNAL10/13 | Fabrication Report drafts edited

## Slide 2: 302.02.07 Structures Status
Magnet | Status | Notes
Series |  | 
MQXFA09 | Disassembled | Two coils no longer available (in A14b, A15); Structures used in MQXFA11; will be renamed MQXFA24
MQXFA12b | Added tapered load shims; vendors for detailed ultrasonic inspection still being contacted | Work to be completed before MQXFA17 starts
MQXFA13b | Cold test started; SG data shown after this update | 
MQXFA17 | Arrived form BNL 7/20 | Could Coil 242 be candidate for replacement? (reviewed with magnet originally)
MQXFA18 | Preload completed, finishing operations, splice box | Tapered load shims installed
MQXFA19 | Will be on hold until A17 rework is completed | 

## Slide 3: 302.02.07 Structures Status 2
Series Magnets (cont.)
Updated Magnet specifications to allow for 120 MPa excursions, increased from 110 MPa
  MQXFA07b, MQXFA16, MQXFA15 reload did not require 120 MPa
  MQXFA17 reached 120 MPa during preload
  MQXFA13b coil 2 reached 126 Mpa in last excursion

## Slide 4: Coils in Storage at LBNL
Coil | Reviewed in Magnet | Notes | LE CMM | Nom. CMM | RE CMM
241 | A13b | (Was) Replacement coil for MQXFA13b (large) | ✓+ | ✓ | ✓+
158 | A12b | Small coil (was originally for MQXFA12b) | ✓* | ✓ | ✓*
242 | A17/13b | Spare (was for MQXFA17 and/or MQXFA13b) | ✓+ | ✓ | ✓
234 | 13b | On Hold. (Too small spare for MQXFA16) | ✓* | ✓ | ✓*
240 |  | Arrived from BNL 12/4; CMM complete | ✓ | ✓ | ✓
248 |  | Arrived from BNL 12/4; CMM complete | ✓ | ✓ | ✓
244 | A18 | Arrived from BNL 2/5/24 | ✓✓ | ✓ | ✓✓
161 | A18 | CMM Measurements on LE/RE 3x; repeatability meas. | ✓✓ | ✓ | ✓✓
251 |  | Arrived from BNL 4/1/24 | ✓✓ | ✓ | ✓✓
156 |  | FNAL Coil arrived 4/15 | ✓✓ | ✓ | ✓✓
245 |  | Arrived from BNL 7/20 |  |  | 
247 |  | Arrived from BNL 7/20 |  |  | 
✓✓ Averaged 3x extra measurements taken on ends
✓+ Measured 6+ additional profiles on LE and RE
✓* Measured 3+ additional profiles on LE and RE

## Slide 5: 302.02.07 Structures Status
Other topics
Technicians
  New techs are getting up to speed
Bladders:
  Working with CERN to source 60-100 bladders of their style for MQXFA lengths
    Planning upgrade for HP cart to accommodate additional circuits
Extra ARMCO is stored in Berkeley
Property Transfer from LBNL to FNAL
  MQXFA07b, MQXFA15 property documents processed
  Transfers to happen in “bulk”
MQXFA spare parts
  Shells, yokes orders placed; Shells forgings QC report accepted
  Bladders PO’s placed
  Magnetic Shims PO arrived last week
  Axial rods PO placed

## Slide 6: Additional slides