## Slide 1
Tony Busch
AD Shutdown Coordinator
Planning & Integration Department
Accelerator
Summer Shutdown

## Slide 2
Shutdown 2024 Timeline
Crew Marching orders
Determine Jobs
Plan phase 1: Define schedule
Execute Shutdown
Close out
Plan phase 2: Finalize Schedule
JAN
FEB
MAR
APR
MAY
JUN
JULY
AUG
SEP
OCT
NOV
DEC
Milestone 1
Define Shutdown Coordinators.
Milestone 2
ID Jobs to the 90% level.
Milestone 3
First pass resource level Schedule.
Milestone 4
Milestone 5
Milestone 6
Milestone 7
Second pass resource level Schedule.
Final resource level Schedule.
Start Shutdown.
Complete shutdown.
Milestone 9
Milestone 8
Complete
Startup.
Return HEP
Define Scope
Plan
Execute
HEP
Dec
Execute
Execute Shutdown
Possible Pause
Shutdown parameters
Original Duration: 10 weeks. Possible lab closure will extend shutdown ~3 extra weeks due to pause.
End of tunnel work/power outages if there is a pause
Week of Monday October 14th

## Slide 3: Shutdown Progress

## Slide 4: Power outage progress
Chart: 
| % Not Completed | % Complete | % Deferred/Rescheduled
 | 0.71345 | 0.25714 | 0.029412

## Slide 5: 8 Gev Collimator
2 Collimators
  825-826 and 827-828
Weight per collimator station: ~175,000 lbs. (88 tons)
Beam direction
Beamtube/ vacuum chamber
Vertical motion controls
Horizontal motion controls
Installation plans for this shutdown.
  Layout floor anchors
  Cable pulls
  Stack steel and align

## Slide 6: Booster Collimator
1 Collimator on 2 stands
Weight ~100,000 lbs.
Beam direction
Vertical motion controls
Installation plans for this shutdown.
  Install floor anchors
  Cable pulls
  Stack steel and align

## Slide 7: Other main jobs on the schedule
  Dual PA upgrades in Main Injector.
  Replacement of H202-5 and SWIC in Switchyard.
  Q 205 Swap and installation of ESS1&2 at Muon Campus.
  Up to 8 Choke repairs in Booster.
  Sump discharge repairs in Main Injector
  Cleaning of all Main Injector heat
  exchangers.

## Slide 8: ISD Shutdown work
  Electrical
    Lighting repairs
      Tunnel relamping
      Service Building relamping
    Power panel inspections
      Tunnel and service buildings
    General Electrical repairs
    Power outage across site
  Mechanical
    Sump repairs/replacement
    Generator maintenance
    MI service building AC unit replacement

## Slide 9: Potential Impacts to Our Shutdown Schedule
Electrical work (Electricians)
  What we need….
    ~10 Electricians to cover ALL of our jobs that have been requested for this summer shutdown.
  What we currently have
    ~3-4 Electricians
Materials on hand
  Still waiting on wire and other items to be delivered. (We need 18 rolls and have 5 rolls.)
Shipment of low level radioactive items
  Only have 1 driver on site that can haul radioactive materials. This affects magnet and other shipments for work.