## Slide 1
Pressing Issues / Special Topic:
  Linac Loft Area - is getting some reactive HVAC work done, affecting some parking.
  MI-65/NUMI – concern with the shield block target door as entered the project list.
Noteworthy Items:
  Monday the Linac Loft will be getting some power work done, currently looking at the power panel effected areas below for power interruptions and communications to mitigate concerns.
  R & G has been performing weed killing. We have been working on notifying the buildings effected when we find out.
Mechanical and Utility Outages: Slide #4 – See slide
Active Projects and Contractors Onsite: Slide #5 & #6
Safety Success – G2 has had some safety concerns addressed by R & G’s. Big thanks to them. G-2 had the sinkhole filled, berm stairwell opened up from growth, and Dracula’s tomb cleared out.
See next slide for photos.
Infrastructure Services Division Updates

## Slide 2
Special Topic:
G-2 – Facelift happening and coming. Safety addressed with sinkhole. Stairs to berms cleared, and Dracula’s Tomb cleared for use.
MI65NUMI – Shield door concerns – Safety Concerns
MI65 Weather Station – Currently contemplating locations best suited for the rooftop evaporator. In discussion/review currently
PIPII –
  Having AEDs installed and continues to have concrete poured. Safety Concern
SEA 2nd Floor Renovations Moving along - ACBM remediation scheduling and lighting plan being designed.
Office Remodeling - concerns are being worked through to find the best course of action moving forward. We value and appreciate the feedback from all.

## Slide 3
MI60, MI-8, MI-52 – Working on getting the falling “I’s” back on the buildings.
C-0 Floors – Abatement – The abatement teams are starting to be mobilized again and items are being scheduled – Waiting on
Discovery Road – Painting project for the buildings on discovery road is in the planning phase. Req/SOW turned and being reviewed.
  NS0 and G-2 – are being scheduled to get a fresh coat of paint.
Old/Unused Equipment – Working on Roof Cleanups and MMR’s for stuff around the buildings. Planning with departments on getting items not needed off the roof. In Process.
Service Agreement – Verifying AD/ISD equipment is moving along nicely at about 30% of roughly 8000-line items. In Progress
Noteworthy Items
🎉Another big KUDOS to the R & G’s Teams and the MMR Teams for working to cleanup our grounds and make travel safer. 🎉

## Slide 4
Mechanical and Utility Outages
Planned Power Outages
Current Outage Schedule is populated.
Shutdowns are being scheduled for May/June.

## Slide 5
Active Projects still in motion and Contractors on Site
AD Projects:
Door EOL Replacements – Requisition for 13 doors on the EOL list is in progress. Plus 4 others on a fast track working with Scott on locations like SWA, ME7, & AP0, MT Worm. No Change – Awaiting Approval
Office Refurbishing – TGC-113/SEA-212 Approved, XGE-106/TGC-109 Approved, XGC-129/XGW-114 Approved, XGE-124/TGS-125 Approved, WGW-106/XGW-108 Approved, XGW-107 Approved, Building Req’s now – no change
Exterior Ladder EOL replacements – Currently 24 ladders are targeted. SOW is being developed. In Progress – no change
New Roofs – HAB almost complete, Minos is prepping, Village Gym/Fuel Station are next up and just waiting on different phases of the projects to firm up dates.
Minos – Emergency Roof – In review process. In Progress
NS3 – Emergency Roof – In review process. In Progress

## Slide 6
Active Projects still in motion and Contractors on Site
AD Projects:
NTF Safety Project – Area scanned and ready to schedule the rail install.
Potential next Projects – APOTH Door & Frame Replacement (waiting on quote), A0 cleanroom sanitary line replacement (performed walkdown and waiting on quote), MI Building Concrete Coatings, C0 Service Building (in beginning phase). – No Change
Lighting Work/Upgrades – CMTF have been halted due to other lab priorities - Received new scheduling information from CMTF and working the FPCs to see if we can work into the schedule.
Foundation Leaks – MT6/MC2/Wilson Hall – In procurement.
And More…

## Slide 8
CUB – picked up new “Slip-Stream” filters
Warehouse 2 – ADA requirements have been installed, new parking spot, and automatic door openers
MW9 gas leaks – after the repairs and new install we are wrapping them with a protective coating to prevent soil condition deterioration.
LAB B – pulled down their old rooftop unit and replaced it with a new one.
PS6 – received some new drain work
Pond Algae Treatment – mechanics are/were cleaning intake grating a couple times a day.
Lab Wide Mentions

## Slide 9
Road Closures
Closures from Fermilab today or R&G site
  Lab closures
  Closures close to WH