## Slide 1
Tony Busch
AD Shutdown Coordinator
Planning & Integration Department
Accelerator
Summer Shutdown

## Slide 2
Shutdown 2024 Timeline
Crew Marching orders
Determine Jobs
Plan phase 1: Define schedule
Execute Shutdown
Close out
Plan phase 2: Finalize Schedule
JAN
FEB
MAR
APR
MAY
JUN
JULY
AUG
SEP
OCT
NOV
DEC
Milestone 1
Define Shutdown Coordinators.
Milestone 2
ID Jobs to the 90% level.
Milestone 3
First pass resource level Schedule.
Milestone 4
Milestone 5
Milestone 6
Milestone 7
Second pass resource level Schedule.
Final resource level Schedule.
Start Shutdown.
Complete shutdown.
Milestone 9
Milestone 8
Complete
Startup.
Return HEP
Define Scope
Plan
Execute
HEP
Dec
Execute
Execute Shutdown
Operation limitations
Shutdown parameters
Original Duration: 10 weeks. Operational limitation period will extend shutdown ~2 extra weeks due to pause.
End of tunnel work/power outages (last outage 10/10 in Main Injector.
Week of Monday October 7th

## Slide 3: Shutdown Progress
As of 8/1/24

## Slide 4: Power outage progress
Chart: 
| % Not Completed | % Complete | % Deferred/Rescheduled
 | 0.71345 | 0.25714 | 0.029412

## Slide 5: Power Outages upcoming week
  (Aug 5th – Aug 9th )
    Tuesday August 5 through 6th
    Feeder 96/97 pulsed power, MI8, MI14, MI40, MI52, MI60, MI62 all pulsed power
      Spans: 8/5 08:20 - 8/6 16:00 hrs.
    Thursday August 8th
      Feeder 44, Education Center, MBD, MINOS, NOvA, SBFDB, LaRTF, Swan Lake, MiniBooNE, ICARUS
      Spans 0800-1620
    Friday August 9th
      Linac, L1, L2, L3
      Spans: 08:20 - 16:00 hrs.

## Slide 6: Keep communications open
Over the next week we will be looking at any necessary adjustments to the schedules and work lists.
The collimator work and electrical work will continue during the operationally limited period.