## Slide 1
Main Injector Shutdown Status
Denton Morris
9 o’clock Meeting
August 9, 2024

## Slide 2
Tunnel Work
8/9/2024
MI Department Meeting | D. Morris
2
MI-8 Collimator installation
Base plates have been installed and grouted
Cable pulls in progress
RF Dual PA cavity upgrades (3 stations)
Electrical pulls are complete
Upgrade four modulators (one spare)
Fix Recycler Vertical IPM cables (completed)
Vacuum leak found on cable feed-through
Address found LCW leaks (underway with TD support)
323 Dipole will be addressed next week
MI-201 Sump discharge line replacement (stairwell/alcove only)
MI-218 Sump discharge line replacement (entire line).
Underway.
Vacuum issues in P150 line (~704) being investigated

## Slide 3
Upstairs Work
8/9/2024
MI Department Meeting | D. Morris
3
Main jobs:
MI-20 Upper transformer cable pulls
MI-20 Lower transformer cable pulls
Heat Exchanger cleaning: MI-62, MI-8 and
MI-10 are finished*
MI-20 in progress
Investigating pitting and corrosion
VCB PMs
Transformer/Switchgear PMs
PM all LCW pumps/motors
MI-218 excavation for sump line replacement

## Slide 4
Conventional Power Outages
8/9/2024
MI Department Meeting | D. Morris
4
Please report any additional MI outages to the MCR.