## Slide 1: Cryo Assembly, Cold Mass Status
A. Vouris
Cryo Assy L2 Meeting
August 12, 2024

## Slide 2: Cold Mass Tooling & Design Status
WorkStation Equipment
  Status
    End Can
      Lead End – Pallet jack cart drawings and note for 2nd unit
      Order additional pallet jack w/ extended forks
    Cold Mass drawings
      Working through redlines for next batch of drawing mods
        dwg for revisions: Magnet Model updated in all drawings
          F10103605 – Released/printed
          F10151260 – Released/printed
          F10178090 – Capillary tube install update – reviewed and redlined- updates needed to finish
          F10172809 – Pressure test drawing default updates from lower dwg
          Update Drawing tree - as needed after final revisions
          Fixture for Beam Tube – completed, released and in machining
    Additional tooling:
      Metrology: adjust/re-survey Welding Station – Rails adjusted and now w/in +/- .04

## Slide 3: Cold Mass Tooling & Design Status
Cold Mass
  Engr Analysis & Note:
    Traveler updates
  Cold Mass Welds
    Welding:
      Calibration plates RT’d complete (passed) – forwarded to J. Seyl

## Slide 4: Cold Mass Tooling & Design Status
Cold Mass
  CM-02 – CA-02 at test stand (IB1)- See R. Rahbel talk
  CM-03
    UT vendor – PAUT completed (11-June-2024) passed
    Weld inspection by CWI using borescope is complete (internal weld inspection)
    CLIQ/Kmod capillary tube welding complete
    Beam tube ring – heat sink fixture used and welding completed succesfully
    Cold Mass Nozzles machining welding in process: Beam tube ext complete, 3 of 4 HT-X complete. Purging started again for welding last HT-X and then Cold Mass IFS/CLIQ/Kmod ports
    Pressure test covers complete
  CM-04 (MQXFA-08b & MQXFA-14b)
    Buss/Loop installed & movement confirmed - bus lock length to be milled
    Magnet alignment: SSW verified – Metrology Survey complete and matches
    Back up strip fit-up & welding complete.
    Both Shells fit up/tacked & rolled in correct orientation.
    Pi-tape & install weld gap measurement pins – Metrology Survey (pre-weld) complete
    SSW in process – hold for results (Metrology survey – origins in process)
    Move to Weld station this week and prep for long welding

## Slide 5: Cold Mass Tooling & Design Status
Cold Mass (cont)
  CM-05 Alignment Station set up (MQXFA07b & 15)
    SSW complete - new metrology survey in process.
    Shell shim tacking in process – one complete second in process
  Production Series
    Final 2 items for procurement:
      Tack Blocks – in QCR reviewed and dispositioned – Reviewed rework of first few and passed. Vendor will proceed to repair the balance including second batch returned
      Lower Saddles, cold mass – reviewing QCRs
      Production N-lines - leak test 100% complete
      Formed Plates in stock at FNAL for CM-07, -08, -09 and -10 (ready for machining)
      CM-05 – CM-10 & Spare Tack blocks – received and in stock
      CM-06 thru CM-10 & Spare Shell Plate Machining PO (REQ #355609)
        CM-06 shells at machining vendor expected completion – pick up this week
        CM-06 shell pick up includes CM-07 Shell pair Drop off
      Shell Plate Forming: CM-10 Picked up & back in storage
        Next 4 plates for forming due August 1st (need plates from CERN) Checking status
      CM-05 – CM-10 & Spare Saddle – Reviewed and released for full order to be machined
        Added thread checks on all parts (100%)

## Slide 6: Cold Mass Tooling & Design Status
Cold Mass (cont)
  Production Series
    Magnet 16
      In temp storage (ICB)
    Q1-Q3 Bus production
      Units up to CM-10 plus 1 spare are complete
      1 Spare Buss – PO being processed, waiting for housing parts