## Slide 1: Cryostat Update
R. Rabehl
August 12, 2024

## Slide 2: Cryostat – Shipping Posts
Teamcenter Engineering Order Form ED0033225 submitted
  Remaining 2 sets of shipping posts/support plates/cover discs. (Req. 354738 / P.O. 712185)
    May 10, 2024 promised date
    All items received, in QC
    Chamfer on all 6 support plates to be corrected at Village Machine Shop after inspections in ICBA are completed.
  All bolting hardware for the remainder of the project. (Req. 357424)
    Placed on SAM.gov due to vendor error in indicating foreign-sourced material.
    A set of bolting hardware for CA-02 has been ordered (P.O. 714732). June 17 promised date. Delivered June 20, in QC.

## Slide 3: Cryostat – CA-02 FSI targets
In CERN’s operating experience, signal from FSI targets was lost when cold.
On IB1 Test Stand 4, viewing windows were installed at two FSI locations.
At both locations, the targets became cloudy once cold.
Warm (July 12, 2024)
Cold (July 31, 2024; vacuum 2.5 x 10-7 Torr)
FSI_IP_4
FSI_Center_3
Warm (July 12, 2024)
Cold (July 31, 2024; vacuum 2.5 x 10-7 Torr)

## Slide 4: Cryostating – CA-02
CA-02 DRs
  13503: Unidentified surfaced blemishes on LD pipe. Awaiting disposition.
  13526: Contact between IFS capillaries and thermal shield extrusions. Awaiting disposition verification.
  13527: FSI target installation screws not torqued to specified value to due lack of an appropriately-rated torque wrench. Awaiting disposition verification.
  13552: Thermal shield is ~5 mm too far towards the Non-IP end such that the thermal shield support pieces cannot be installed at the fixed support post. Awaiting disposition.
  13583: IFS-A RTD miswiring. Awaiting disposition.
  13584: Misalignment between new IFS-A cover and interface ring after welding. Awaiting disposition verification.
CA-02 NCRs
  Cold Mass saddle threads/support post installation (LHC-LQXFA-QN-0006) – WP Evaluation.
  Thermal shield misalignment (LHC-LQXFA-QN-0007) – Actions Underway.
  Central support post bearing bolts (LHC-LQXFA-QN-0008) – WP Evaluation.

## Slide 5: Cryostating – CA-03
Pressure test permits submitted to engineering note reviewers
  EN04771 (Cryo-Assembly piping)
  EN04901 (Pipe extensions welded onto Cryo-Assembly piping)