## Sheet1
Recommendation | Responsible Person | Status
LAB MANAGEMENT PERFORMANCE
FNAL Directorate must be diligent to ensure that the US HEP community sees FNAL as the major resource for all US HEP.
STRATEGIC PLANNING
Develop a straw man timeline that shows the different stages of LBNE, Project X and the time when new smaller experiments could fit into the program.
The straw man program should be flexible enough to respond to possible changes in the assumed HEP budget. (One might anticipate changes in both directions).
The lab would benefit from an in-depth cost review. The goal of the review will be a coherent picture of the tasks and resources going into the various elements of its long term planning document. Manpower management would be an important component of such a review. The lab’s workforce planning process should encompass the entire workforce, not just the projects as shown during the review, and it should be extended out to 2020.
Recommendation | Responsible Person | Status
ACCELERATOR OPERATIONS
The funding profile for the PIP should be reevaluated, particularly in FY13, and the impacts on the post shutdown experimental program should be determined.
GENERAL ACCELERATOR DEVELOPMENT
None
FUTURE ACCELERATORS / SRF
None
SCIENTIFIC COMPUTING
FNAL should continue to vigorously seek needed additional resources from US Universities to mitigate limitations and problems in software packages and their support.
The scientific computing division should present their current status and plans for developing and supporting simulation tools at a focused review after Snowmass. If there is no plan, they should develop one because adequate simulation tools are critical to the lab’s success in developing new intensity frontier initiatives. The plan should address the problem stated by several groups at this review – that simulations of several of the most important intensity frontier experiments at FNAL, including MicroBooNE and LBNE, are lagging other approaches to developing experimental designs and are, therefore, not actively contributing to the success of the program.
Recommendation | Responsible Person | Status
COLLIDER EXPERIMENTS - DZero & CDF
None
NOvA
FNAL must intervene as needed to prepare a realizable plan B if the problems with the APD/thermo-coolers compromise the NOvA’s schedule and cost.
MicroBooNE
FNAL should take steps to ensure that MicroBooNE has all reasonable and necessary support to maximize its probability of early success.
Muon g-2
None
Mu2e
FNAL should review why the team has not considered other reasonable experimental concepts that could produce results at interesting levels of sensitivity less than 10⁴, but at much earlier times. Such a review should consider if staging of this experiment is feasible, cost effective and more timely.
LBNE
None