## Slide 1
FAST / IOTA Shutdown 2023-2024
Enclosure STATUS: ODH-0 & Supervised Access (“same as it ever was”)
General: -IOTA Bake GFCI (AD/Web 57570). No movement
-ESB Laser Lab electrical work on hold for vestibule
ES&H: -OSC Mode in LL. New South Gate. Interlock Test. Poly beads.
IPI: -ESB 480/120VAC Electric Req being generated (still).
  -DON’T TOUCH beamline stuff.
  -Exciting IPI updates to follow (Chip)
Water: -Chiller needs repair since Jan. Waiting on PO. (Req 360865)
•Fluids Engineer, Mike Hanson, is on it™
AD Shutdown’24: Power outages: none, KSS T88 caught fire
— Contact FAST RunCo with any work or access requests —

## Slide 2: ISD Updates for NML
E-Lights – In Progress (166735 being re-Scheduled)
Carpeting – Carpet Tile Loose – Complete ✅
Raised Floor Panel – Complete ✅
Data Center Carpet Tile with hole – Complete ✅
South Stair Lighting – Complete ✅
Roll Up Door - In Progress (168986) assigned to the “Schedule Planner”.
Clean Y-Strainer – Hold (181072) due to Abatement – the project is not going well, not able to get the old bolt out, calling in a contractor possibly.
Loading dock weight capacity – Approved for Arial Lift use. FPC is aware of the progress. In Progress – Amy is working on ComEd Credits. So hopefully this will get it moving. Related to High Bay Lighting LED Upgrade (163677).

## Slide 3: ISD Updates for NML (cont.)
Catwalk Electrical Receptacle Changeouts – In Progress (189398) Placed WO and NML taped near the outlets. Electricians working.
ESB Lights Out – In Progress (189694)
ESB HVAC – waiting on NPT to start. In Progress – PO date pushed back to 01/27/2025. 6-8 week lead time on the units.
Strips on driveway – R & G needs a task code. In Progress
HVAC in control room – this has been passed to Tim Burger to look at.

## Slide 4: ISD Updates for NML (cont.)
Cleanup in mech rooms – Working with JP & his team to tag items to keep. Anything else ISD will get Clorica to clean up. In Progress (still some stuff)
Tire Marks from lift – Electrical group to pay for this? In Progress
Other outside work – Cleanout the front forest under the grates. Complete ✅
Mechanical Checks on critical water connections – In Progress
Ejector Pit piping system tightening work – In Progress. I believe this is done.
Window Cleaning - In Discussion. FY2025
Exterior Lights (both inground and canopy) - waiting on quote. On Hold
Concrete form tabs removal – Complete ✅
South Bathroom Lights. Being scheduled

## Slide 5
FAST shutdown continues through fall for the installation of the IOTA Proton Injector. Thanks to support groups helping us
  (HLRF, Instrumentation, MSD, ISD, etc...)
IPI source conditioned up to 51kV, 12mA
  Connecting Allison Scanner to IPI Source
HLRF build out is nearing completion
  Commissioning HLRF on standby as we await further support
  HLRF is now our Critical Path
LCW chiller repair still waiting on PO (Req 360865)
Thanks to OPS for being vigilant on ACNET alarms
— Contact FAST RunCo with any work or access requests —
FAST / IOTA 9:00 Report