## Slide 1
Main Injector Shutdown Status
Denton Morris
9 o’clock Meeting
August 15, 2024

## Slide 2
Tunnel Work
8/16/2024
MI Department Meeting | D. Morris
2
MI-8 Collimator installation
Cable pulls in progress
Collimator steel is being staged at MI-8
RF Dual PA cavity upgrades (3 stations)
Electrical pulls are complete
Upgrading four modulators (one spare)
NOTE: Unable to test RF until KRS pulsed power returns
Address found LCW leaks (underway with TD support)
323 Dipole will be addressed next week
MI-201 Sump discharge line replacement – underway
MI-218 Sump discharge line replacement – complete
Vacuum issues in P150 line (~704) being investigated

## Slide 3
Upstairs Work
8/16/2024
MI Department Meeting | D. Morris
3
Main jobs:
Heat Exchanger cleaning: MI-62, MI-8, MI-10 and 20 are finished*
MI-30 in progress
Investigating pitting and corrosion
VCB PMs
Transformer/Switchgear PMs (paused)
PM all compressors LCW filters/pumps/motors
MI-218 excavation complete, topo done and in process for shielding verification
MI-20 Upper transformer cable pulls
MI-20 Lower transformer cable pulls

## Slide 4
Conventional Power Outages
8/16/2024
MI Department Meeting | D. Morris
4
Please report any additional MI outages to the MCR.