## Slide 1: Muon Campus Shutdown Report
Jerry Annala
Friday 09:00 Shutdown Meeting
August 23, 2024

## Slide 2: Muon Campus status
Study – Alternative M5 optics
Study – M1-M3 Optics
Many tunnel jobs still need final engineering or planning details before work begins
Injection Kicker horizontal motion-control issue fixed
M4 Final Focus LQ’s alignment work holding for analysis of target position change
Planning for Power Supply primary wiring and circuit breaker work
ESS2 assembly has begun
Prototype ESS2 will need to be removed from DR prior to running beam
  Related to buyback accounting between Mu2e Project and AD spares funds
  Hope that operational ESS2 will be ready for installation in early October
  Will evaluate options if operational ESS2 is delayed significantly
AP-0 A/C work back on hold after a few days of controls activity four weeks ago
Fluorinert skid for extraction septa is in progress

## Slide 3: Upcoming work
Main worklist items
  AP-0 Dump system will be drained but is on hold.
    Crane control pendant batteries are on order
  Install rad hard 8Q24 at Q205, send uninstalled 8Q24 to TD for rad hard water lines
  Q205 vacuum pipe replacement to simplify vacuum connection to ELAM
  Profilometer extraction profile monitor vacuum Tee installed upstream of ELAM
  Several alignment tasks including D30 level run and M4 Final Focus
  ESS1 and ESS2 septum stand motion-control improvements in progress
  M4 Final Focus vacuum installation, A/C dipole installation
  Need to upgrade power supply panel breakers as necessary
  Install additional steel shielding above ECMAG
  Repair Kirk Key hardware on disconnects
  Hope to finish operational ESS2 and install it in tunnel late in shutdown
ESS2 (operational version in A0 Clean Room)
  ESS2 cathode will be installed with the small warpage
  Three-point cathode support adjustments may reduce the warpage
AP-0 A/C controls work paused; reason unknown