## Slide 1
Main Injector Shutdown Status
Denton Morris, Marty Murphy
AD 0:900 Scheduling Meeting
September 6, 2024

## Slide 2
Tunnel Work
9/5/2024
MI Department Meeting | D. Morris
2
MI-8 Collimator installation
Cable pulls completed
Steel for both collimators is over half-way stacked
-Configuring and installing the vacuum chamber next
RF Dual PA cavity upgrades (3 stations)
Electrical pulls are complete
Upgrading four modulators (one spare)
NOTE: Unable to test any RF until KRS pulsed power returns
Address found LCW leaks (underway with TD support)
332 Dipole will be addressed soon
MI-201 Sump discharge line replacement – completed
MI-218 Sump discharge line replacement – completed, waiting on
topo analysis
Vacuum leak in P150 line identified and being repaired

## Slide 3
Upstairs Work
9/5/2024
MI Department Meeting | D. Morris
3
Main jobs:
Heat Exchanger cleaning: MI-62, MI-8, MI-10, 20, 30, 40, 50 are clean
MI-52 in progress
Investigating pitting and corrosion in end shells
VCB PMs completed
Transformer/Switchgear PMs (paused)
PM all compressors LCW filters/pumps/motors
MI-20 Upper transformer cable pulls in progress
MI-20 Lower transformer cable pulls in progress

## Slide 4
Conventional and Pulsed MI Power Outages
9/5/2024
MI Department Meeting | D. Morris
4
Please report any additional MI outages to the MCR.