## Slide 1
Main Injector Shutdown Status
Denton Morris, Marty Murphy
AD/MI Dept. Meeting
September 11, 2024

## Slide 2
Tunnel Work
9/11/2024
MI Department Meeting | D. Morris
2
MI-8 Collimator installation
Steel for both collimators is over half-way stacked
Waiting on delayed parts for the jaws
Bob Zwaska wants us to fabricate a spool piece to have on hand
RF Dual PA cavity upgrades (3 stations)
Electrical pulls are complete
Upgrading four modulators (one spare)
NOTE: Unable to test any RF until KRS pulsed power returns
Getting estimates on schedule for testing after pulsed power
and water are back online
MI-201 Sump discharge line replacement – completed
MI-218 Sump discharge line replacement – completed, waiting on
topo analysis

## Slide 3
Tunnel Work
9/11/2024
MI Department Meeting | D. Morris
3
Vacuum leak in P150 line identified and being repaired
Still needing to be done:
332 dipole leak repair
Compressed air leak repairs (BV solenoids)
Adjust aperture at 232 ???
Move MI quads based on previous high field orbit ???

## Slide 4
Upstairs Work
9/11/2024
MI Department Meeting | D. Morris
4
Main jobs:
Heat Exchanger cleaning: MI-62, MI-8, MI-10, 20, 30, 40, 50 are clean
MI-52 in progress, prepping MI-60 magnet/RF equipment systems
Investigating pitting and corrosion in end shells
VCB PMs completed, a few need additional attention
Transformer/Switchgear PMs (paused)
PM all compressors LCW filters/pumps/motors
MI-20 Upper transformer cable pulls in progress
MI-20 Lower transformer cable pulls in progress

## Slide 5
Conventional and Pulsed MI Power Outages
9/11/2024
MI Department Meeting | D. Morris
5
Please report any additional MI outages to the MCR.