## Slide 1
Main Injector Shutdown Status
Denton Morris, Marty Murphy
AD/MI 0900 Meeting
September 13, 2024

## Slide 2
Tunnel Work
9/13/2024
MI Department Meeting | D. Morris
2
MI-8 Collimator installation
Steel for both collimators is over half-way stacked
Delayed parts for the jaws arriving next week
Spool pieces are in hand
RF Dual PA cavity upgrades (3 stations)
Electrical pulls are complete
Upgrading four modulators (one spare)
NOTE: Unable to test any RF until KRS pulsed power returns
Getting estimates on schedule for testing after pulsed power
and water are back online

## Slide 3
Tunnel Work
9/13/2024
MI Department Meeting | D. Morris
3
Vacuum leak in P150 line repaired
Still needing to be done:
332 dipole leak repair
Compressed air leak repairs (BV solenoids)
Adjust aperture at 232
Move MI quads based on previous high field orbit
Investigate WQB inductance concern

## Slide 4
Upstairs Work
9/13/2024
MI Department Meeting | D. Morris
4
Main jobs:
Heat Exchanger cleaning: MI-62, MI-8, MI-10, 20, 30, 40, 50 are clean
MI-52 in progress, prepping MI-60 magnet/RF equipment systems
Investigating pitting and corrosion in end shells
Transformer/Switchgear PMs (paused)
PM all compressors LCW filters/pumps/motors 75% complete
MI-20 Upper transformer cable pulls in progress
MI-20 Lower transformer cable pulls in progress

## Slide 5
Conventional and Pulsed MI Power Outages
9/13/2024
MI Department Meeting | D. Morris
5
Please report any additional MI outages to the MCR.