## Slide 1
Main Injector Shutdown Status
Denton Morris, Marty Murphy
AD/MI 0900 Meeting
20 September 2024

## Slide 2
Tunnel Work
9/20/24
MI Department Meeting | M. Murphy & D. Morris
2
MI-8 Collimator installation
Steel for both collimators is over half-way stacked
Delayed parts for the jaws arriving next week (9/23/24)
Spool pieces are in hand if needed.
RF Dual PA cavity upgrades (3 stations)
Electrical pulls are complete
Upgrading four modulators (one spare)
NOTE: We are unable to test any RF until KRS pulsed power
returns. Developing a schedule for testing after pulsed
power and water are back online.

## Slide 3
Tunnel Work
9/20/24
MI Department Meeting | M. Murphy & D. Morris
3
Vacuum leak in P150 line repaired
Still needing to be done:
MI-332 dipole LCW leak repair begins today.
Compressed air leak repairs (BV solenoids) – will start next week
Adjust aperture at RR232 - Pending
Move MI quads based on previous high field orbit - Pending
Investigated Q402 WQB inductance concern: all is well!
Thanks to Ops and PESD for their efforts.
Leaking LCW hoses in MI30 HRA/Contamination area will be replaced. ALARA planning in progress now.

## Slide 4
Upstairs Work
9/20/24
MI Department Meeting | M. Murphy & D. Morris
4
Main jobs:
Heat Exchanger cleaning: MI-62, MI-8, MI-10, 20, 30, 40, 50 & 52 are clean
MI-60 in progress.
Investigating pitting and corrosion in end shells
Transformer/Switchgear PMs (paused)
PM all compressors LCW filters/pumps/motors 85% complete
MI-20 Upper/Lower transformer cable pulls will be complete at COB today.

## Slide 5
Conventional and Pulsed MI Power Outages
9/20/24
MI Department Meeting | M. Murphy & D. Morris
5
Please report any additional MI outages to the MCR.