## Slide 1: Muon Campus Shutdown Report
Jim Morgan
Friday 09:00 Shutdown Meeting
September 20, 2024

## Slide 2: Muon Campus status
Study – Alternative M5 optics
Study – M1-M3 Optics
ESS2 survey was completed, followed by completion of vacuum work
  Successful leak check after ion pumps installed, ready to transport to NWA
D30 downstream mechanical work waiting on key Q205 part (next week?)
AP-0 Dump System drained and lines dried, Vault shielding blocks back in place
Fire Hydrant near AP-10 valved out due to underground water leak
LCW leak rate greatly reduced after MSD repaired most known leaks
  Largest leak was on sub-header
  A Delivery Ring sextupole has an internal leak and needs to be replaced
  Resistivity has been declining, may be time to change DI bottles at CUB
Prototype ESS2 will need to be removed from DR prior to running beam
  Related to buyback accounting between Mu2e Project and AD spares funds
  Hope that operational ESS2 will be ready for installation in late October
  Will evaluate options if operational ESS2 is delayed significantly
Domestic water leaks near AP-0 adjacent to Transport berm
AP-0 A/C work continued Thursday, after a month pause

## Slide 3: AP-10 downstream sump activity after hydrant flushing
AP-10 fire hydrant flushing
AP-10 fire hydrant valved out

## Slide 4: Muon LCW resistivity decline in the past two years
LCW polish resistivity
LCW resistivity

## Slide 5: ESS vacuum leak-check in A0 Clean Room

## Slide 6: Upcoming work
Main worklist items and other upcoming work
  Repair Kirk Key hardware on disconnects
  Leaking Delivery Ring sextupole needs to be replaced
  Install rad hard 8Q24 at Q205, send uninstalled 8Q24 to TD for rad hard water lines
  Q205 vacuum pipe replacement to simplify vacuum connection to ELAM
  Unroll ELAM? (was rolled 24 mr to improve g-2 extraction trajectory)
  Profilometer extraction profile monitor vacuum Tee installed upstream of ELAM
  Several alignment tasks including D30 level run and M4 Final Focus
  M4 Final Focus vacuum installation, A/C dipole installation
  Need to check sizing of all power supply panel breakers, upgrade as necessary
  Install additional steel shielding above ECMAG
  ESS1 and ESS2 septum stand motion-control improvements
  Hope to finish operational ESS2 and install it in tunnel late in shutdown
  Repair of domestic water break near AP-0 may disturb Transport berm
ESS2 (operational version in A0 Clean Room)
  Transport to NWA planned for today for eventual high voltage conditioning
AP-0 A/C will hopefully continue and finish