## Slide 1: OTE Building PMG Report a/o March 25, 2013

## Slide 2: Agenda
CDF D&D: C. Cooper
IARC Networking: C. Cooper
OTE Building Project: R. Merchut
  Coordination
  State Activities
  Schedule
  Fiscal
  Summary Action Items

## Slide 3: CDF Decommissioning and Preservation
Goal: Preserve CDF assets so they can potentially be used by ORKA
  Solenoid
  Mechanical systems
  Electrical infrastructure
Scope of work
  Remove tracking detectors and plug EM calorimeters
  Remove electronics and cabling
  Dismantle external muon systems
  Return central spectrometer to collision hall to be ready for modification for future uses
Boundary conditions
  Must be compatible with IARC
    Coordinate future building needs
    Complete work before beneficial occupancy
      End of CY14

## Slide 4: CDF Decommissioning Status
Ready for heavy lifting
  NOvA FHEP removed in February
  Assembly hall cleanup is complete
    CDF display items moved to storage
    NOvA near detector factory on east side
  Ready to open 1200 ton shield door
Rate limiting factor is availability of labor
  PPD Mechanical Group is oversubscribed
    Rigging group working on MicroBoone
    Techs on various IF projects
  POs placed for contract techs and riggers
    $200k M&S allocated
      Includes $100k from buybacks and cancelled display project POs
Getting estimates for muon wall demolition
  LBNE interested in steel for shielding
  Circulating draft Statement of Work for comments

## Slide 5: CDF Decommissioning Plan
FY13
  Move north muon wall and central detector to assembly pit
  Remove tracker
  $200k budget is just enough based on planning exercise
    This is base labor from estimate, i.e. zero contingency
  Use summer labor to strip cables, electronics, etc.
  Recover scintillators, PMTs for IF experiments
  Can start muon wall demolition if other funds are available
FY14
  Remove cable bridge
  Demolish CMX arches
  Demolish muon walls
    Move to assembly pit if funds insufficient
  Return spectrometer to collision hall
Not CDF,
but an incredible simulation
ORKA

## Slide 6: Future Use Activities
New discussions of removing gas shed, removing horizontal nitrogen Dewar, and moving vertical nitrogen Dewar (pictured)
Planning ICW upgrade
Considering best location for mechanical systems
  Moving air handlers to roof may be less expensive and can add ~800 sq. ft. of usable space
OTE Associated work:
  Build wall by bridge
  Some minor painting
  Temporary dust barrier in opening built between CDF and OTE

## Slide 7: Outlook
On the edge for getting trackers out in FY13
Budget was $4M fully loaded with contingency
To be confident we will get the job done
  Need at least $3M in FY14
  Need greater access to FNAL technicians
    Task managers and team leaders if we are relying on contract labor

## Slide 8: OTE Outfitting GPP G13-211
FY 13: $2M for VoIP/networking & Contingency.
  Develop Plan for moving ahead with VoIP/Networking w/out tenant layouts.
    Discussions with CD to incorporate independent network underway.

## Slide 14
IASU Update (IGPP)
Phase 2 scope approximately 85% complete.
CDF Coordination
Demolition for 1st floor OTE/CDF entrance complete.
  CDF barrier to remain in place until OTE is environmentally enclosed & CDF protected from all dirt and dust.

## Slide 15: OTE Project Status:
Shop drawing review continues
More than 235 RFI’s rec’d from contractor have been responded to.
Schedule Oversight on-going. Continue to work with contractor to provide coordinated information.
Safety procedures continue to be expanded as more subs come onto the project.
Change Control Board reviewing COR 122 for ceiling changes. (Change Request #3).

## Slide 16: OTE Project Status:
LEED procedures & Action Plan implemented.
  Contractor reporting 99% construction waste has been recycled.
  On track to meet goal of 20% (by cost) of regionally manufactured materials.
  On track to meet goal of 20% (by cost) of recycled content in materials used.

## Slide 17
Continue to have 35-45 workers daily.
  Exterior enclosure
    Corrugated Metal Panels - 2nd & 3rd floor
    1st floor framing started
  Window framing & glazing
  Roofing
  MEP & FP pipe, raceways & ductwork hanging
  Stairway #1
  Interior Studs
  Geothermal field

## Slide 18: Exterior Enclosure

## Slide 19
Enclosure

## Slide 20
Roofing

## Slide 21
West Elevator & Stair

## Slide 22
2-hour wall at CDF
2nd floor Conference Rm
East Stair

## Slide 23: MEP

## Slide 24: Geothermal

## Slide 25: Two Week Look Ahead
Roofing on high & low roofs
Curtain wall framing.
Exterior panels 2nd & 3rd floor.
Glass installation 2nd & 3rd floor ribbon windows.
MEP, FP equipment & pipe runs
1st floor enclosure
West Stair
Geothermal

## Slide 26: State DCEO Activities
DCEO quarterly report to State due 3/29/13 for quarter ending 2/28/13.
Project on schedule for grants to be 100% costed by 5/31/14 grant requirement.

## Slide 27: Schedule Adjustments
No requested schedule adjustments.
  MS 1 Bldg Shell Complete: 5/9/13*
  MS 2 Substantial Completion: 11/5/13
    (Project is fully costed at MS 2, retention remains)
  MS 3, Project Complete: 1/29/14
  *No cost COR 151 rec’s from BMC to extend MS-1 only to 6/19/13 under review.

## Slide 28: BMC Schedule

## Slide 29: Schedule

## Slide 30: Schedule

## Slide 31: Tracking Milestones
Project is fully costed at MS 2, retention remains

## Slide 32
BMC Construction BCWS & ACWP

## Slide 33
BMC Monthly Costing
Monthly Average to date: $996,215
Required Monthly Average to complete: $1,066,000

## Slide 34
601 TSR Budget Balance
ALL Grant Costing w/ BMC Projection
NOTE: $1.8M BMC Feb pay request was not processed by end of month.

## Slide 35: Financial

## Slide 36: Financial – Estimated at Completion

## Slide 37: Financial – Available Contingency
Feb ’13:
48% based on Cost
50% based on Time
(Does not include IGPP)

## Slide 38: Contingency Management
Sources available to fund change orders:
  IGPP;
  De-scope from anticipated T&M work;
  De-scope from A/E support work;
  DOE backstop (GPP Outfitting project);
  De-scope from main construction work (will not recover all funds);
  Value engineering main construction work

## Slide 39: Summary Action Items
Continue shop drawing & change order review, RFI responses
Continue construction coordination & oversight.
Continue schedule oversight
Initiate plan for engineering design Outfitting GPP.
Continue discussions with CD for VoIP, networking.

## Slide 41: Backup

## Slide 42: CDF Layout