## Volodya T.
Section | Comment | Response
| Chamfered edges for welding: do they require QC inspection? If so, who will inspect them and what are the acceptance criteria. | The chamfered edges should meet the dimensions in the applicable drawing and verified by the fabricator. There is a source final inspection by FRA which states that they will be verifying dimensions but they should put together a source inspection plan so that all the requirements will be verifying during the source inspection. This inspection plan would also address your last comment on the fit up at the fabricator.
Weld inspection:
| Who will perform the inspection and evaluate if the welds are of a good quality (the vendor and will provide inspection certificate, DUNE/FNAL expert, or an independent subcontractor)? | The welding requirements are addressed in the technical specification for the welding performed by the fabricator. The documentation does not address the welding inspection that should be performed during assembly at SURF. The procedures should be revised to include the welding and NDE requirements for the assembly.
What type of inspection is needed (just visual, dye, etc.)?
What are the acceptance criteria?
The monorail will be load tested by the fabricator.
| Will this be sufficient, or an independent load testing will be required at SURF? | Additional load test at SURF
| Will DUNE/FNAL experts participate in the load test by the fabricator or an independent expert will need to be subcontracted? | Source inspection to include site visit of dry fit/load test
Engineering note
| CE cross with electronics will be mounted to the penetration. Has the load been estimated? Does this require engineering analysis? | Load has been included in analysis
| How the work on CE will be performed – off scissor lifts, a work platform will be installed, or people will be standing on the roof of colboxes? | Additional platform structure located above coldboxes for work access
| Similar question on the cryogenic instrumentation: if the load due to cryogenic instrumentation has been analyzed / needs to be analyzed? | Load has been included in analysis
If I understand it right, the cold boxes will be grounded to the FD ground.
| Are there any dedicated ground points designed on the ColdBox? | Coldboxes will have lateral support to cryostat, additional jumpers may be added for grounding
Bolted connections:
| could somebody please point me to the document where the torques are specified? | AISC370 - Section J3, AISC Steel Design Guide 27 - Chapter 12.6/12.7. "Installation methods for stainless steel fasteners are not standardized." "...galling should be avoided."
Interface drawing
| I think it does not show the patch panel for the cold electronics cables. Since the space is really tight, did you check that there is enough room to accommodate the patch panel, the cable strain relief system and to account for cable bending radius? Same for PDS cables - have those been taken into consideration? | This has been checked with CE consortia and is shown in coldbox interface drawing.
Dry fit of completed assemblies at vendor’s premises.
What will be inspected?
| bolted parts mate properly | yes
| tolerance on the door (enable the box to be sealed). | gaps <1/4":10'
| Anything else? and what acceptance criteria would be? | meets or exceed tolerances
| Internal dimensions of the coldbox | yes
| Fitment of quadrants (I guess there should be some check for the flatness of quadrants and the edges must be flush for welding, etc.) | meets or exceed tolerances
| External interfaces like attachment points for the clamps (position, dimensions, etc) | Vendor shall provide plan as part of pre award submittals during procurement process
Do these need to be spelled out in the contract (along with requirement to provide material certificates, quality inspection results, etc.)?

## Kyle Z.
Section | Comment | Response
| Drawing note which appears throughout: “LARGE NON-STOCK ITEMS MAY BE WELDED TOGETHER TO MAKE UP THE LONG LENGTHS. GRIND FLUSH.” Have you considered adding a weld prep and weld callout specific to this? | Full penetration weld shall be adequate.
Flange parts with through holes:
Double check quantity callouts (see notes in pdf).
Double check feature control frames throughout drawings. There are a few of them which aren’t consistent. And a few with confusing units (see notes in pdf).
Bolts in BOMs (see notes in pdf)
| Fastener specifications are vague and open to interpretation. Recommending adding details to the drawing package which match the bolts from analysis. | Shall add explicit callout to hardware with additional specificity
This is particularly true on pdf pages 33 and 34. Page 33 notes call for “coated steel”. Although it’s not clear why these would differ from the others in the assembly
Double check quantities
| Have you considered specifying with some quantity of spares as part of procurement? | 25% extra
Bolts for doors: Is length okay with gasket in place?
| Should quantity of washers (for 5/8” bolts) be twice the quantity of 5/8” bolts? | yes
There is an option of welding small plates of x thickness to the back side of the CB quadrant door flange (in lieu of a nut). There is a small efficiency gain when connecting or disconnecting the door. Conversely, if a bolt were to gall in place it would be more challenging to fix. In conversation with the team this option has been considered previously but has been ruled out due to the risk of galling and fusing a bolt which would result in the need to halt operations and make a repair.
Regarding the height of the monorail: Consider the possibility of needing to raise, lower or pitch the beam (i.e. shims) so it mates with the rest of the system. It is easy to lower it with shims but not so easy in the other direction.
| Regarding loads in analysis: The cable tray (with trolley wheels on monorail) and cables mass was not included. Please assess the implications of this and whether the analysis needs updating. | Double checking weld capacity.
In a follow up meeting on Wednesday the 30th, a subset of engineers reviewed the model and drawing of the CB with its detector components inside. The tightest fit is in the CB’s depth direction (width of APA). These drawings should be reprinted and uploaded.

## Caroline F.
Section | Comment | Response
Scaling
F: DUNE HD cold box (DUNE HD-CB) is twice the height of ProtoDUNE HD-CB, of similar 304 SS structure.
Heat load
| REx: ProtoDUNE HD-CB internally insulated w 200 mm of PIR (or PUR ?) insulation foam. Not sufficient: cold spots observed at the bottom of CB; excessive LN2 consumption; lowest achieved temperature : 150 K. | Polyiso foam. Samples sent to CERN, deemed adequate
F: DUNE HD-CB internally insulated w 400 mm of PIR. Same as ProtoDUNE VD-CB which proved satisfactory.
Internal Pressure rating
REx: ProtoDUNE HD-CB operating pressure limited to 30 mbarg (PSV@60 mbarg ) which limits cool-down flow rate, and cryo operability. ProtoDUNE HD-CB is always open to vent (open pipe) protected by safety relief w weight flange. Pressure drop in vent pipe is a limiting factor towards achievable flow with respect to admissible pressure.
F: edms 2373857 Requirements - With a design pressure of 90 mbarg and a pressure relief set around 85 mbarg DUNE HD-CB will allow more flexibility for cryo operation. However still depending on how low the pressure drop in the vent line will be.
F: A nominal operating pressure of 60 mbarg is quoted in edms 3087803 leak test procedure.
C: Special care should be taken to minimize the pressure drop in the vent line and associated instrumentation.
F: edms 3123703 Pressure Relief Valve sizing - The considered worst case scenario is "blocked discharge" with incoming GN2 cool-down flow rate of 28 g/s @ 90 K
| Q1: From P&ID in pp.4 it appears the vent line is equipped with a number of instruments including a shut-off and a control valve (so vent is not an open pipe). Closure of the valve gives rise to the "blocked discharge" scenario. Is the upstream cryo system equipped with integrated safety in order to limit the incoming GN2 flow rate to the considered 28 g/s ? | cryo engineer to answer
| Q2: In the considered sizing scenario the relieving temperature is 90 K. Is this the scenario leading to the largest volumetric flow rate through the safety valve? Have any other scenario with same mass flow rate @ higher temperature been considered / excluded (e.g. beginning of cool-down or to account for the + 60 K specified as uniformity requirement)? | cryo engineer to answer
Cleanliness
REx: ProtoDUNE HD-CB foam insulation is sealed from the inner volume of CB via plastic liner. Liner is fragile and easily damaged during handling creating openings and dust. A metallic internal membrane would be preferable to protect cold volume from insulation foam dust.
F: edms 3061763 2D drawings specify "Finished article shall be free of oils, lubricants and other contaminants".
| Q3: Does this refer to a basic cleaning or to any more specific cleaning procedure referenced in the quoted standards? What is the cleanliness acceptance criteria? How will it be checked? | Standard note for fabricated metals
Leak tightness
REx: On ProtoDUNE HD-CB there is no way to check the tightness of the seal after door closing (open vent). Tightness is defined by safety in the cleanroom, not by purity requirement (since permanent flushing). As a consequence access to the clean room is forbidden during cool-down; at the end of cool-down oxygen level and seal tightness are checked before granting access.
Requirements
F: edms 2373857 Requirements - There is no leak tightness requirement specified.
| Q4: Is it foreseen that people work in the clean room continuously during all phases of the cold boxes operation? Is there any leak tightness criteria defined which conditions access to the clean room during cool-down from an ODH safety point of view ? Is any leak-tightness check possible and foreseen after each door closing operation ? How ? | Yes, people work in cleanroom through all phases. ODH sensors located within cleanroom during cooldown.
Welds
F: edms 3061763 2D drawings - specifies "continuous air-tight weld on all interior corner joints". This is understood as an individual acceptance criteria.
| Q5: "Air tight" is not a common phrasing to me for the acceptance criteria. Is it specified in the welds specification AWS D1.1/1.6 ? What is the acceptance criteria of air-tight and how is it controlled at the factory ? | Pressure drop on pneumatic test, soapy water test check for air bubbles
F: edms 3061763 2D drawings - specifies in note 3 of assy dwg: "completed assembly of (4) quadrants and (2) doors to be air-tight when bolted and welded together", while note 6. on following dwgs quotes "to be air-tight when bolted together". This is understood as a global acceptance criteria, controlled at the Site Acceptance Test, when the full assy is welded together and seal is installed, covered by edms 3087803 Leak test procedure.
C: The spec should be "air-tight when bolted and welded together", consistent through all dwgs. Consider also mentioning door seal installed for better clarity.
Seal
REx: At ProtoDUNE HD-CB the seal is installed on the door with glue which is sometimes not enough to hold it in place. It would be preferable to hold it in place thanks to a groove or to screws. The rectangular section does not permit to fill all gaps unless a big force is applied. A round section would be preferable.
F: During the DUNE HD-CB PRR presentation it was mentioned that the seal would be installed on the cold box flange side. However, in edms 3024281- Assy Sequence section 5 states to "clean the door sealing surface" and prepare according to glue specs and edms 3087803 Leak test procedure pp 4-9 mentions that "The top and bottom halves of the doors have been welded together and the gas seal has been glued to the door". At the same time, edms 3024281- Assy Sequence section 4 first installs seal (according to 5) and then after prepares doors, including welding the half sections which seems inconsistent with installing the seal on the door. Not sure what the selected seal location (door or cold-box side) and sequence is.
F: edms 3024281- Assy Sequence section 5 states "The door seal is heavy and should be applied while the coldbox is horizontal" while fig 5-1 quotes "The door seal should be installed in the vertical orientation".
C: The seal location (door or cold-box side), orientation (vertical or horizontal) and installation sequence should be clarified and consistent through documentation.
F: edms 3087803 Leak test procedure pp 4-10 mentions handling of the door equipped with the seal.
| Q7: How is the integrity of the seal ensured during handling ? | Visual inspection; rips,tears,embrittlement, material degredation, etc.
Leak-test of the full assy
F: edms 3087803 Leak test procedure pp 1-6: "The purpose of the leak test is to verify that all the welds are gas tight to at least 1 SCFM." "At the same time the door will fit on the box and that the gasket will form a gas tight seal against the main body." This test will quantify the total tightness of the cold box system (welds + seal) by the pressure decay test method. This is understood as the Site Acceptance Test.
F: edms 3087803 - leak-test procedure: section 4.5: "If the drop is more than 18 mBar then Snoop leak detector is applied around the gasket to locate where the leak is. The leak will then need repaired, and the leak test repeated." The seal is understood as the main candidate for leaks.
| Q8 : What if a leak is suspected on a weld ? | repair
F: according to edms 3024281- Assy Sequence section 3, thermal insulation is installed after welding 2 quadrants together and before the final seam weld of both 1/2 assemblies.
| Q9: Are the site seam welds between quadrants individually inspected and qualified before insulation can proceed? How ? | We are developing a QC check for the onsite welds. Qualified welding inspector shall be required.
| Q10: Can you confirm the already installed insulation is not a tight volume at this stage and pressurized air will reach out to all welds? In case the total leak test exhibits an unacceptable leak on any site (or factory) weld already covered by insulation, how is it foreseen to localize the leak and to repair it ? | repair weld from exterior
F: edms 3087803 Leak test procedure - Table 1-1 coldbox parameters defines the global leak-tightness acceptance criteria as "allowable leak rate 1SCFM (478mbarL/s)" .
C: For completeness the considered gas nature and the considered standard temperature and pressure conditions should be specified
C: Nominal operating test temperature should be documented as a parameter
| Q10: How is this criteria defined? Does it correlate to the individual acceptance criteria of "airtight" welds in 2D (cf Q5) ? Or does it correlate to ODH safety in the clean room ? | 1 SCFM was provided by project ODH cryogenic engineer
F: edms 3087803 - leak-test procedure: Table 1-1 cold box parameters - the considered volume for the leak test is internal volume without insulation 95.5 m3, while assy procedure involves installing most insulation on 2 assembled quadrants before 1/2 cold box assemblies are welded together and the fully assembled cold box is leak tested.
C: Reference parameters and pressure decay calculation should be revised taking into account the relevant configuration, i.e. internal volume with insulation.
C: "Dimensions" to be quoted "overall dimensions" to relate to table 1 HD cold box Requirements; Other internal relevant dimensions to be quoted. "pressures" to be quoted mbar gauge to avoid confusion.
F: edms 3087803 - leak-test procedure: section 4.4: "The final pressure relief valve is mounted to its port."
| Q11: The cold box is in horizontal position at this stage. Can the safety valve indeed be mounted in horizontal position without risk to damage its seat/seal ? Is any adaptation for vertical orientation foreseen? | install valves when coldbox assembled and in vertical orientation, or brace features during rotation
F: edms 3087803 - leak-test procedure: section 4.5: "Pressure test"
| C: As the cold box is not a pressure equipment the test is not stricto sensu a pressure test, rather a functional leak test. | wording shall be adjusted in documents to consistently show "leak test", and not pressure test
C: The allowable leak rate 478 mBar L/S is specified in standard pressure and temperature conditions in Table 1-1, to be defined. In case the nominal test temperature is different from the standard temperature, then a temperature correction should be applied in the calculation of the admissible pressure decay at the nominal test temperature. Temperature measurement to be foreseen in test set-up. Eventual temperature changes during the test period to be taken into account.
| Q12: Should the procedure make reference to any applicable standard for leak testing ? | leak test document outlines procedure
| Q13: Is this test or a similar one in vertical position intended to be repeated after each door opening / closure operation ? Is there a way to close off the cold box volume once connected to its interfaces (e.g. valve present in each cryo pipe) ? How often is it expected to exchange the door seal ? | Each coldbox shall cycle 25 times over the period of 1 year. Will ensure we have a set number of spare gasket material for repair of damaged seals.
Engineering note
F: edms 2874218 - Eng.Note: pp9 "During APA testing gaseous nitrogen at approximately 90K and operating pressure flows through the roof cryogenic penetrations into the coldbox internal volume."
| Q17: in Load case #2 what is the considered shell temperature / cryo interface temperature ? | room temp, thermal CFD analysis conducted seperately
2D
Handling
F: edms 3061763 - 2D drawings - Cold box Assy dwg Note 7: "When handling each piece; ensure flange faces are protected and maintain flatness."
F: edms 2825997 - Eng Note: pp.41 Handling results states : " The peak stresses in this configuration result in plastic deformation, and such this configuration shall not be permitted without additional support on the cantilevered corner. It is preferred to support the coldbox quadrants either on the side with bolt flanges facing up, or on the back as noted in the following subsection. "
| Q14: Where in the specs is this restriction turned into a requirement to the manufacturer for handling at the factory? Which provisions are made at the site to avoid this configuration? Worth mentioning it in the Assy Sequence? | Can add handling restriction document to deliverables
Welding
F: edms 3061763 - 2D drawings - Cold-box door half bot Note 5: "Large non-stock items may be welded together to make up the long lengths". It is understood sheet metal cladding is permitted .
| Q14: Where is this specified how the cladding shall be done ? And controlled ? | Full penetration weld specified to minimize warping during weld cooling. Fabricator to detail weld prep.
Bolting
F: edms 3061763 - 2D drawings - Cold box Assy dwg BOM: "Hex bolt stainless steel"
F: edms 2825997 - Analysis Plan: pp7 Material properties "Further details regarding the materials of bolts, nuts, and washers as well as welding materials will be provided in the final design and manufacturing documents."
| Q15: Should there be a more specific specification of bolts through manufacturing and assembly documentation, consistent with the bolts and torque definition per Analysis and Eng Note ? | Understood, shall update hardware specification on drawings and in the tech specification
| Q16: Why is ASTM A320 for SS bolting for low temp service not quoted as applicable standard in specs while it is in Analysis Plan and Compliance Office Validation ? | Sall update applicable specification to document
Technical Specification
General
F: build-to-print contract. Contractor has no design responsibility. Technical specification, 3D model and 2D drawings and any indication on these drawings is considered as "contractual specification". No other documentation supplied. Edms 3061760 technical specifications is not very specific in terms of technical requirements. It is understood most specific technical requirements reside in 2D drawings.Edms 3061760 technical specifications is not very specific in terms of QA/QC requirements. It is understood most QA/QC requirements reside in quoted applicable standards. Only additional specific controls like FAT dry assembly, load test or "critical test" identified by customer are to be described in specs.
| Q17: correct understanding ? | Yes
C: pp1-1 intro: quoted temperature is 90K, (+40K, -0K), same in assy sequence, while (+60K, -0K) is quoted in requirements and other doc. Ensure consistency through all doc.
Materials
F: Edms 3061760 tech specs: pp3-4 "All components will be constructed from 304 SS". At the same time below: skin constructed of stainless steel plate and external and internal ribs constructed out of steel plate.
| C: Keep consistency of material definition being 304 SS . | Shall ensure stainless steel is consistent through documentation
Handling, Packing and Shipping
F: Edms 3061760 tech specs: pp3-3 "All components must be packaged to ensure materials will conform to specifications upon shipment, delivery, and storage at SDWF."; p5-5: "The shipping/packaging plan will be submitted with the proposal to verify that the packaging will facilitate transport down the shaft. This primarily is a verification that any cross bracing for stability will not exceed the envelope required to fit in the shaft and that the lifting point are free. " The tech spec does not include any information / requirement about the ross shaft envelope.
| Q18: Why only specify a verification of a proposed plan? Why not specify in this specs the overall packing envelope compatible with Ross Shaft envelope and the accessibility to the lifting fixtures so the packing can be designed accordingly? | Shall investigate the rigging/handling plan at the farsite surface cage. A Ross Cage dimension appendix document to be provided.
F: Edms 3061760 tech specs: pp3-4 "Develop any specialized tooling and procedures required to realize and handle the HD cold box structure assemblies." Package and ship completed product components such that the products conform to specifications.
| Q19: Not clear which specs to conform to ? Means preservation of integrity of delivered structures? | Yes
R: Include spec of handling restriction (configuration not permitted) as stated in edms 2825997 - Eng Note: pp.41 Handling results: (see 2D- Handling section above)
Applicable codes and standards
| Q20: Why is ASTM A320 for SS bolting at low temp. not listed in specs (see Q16)? | Shall add A320 to the applicable specifications for hardware
QC / acceptance tests
F: Edms 3061760 tech specs: pp3-4 Hold/witness points may include dry fitting and load test.
| Q20: Do you plan to include an interfaces dimensional check ? | Yes
| Q21: Edms 3061760 tech specs: pp3-4 "additional details of this scope": would you add a specific mention about interfaces to be as specified in dwg, together with eventual control point ? | Yes
C: Consider using (and sharing with manufacturer) the cold-box-assy-interfaces document and ICD listing all interfaces with their specifications, to be used as a support for interfaces inspection at eventual witness point?
F: Edms 3061760 tech specs: pp3-4 "Required documentation" is not detailed.
| Q21: Refers to specification by applicable standard ? | Shall be included in procurment specification, as pre-award, post-award, and upon completion
F: Edms 3061760 tech specs: pp5-5 Quality: the QA/QC Plan is submitted by the contractor with its bid, for approval by LBNF/DUNE
F: Edms 3061760 tech specs: pp5-6 "Tests shall be identified as individual activities in the specifications." "The Customer shall identify critical tests (e.g., x-rays, dye penetrant tests) that must be included as schedule activities."
| Q22: Please clarify. Are the tests implicit, i.e. refers to specification by applicable standard ? Or is it a free proposal by contractor to be approved by LBNF/DUNE? Or defined by customer ? Why not specifying customer "critical tests" at this stage in the specs? How to compare bids if tests are not specified ? | Developing QA source inspection document with our quality team
| Q23: For weld : what is the specified extend of control and which controls ? | Follow AWS structural welding code
F: edms 2825997 - Eng Note: pp.22 : "We must ensure the bolt holes can align properly with respect to the clearances/tolerances specified and provided by the manufacturer. Edms 3061760 tech specs: pp5-6 "The coldboxes will be test assembled at the factory to ensure all the pieces fit together and the tolerance on the door will enable the box to be sealed."
C: the definition of the dry assy test and control points may be more specific e.g. quoting eng note: "bolt holes can align properly with respect to the clearances/tolerances specified"
| Q24: Is the dry assy test considered the Factory Acceptance Test? Is it coupled/ included in Final Inspection where all the QC documents will be collected? | Yes
C: Inspections, hold/witness points, test, documentation, certificates are mentioned at various places in the tech specs. An annexed summary table listing all hold/witness points, description, milestone, and documentation to be delivered at each point would be more specific and helpful to get a clear and global view of the QC.
Installation procedure
F: Assy procedure includes high level assy points and procedures. It is understood it will be refined at a later stage about safety (e.g. welding with insulation in place, confined space …), securing items in place, eventual control points other than leak test, final rotation and installation in place against cryostat wall.
C: see questions/comments in sections above: handling and leak tightness / seal

## Shishir S.
Section | Comment | Response | Reference images
2D Drawings
6, 7, 8 | Rib end detail might be useful | We included note, "Grind ends of ribs as needed for a good fit"
6, 7, 8, 14, 15 | Rib end detail might be useful
6, 7, 8, 14, 15 | Rib opposite end detail might be useful
4, 5, 13 | Flange to Flange Weld detail and Flange to Shell weld detail seems missing | Shall add explicit weld callout
4, 5, 13 | Flange to Shell dimensional reference seems missing | Shall add additional dimensions to drawing asembly |  | Same as cell 42
10, 19, 1 | Rib to Rib and Rib to Shell weld detail seems missing | Shall add explicit weld callout
10 | Rib to Shell dimensional reference seems missing | Shall add additional dimensions to drawing asembly |  | Same as cell E44
2 | Feed through holes on the shell and their locations details seems missing | Located on coldbox-quad-2 sheet 2/5
2 | Including the secure mechanism detail in the plan will prevent the need for modifications to the certified component, thereby avoiding additional engineering efforts.
Engineering Note
1 | What is an appropriate contact condition between the door and the quad flange interface? Frictional or Bonded? | frictional (0.2)
LC1 | Does the term "eccentric loading case" specifically refer to the transient condition in which the APA load is fully transferred from the crane to the monorail system? | APA load applied to end of beam
LC1 | What mechanism or structural feature restricts the movement of the APA toward the access door during load transfer? | N/a
LC1 | What alignment controls prevent misalignment between the monorail and telescopic rails as the APA transitions? If misalignment occurs, what is the allowable step-up tolerance for the trolley? | Shall have a bolted connection once monorail from telescoping bridge crane is contracted.
LC1 | Can the telescopic beam bump into monorail and make the system instable? | Shall survey monorail telescoping beam during commisioning stage of bridge crane in cleanroom
LC1 | How does the deformation due to weight affect the weld at the feed-throughs? | N/a, displacements small
LC3 | Does the 45-degree tilt of the Cold Box impact the column top plate or column connecting plate, potentially introducing additional stresses due to the weight of the monorail assembly attached to these columns? | Shall bolt columns/monorail in vertical orientation or provide additional bracing during rotatioin
Technical Specification
| Are we going to suggest a specific ASME standard such as B30.11 for the monorail design? | N/a
The vendor shall not make a cost intensive change without consulting the stake holders
Feed-through welds
Trailing trolley fully transferred on monorail
APA Sliding towards the door

## Jim M.
Section | Comment | Response
Technical Specification | Coldbox Assembly drawing FD-1_COLDBOX_DRAWING_PACKAGE_READY_FOR_APPROVALS_AUG_27-2024.pdf does not identify any locking means for the ⅝ inch Hex Nut, Bolt and Flat Washer. The ½ inch Hex Nut, Bolt, Flat Washer and Helical Spring Lock Washer assembly does not provide a locking means. The Department of Navy and NASA have done a study and determined that the use of a split lock washer does not provide a locking means. The preferred lock washer is the Belleville or similar lock washer.

## Kevin F.
Section | Comment | Response
Technical Specification | We only want to see the test reports of passing inspections. No sense being notified of failing equipment since they need to have everything passing by final inspection. I added a separate section on how to control nonconforming items.
5.3 Control of Nonconforming Equipment and Materials
| When the Subcontractor identifies equipment or material as nonconforming to the specifications and/or drawing requirements, the nonconforming condition shall be documented, segregate the nonconforming item, disposition the nonconforming condition, perform the applicable corrective action and verify that it has been performed and close out the nonconformance once the disposition has been verified as being satisfactorily completed. Dispositions of Accept as Is and Repair will require approval by the LBNF/DUNE Project personnel. For Accept as Is and Repair dispositions a technical justification shall be provided showing that although the equipment will not meet the specification requirements, it still meets its intended form, fit and function. Rework and Scrap dispositions do not require LBNF/DUNE Project approval since the reworked item is brought into compliance with the specifications and/or drawings and the scrapped items are removed from the fabrication. A list of Nonconformances shall be maintained for review by the LBNF/DUNE Project. | Adding section to technical specification Quality section