## Slide 1: Muon Campus Shutdown Report
Jim Morgan
Friday 09:00 Shutdown Meeting
October 4, 2024

## Slide 2: Muon Campus status
Study – Alternative M5 optics
Study – M1-M3 Optics
ESS2 is at NWA and has begun high voltage conditioning
  Target voltage is 100 kV, is expected to take several weeks
  Vacuum is presently around 1E-8 Torr
D30 downstream mechanical about to begin
  Key Q205 part (mounting plate assembly) was received this week
Mu2e Extinction Collimators and magnet staked out by Alignment
Leaking Delivery Ring D5SD15 sextupole was replaced
Domestic water leaks near AP-0 adjacent to Transport berm
Muon LCW resistivity continues to be poor
BTW temperature problems was resolved last Friday
Attempted to begin Kirk Key Disconnect repair, had difficulties
  Existing mounting holes for cylinders not sized properly and inconsistent
Hope to begin replacement of some power supply circuit breakers soon
Prototype ESS2 will need to be removed from DR prior to running beam
  Related to buyback accounting between Mu2e Project and AD spares funds
  Hope that operational ESS2 will be ready for installation in early November
  Will evaluate options if operational ESS2 is delayed significantly
AP-0 A/C work paused, blamed on badging issues

## Slide 3: Muon LCW resistivity over the past four weeks
LCW polish resistivity
LCW resistivity

## Slide 4: ESS2 conditioning at NWA
Voltage
Vacuum
Current
Spark Detector

## Slide 5: Mu2e upstream Extinction Monitor Collimator
Existing concrete
Concrete poured
after installation

## Slide 6: Upstream Extinction Monitor Collimator

## Slide 7: Upcoming work
Main worklist items and other upcoming work
  Repair Kirk Key hardware on disconnects, requires more modifications to disconnect
  Replace several power supply circuit breakers and some primary wiring
  Remove D40 shielding blocks for moving 8Q24’s in and out of tunnel
  Install rad hard 8Q24 at Q205, send uninstalled 8Q24 to TD for rad hard water lines
  Q205 vacuum pipe replacement to simplify vacuum connection to ELAM
  Profilometer extraction profile monitor vacuum Tee installed upstream of ELAM
  Unroll ELAM? (was rolled 24 mr to improve g-2 extraction trajectory)
  Install additional steel shielding above ECMAG
  Several alignment tasks including replacement Q205 and M4 WCM
  Repair of domestic water line breaks near AP-0 may have disturbed Transport berm
  Prepare to install Mu2e Extinction Monitor Collimator in Absorber area
  M4 Final Focus vacuum installation, A/C dipole installation
  ESS1 and ESS2 septum stand motion-control improvements
  Hope to finish operational ESS2 and install it in tunnel late in shutdown
ESS2 (operational version)
  Continue high voltage conditioning (duration ~4 weeks)
AP-0 A/C work paused again
Jerry is out of town this afternoon and through the weekend