## Slide 1: Cryo Assembly, Cold Mass Status
A. Vouris
Cryo Assy L2 Meeting
Oct. 14, 2024

## Slide 2: Cold Mass Tooling & Design Status
WorkStation Equipment
  Status
    End Can
      Lead End – Pallet jack cart drawings and note for 2nd unit
      Order additional pallet jack w/ extended forks
    Cold Mass drawings
      Working through redlines for next batch of drawing mods
        dwg for revisions: Magnet Model updated in all drawings
          F10103605 – Released/printed
          F10151260 – Released/printed
          F10178090 – Capillary tube install update – Released & submitted revision ticket for missed corrections
          F10172809 – Pressure test drawing default updates from lower dwg
          Update Drawing tree - as needed after final revisions
          Fixture for Beam Tube – completed, released and in machining
    Additional tooling:
      Metrology: adjust/re-survey Welding Station – Rails adjusted and now w/in +/- .04

## Slide 3: Cold Mass Tooling & Design Status
Cold Mass
  Engr Analysis & Note:
    Traveler updates
    Changes to End Cover Tooling made – Note updated. Spacers and counterweight made.

## Slide 4: Cold Mass Tooling & Design Status
Cold Mass
  CM-02 – CA-02 at test stand (IB1)- See C. Orozco talk
  CM-03 – CA-03 – See C. Orozco talk
  CM-04 (MQXFA-08b & MQXFA-14b)
    longitudinal welding complete – repairs needed prior to UT but after end can welding
    Circumferential Welding Complete
    Metrology survey completed post welding of both End Cover (waiting for report)
    Survey group inspecting Inspection table and saddles today
  CM-05 Alignment Station set up (MQXFA07b & 15)
    2nd Shell fit up complete
    Awaiting Pre-weld Survey: OD measurements weld joint gap measurements, etc.
  CM-06 (MQXFA13b & MQXFA __)
    Shells washed.
    Awaiting to finish shell inspection: thickness & arc length
    Magnet MQXFA13b in receiving inspection

## Slide 5: Cold Mass Tooling & Design Status
Cold Mass (cont)
  Production Series
    Final 2 items for procurement:
      Tack Blocks – in QCR reviewed and dispositioned – Reviewed rework of first few and passed. Vendor will proceed to repair the balance including second batch returned
      Lower Saddles, cold mass – reviewing QCRs
      Production N-lines - leak test 100% complete
      Formed Plates in stock at FNAL for CM-07, -08, -09 and -10 (ready for machining)
      CM-05 – CM-10 & Spare Tack blocks – received and in stock
      CM-06 thru CM-10 & Spare Shell Plate Machining PO (REQ #355609)
        CM-06 shells rec’d
        CM-07 Shells – 1 shell roughed 2nd in roughing process
      Shell Plate Forming: CM-10 Picked up & back in storage
        Next 4 plates for forming waiting for plates from CERN
      CM-05 – CM-10 Lower plates – Received all 30 pcs
        First 5 units: QC complete, QCR reviewed, picked 3 units for Unit 4 on Insp. Table
        Final 25 units rec’d and in QC
        All threads being chased/checked for fit & reamed holes checked for fit up with pin

## Slide 6: Cold Mass Tooling & Design Status
Cold Mass (cont)
  Production Series
    Magnet 16
      In temp storage (ICB)
    Q1-Q3 Bus production
      Units up to CM-10 plus 1 spare are complete
      1 Spare Buss – PO being processed, waiting for housing parts