## Slide 1
Project Activities for MSD
Mayling Wong-Squires
AD Operations Friday 9am Meeting
13 September 2024

## Slide 2: LBNF Primary Vacuum and Magnet Installation Kevin Duel, Ty Funk, Jason Morin, Kathrine Laureto, Scott Oplt, Will Derylo, Dan Vrbos
Primary Vacuum
  Kicker ceramic beam tube TiN coating
    Waiting for 12” long tube samples from vendor
  Drawings and models for relocation of MI/RR components in progress
  Updating magnet models and drawings with new beam tube design
Magnet Installation
  Preparing for installation plan preliminary peer review on Tuesday 10/22 (equipment, procedures, etc)
  Installation procedures written for dipoles, quads, and correctors
  Corrector magnet stand drawings updated for prototype procurement
  Screw jacks for dipole prototype req submitted
  NuMI quad magnet retrieval procedures drafted
    ~9 NuMI quads will be re-purposed for LBNF
  Primary Beam Enclosure dipole stand design drawings in progress, engineering note updated and awaiting review

## Slide 3: PIP-II BTL Collimators Bob Donahue
PRR deliverables are complete
  Engineering note approved and released
  All drawings released
  Procurement packages identified
PRR deliverables in progress
  Writing Statement of Work (SOW) for each procurement
Horizontal collimator
Vertical collimator