## Slide 1
Main Injector Shutdown Status
Denton Morris, Marty Murphy
AD/MI 9 o’clock
October 18, 2024

## Slide 2
Tunnel Work
10/18/2024
MI Department Meeting | D. Morris
2
MI-8 Collimator installation
Jaws are welded
Tunnel cable terminations completed in the tunnel
in progress in the service building
RF Dual PA cavity upgrades (3 stations)
Upgrading four modulators (one spare)
NOTE: Unable to test any RF until KRS pulsed power
and LCW returns. Then need ~3 weeks for testing
MI-40 LCW pump #1 has a bad bearing and #3 has a leaking seal.
The check valve has also failed.
Move MI quads based on previous high field orbit
Q211 stand needs attention for it to be aligned
MI tunnel cleaning 75% complete

## Slide 3
Plan
10/18/2024
MI Department Meeting | D. Morris
3
Yesterday
Recore MI-10 and MI-8
Search and Secure MI-8 and MI-10
Today Safety system testing MI-8 and MI-10
Return MI-8 to shutdown keys for remainder of Iron Work effort
Testing for BNB running
End of MI-8 line and BNB line power supply testing
Need MI-10 secure and ESS permit
Need LCW for almost all of it

## Slide 4
Conventional and Pulsed MI Power Outages
10/18/2024
MI Department Meeting | D. Morris
4
Please report any additional MI outages to the MCR.