## Slide 1: Muon Campus Shutdown Report
Jim Morgan
Friday 09:00 Shutdown Meeting
October 18, 2024

## Slide 2: Muon Campus status
Study – Alternative M5 optics
Study – M1-M3 Optics
ESS2 has been high voltage conditioning at NWA
  Beneficial spark on Sunday, good progress since then
  Current draw improved dramatically after spark
D30 downstream mechanical work in progress
  D40 blocks removed and Forklift lowered Thursday
  Grinding with rad tech coverage today, welding on Monday
  Forklift required for Q205 removal temporarily moved from MI-8
Another domestic water leak north of AP-0, will need berm topo after repairs
Muon Campus Feeder 24 power outage this morning
Rapid increase in upstream AP-30 and MI-8 sump activity on Wednesday
Muon LCW resistivity continues to be poor
Attempted to begin Kirk Key Disconnect repair, had difficulties
  Existing mounting holes for cylinders not sized properly and inconsistent
Hope to begin replacement of some power supply circuit breakers soon
Prototype ESS2 will need to be removed from DR prior to running beam
  Related to buyback accounting between Mu2e Project and AD spares funds
  Still hope that operational ESS2 will be ready for installation late this month
AP-0 A/C work paused, blamed on badging issues

## Slide 3: ESS2 conditioning at NWA
Voltage
Vacuum
Current
Spark Detector
Operational Voltage

## Slide 4: Upstream AP-30 and MI-8 sump activity

## Slide 5: Location of upstream AP-30 and MI-8 sumps
Tunnel ceiling leak

## Slide 6: Upcoming work
Main worklist items and other upcoming work
  Repair Kirk Key hardware on disconnects, requires more modifications to disconnect
  Replace several power supply circuit breakers and some primary wiring
  Install rad hard 8Q24 at Q205, send uninstalled 8Q24 to TD for rad hard water lines
  Q205 vacuum pipe replacement to simplify vacuum connection to ELAM
  Profilometer extraction profile monitor vacuum Tee installed upstream of ELAM
  Unroll ELAM? (was rolled 24 mr to improve g-2 extraction trajectory)
  Install additional steel shielding above ECMAG
  Several alignment tasks including replacement Q205 and M4 WCM
  Repair of domestic water line breaks near AP-0 may have disturbed Transport berm
  Prepare to install Mu2e Extinction Monitor Collimator in Absorber area
  M4 Final Focus vacuum installation, A/C dipole installation
  ESS1 and ESS2 septum stand motion-control improvements
  Hope to finish operational ESS2 and install it in tunnel prior to turn-on
Second Muon Campus Feeder 24 outage planned for Tuesday
ESS2 (operational version)
  Continue high voltage conditioning at NWA
  Deliver to tunnel in late October or early November?
AP-0 A/C work paused again (18 months since start)