## Slide 1: Muon Campus Shutdown Report
Jim Morgan
Friday 09:00 Shutdown Meeting
October 25, 2024

## Slide 2: Muon Campus status
Study – Alternative M5 optics
Study – M1-M3 Optics
ESS2 has been high voltage conditioning at NWA
  Reached target voltage of 90 kV on Thursday
  Finishing with several days at operational voltage of 86 kV
D30 downstream mechanical work in progress
  Short delay due to problem with parts for special Q205 vacuum pipe
  Old Q205 has been removed, new rad hard Q205 being readied for installation
  Need to return forklift to MI-8 Line for Collimator work
Muon Campus Feeder 24 power outage Tuesday morning
Increased upstream AP-30 and MI-8 sump activity continued
Another domestic water leak north of AP-0, will need berm topo after repairs
Muon LCW resistivity continues to be poor
Attempted to begin Kirk Key Disconnect repair, had difficulties
  Existing mounting holes for cylinders not sized properly and inconsistent
Replacement of some power supply circuit breakers awaiting electricians
Prototype ESS2 will need to be removed from DR prior to running beam
  Related to buyback accounting between Mu2e Project and AD spares funds
  Operational ESS2 expected to be ready for transport to tunnel next week
AP-0 A/C work paused, blamed on badging issues

## Slide 3: ESS2 conditioning at NWA
Voltage
Vacuum
Current
Spark Detector
Operational Voltage

## Slide 4: Q205 rad hard quad swap

## Slide 5: Upstream AP-30 and MI-8 sump activity
Transport “Y” sump
MI-8 828 “B” sump
AP-30 upstream sump
MI-8 828 “A” sump

## Slide 6: Location of Muon Campus sump pumps
Currently has level monitor
Currently does not have monitor
MI-8 sumps
MI-8 823 sump

## Slide 7: Location of upstream AP-30 and MI-8 sumps
MI-8 823 sump
Upstream AP-30 sump
discharge to header
In tunnel
Old “Reverse
Injection
Line” sump
Transport “Y” sump
Minimal flow
from ditch
Sump discharge

## Slide 8: Reverse Injection Line that predated Antiproton Source

## Slide 9: Upcoming work
Installation of ESS2 (operational version) and rad hard Q205
  High voltage conditioning at NWA scheduled to end Monday
  Prototype ESS2 will be uninstalled in D30 and prepared for transport to A0
  Delivery of Operational ESS2 from NWA to tunnel scheduled for next Wednesday
  Install rad hard 8Q24 at Q205, send uninstalled 8Q24 to TD for rad hard upgrade
  Q205 vacuum pipe replacement to simplify vacuum connection to ELAM
  Profilometer extraction profile monitor vacuum Tee installed upstream of ELAM
  Unroll ELAM? (was rolled 24 mr to improve g-2 extraction trajectory)
Other upcoming work
  Install additional steel shielding above ECMAG
  Several alignment tasks including replacement Q205 and M4 WCM
  Repair of domestic water line breaks near AP-0 may have disturbed Transport berm
  ESS1 and ESS2 septum stand motion-control improvements
  Repair Kirk Key hardware on disconnects, requires more modifications to disconnect
  Replace several power supply circuit breakers and some primary wiring
  Prepare to install Mu2e Extinction Monitor Collimator in Absorber area
  M4 Final Focus vacuum installation, A/C dipole installation
More Muon Campus Feeder 24 outages planned over the next two months
AP-0 A/C work paused again (18 months since start)