## Slide 1
Main Injector Shutdown Status
Denton Morris, Marty Murphy
AD/MI 9 o’clock
October 25, 2024

## Slide 2
Tunnel Work
10/25/2024
MI Department Meeting | D. Morris
2
MI-8 Collimator installation has stopped
Preparing to install vacuum spool piece and surrounding
magnets.
This will potentially gain us ~2 weeks of BNB beam
RF Dual PA cavity upgrades (3 stations) continues
Upgrading four modulators (one spare)
NOTE: Unable to test RF until KRS pulsed power
and LCW returns. Then need ~3 weeks for testing
MI tunnel cleaning finished yesterday

## Slide 3
Additional Work
10/25/2024
MI Department Meeting | D. Morris
3
Closed up MI heat exchangers
Configured all pond systems into bypass except MI-30 heat exchanger
Turned on MI magnet system pond pumps in 60 hp mode.
Does not include MI-8, MI-52, MI-62 or MI-60 RF systems
Magnet LCW pumps will be turning on today

## Slide 4
Plan
10/25/2024
MI Department Meeting | D. Morris
4
Yesterday
Re-cored MI-8
Search and Secure MI-8
Today
Booster CDC and logic testing
No access into MI-8 until after testing is completed
Turning on magnet LCW pumps
Next Monday:
Re-core MI-20 to 62 to Operational keys
Followed by search and secure for safety system testing
Search and Secure MI-10 in preparation for BNB power
supply testing
Testing for BNB running
End of MI-8 line and BNB line power supply testing
Need MI-10 secure, ESS permit, LCW, and ALL LOCKS OF MI-10 LOTO Box.

## Slide 5
Conventional and Pulsed MI Power Outages
10/25/2024
MI Department Meeting | D. Morris
5
Please report any additional MI outages to the MCR.