## Slide 1: Cryo Assembly, Cold Mass Status
A. Vouris
Cryo Assy L2 Meeting
Oct. 28, 2024

## Slide 2: Cold Mass Tooling & Design Status
WorkStation Equipment
  Status
    End Can
      Lead End – Pallet jack cart drawings and note for 2nd unit
      Order additional pallet jack w/ extended forks
    Cold Mass drawings
      Working through redlines for next batch of drawing mods
        dwg for revisions: Magnet Model updated in all drawings
          F10151260 – Released/printed – redlined to clear welding station saddles
          F10178090 – Capillary tube install update – Released & submitted revision ticket for missed corrections
          F10172809 – Pressure test drawing default updates from lower dwg
          Update Drawing tree - as needed after final revisions
    Additional tooling:
      End cover tooling – 1 set complete, need set for opposite end

## Slide 3: Cold Mass Tooling & Design Status
Cold Mass
  Engr Analysis & Note:

## Slide 4: Cold Mass Tooling & Design Status
Cold Mass
  CM-02 – CA-02 at test stand (IB1)- See C. Orozco talk
  CM-03 – CA-03 – See C. Orozco talk
  CM-04 (MQXFA-08b & MQXFA-14b)
    longitudinal welding complete – repairs needed prior to UT but after end can welding
    Circumferential Welding Complete
    Survey inspection of welding table and saddles complete
    Metrology survey completed post welding and move to Inspection station – result look good
    Welding FSI targets today/tomorrow w/ Metrology
    Long seam dressing to begin this week after FSI is complete
    Welding Qa side tee branches complete
    Flare flanges for Ht-X’s – welded on End Cover side only (need to adjust HT-X prior to finishing welds on tube to flare side)
    Beam tube Flares – awaiting SSW removal
  CM-05 Alignment Station set up (MQXFA07b & 15)
    2nd Shell fit up pre-weld survey inspection complete- review survey report
  CM-06 (MQXFA13b & MQXFA __)
    Shells washing complete
    Awaiting shell inspection: thickness & arc length

## Slide 5: Cold Mass Tooling & Design Status
Cold Mass (cont)
  Production Series
    Final 2 items for procurement:
      Tack Blocks – in QCR reviewed and dispositioned – Reviewed rework of first few and passed. Vendor will proceed to repair the balance including second batch returned
      Lower Saddles, cold mass – reviewing QCRs
      Production N-lines - leak test 100% complete
      Formed Plates in stock at FNAL for CM-07, -08, -09 and -10 (ready for machining)
      CM-05 – CM-10 & Spare Tack blocks – received and in stock
      CM-06 thru CM-10 & Spare Shell Plate Machining PO (REQ #355609)
        CM-07 Shells – both shells rough machined & moving to final machining stage this week waiting for status report
      Shell Plate Forming: CM-10 Picked up & back in storage
        Next 4 plates for forming waiting for plates from CERN
      CM-05 – CM-10 Lower plates – Received all 30 pcs
        First 5 units: received and in stock (3 in use for CM-04)
        Final 25 units rec’d and inspected – will review QCR
        All threads being chased/checked for fit & reamed holes checked for fit up with pin

## Slide 6: Cold Mass Tooling & Design Status
Cold Mass (cont)
  Production Series
    Magnet 16
      In temp storage (ICB)
    Q1-Q3 Bus production
      Units up to CM-10 plus 1 spare are complete
      1 Spare Buss – housing parts received and inspected – waiting QCR review