## Slide 1
FAST / IOTA Shutdown 2023-2024
IPI installation and commissioning is our highest priority. All hands on deck.
Electric: -IOTA Bake GFCI breakers (AD/Web 57570) (no movement)
-ESB Laser Lab electrical work complete (Need Interlocks)
ES&H: -LLSS in OSC Mode / New South Gate / IPI Interlock Install
IPI: -ESB 480/120VAC Electric Req “being generated” (T&M???)
  -Beamline under vacuum. DON’T TOUCH beamline stuff
Water: -Chiller repair finished next week (PO717353)
-ICW “LOMO” period end of October
AD Shutdown’24: 11/5 KRS. Winding down -Support groups are freeing up
Inform FAST RunCo of any work on the accelerator—
IRR and DOE/GARD visit went well (still much work to be done)

## Slide 2: ISD Updates for NML
Roll Up Door - In Progress (168986) assigned to the “Schedule Planner”.
Clean Y-Strainer – Hold (181072) due to Abatement??
High Bay Lighting LED Upgrade – In Progress (163677)
Catwalk Electrical Receptacle Changeouts – In Progress (189398)
Bathroom drains leaking – 2-week downtime to fix. In Progress
ESB HVAC – In Progress –pushed back to 01/27/2025.
Cleanup in mech rooms – Working with Clorica to clean up. In Progress
Tire Marks from lift – Electrical group to pay for this? In Progress
Mechanical Checks on critical water connections – DONE
Window Cleaning - In Discussion. FY2025
Exterior Lights (both inground and canopy) - waiting on quote. On Hold
Lightbulbs: Bathroom, FCR, ESB, 9WX,… Being scheduled™

## Slide 3
FAST shutdown continues through CY24 for the installation of the IOTA Proton Injector (IPI). Thanks to support groups…
IRR and DOE/GARD visit went well
IPI beamline complete. At UHV levels
Spect. & Allison Scanner analyzing species from Source
IPI HLRF build out is close to completion, but stopped
  IPI HLRF is now our Critical Path to IPI start-up
  IPI LCW build-out needs completion to commission beamline
LCW work has resumed
LCW chiller repair still waiting on vendor (scheduled 11/06)
Thanks to OPS for help and vigilantes on ACNET alarms
— Contact FAST Coordinator with any work or access requests —
FAST / IOTA 9:00 Report