## Slide 1: Muon Campus Shutdown Report
Jim Morgan
Friday 09:00 Ops Meeting
November 8, 2024

## Slide 2: Muon Campus status
Study – Alternative M5 optics
Study – M1-M3 Optics
Rigging work through D40 Hatch completed on Wednesday
  Operational ESS2 transported from NWA to tunnel
  Prototype ESS2 removed from tunnel and transported to A0 Clean Room
  Original Q205 quadrupole transported to Technical Division for rad hardening
  Forklift returned to MI-8 Line for Collimator work
D30 downstream mechanical work in progress
  ESS2 installed in Delivery Ring, vacuum connections next
  Preparing for installation of Rad Hard Q205 installation
Domestic water line repair north of AP-0 and over MI-8 Line
  Small sinkhole observed last Friday in area to be excavated
Transport Enclosure secured for Booster CDC testing
Muon LCW resistivity continues to be poor
AP-0 A/C work paused, reasons unclear

## Slide 3: Operational ESS2 being lowered into tunnel

## Slide 4: Operational ESS2 set in Delivery Ring

## Slide 5: Domestic water line replacement
Domestic water
leak/repair zone

## Slide 6: PIP-II Beam Transport Line Civil Construction
Booster Phase 2
Begins January 2028
Booster Phase 1
Begins January 2027
F-Sector Reconfiguration Task Force
Dean Still - Chairman
Mark Austin, Maurice Ball, Steve Dixon, Cons Gattuso, Michael Geelhoed, Stan Johnson, Jim Morgan, Denton Morris, Michael Olander, Dan Vrbos
Muon Campus
cryo header

## Slide 7: PIP-II Beam Transport Line Civil Construction
Booster Phase (2027-2028)
Linac Phase (in progress)
Main Ring Road excavation begins January 2025
Main Ring Road

## Slide 8: Lab Schedule

## Slide 9: Upcoming work
D30 installation work continues
  Getting operational ESS2 under vacuum highest priority, alignment on Monday
  Rad Hard Q205 and special vacuum pipe
  Vacuum Tee for Profilometer
  Plan to leave 24 mr roll on ELAM in as it improves extraction trajectory
More Muon Campus Feeder 24 outages planned over the next two months
Domestic water line repairs south of AP-0 may have compromised shielding
  Close to Transport berm, need to survey to understand if berm was disturbed
  Excavation for new water line crossed over MI-8 tunnel
Other upcoming work
  Install additional steel shielding above ECMAG
  Several survey & alignment tasks including Q205, ESS1, ESS2 and M4 WCM
  Repair Kirk Key hardware on disconnects, requires more modifications to disconnect
  Replace several power supply circuit breakers and some primary wiring
  Prepare to install Mu2e Extinction Monitor Collimator in Absorber area
  M4 Final Focus vacuum installation, A/C dipole installation
Hope to begin preparing for beam operation later this month