## Slide 1: Cryo Assembly, Cold Mass Status
A. Vouris
Cryo Assy L2 Meeting
Nov. 11, 2024

## Slide 2: Cold Mass Tooling & Design Status
WorkStation Equipment
  Status
    End Can
      Lead End – Pallet jack cart drawings and note for 2nd unit
      Order additional pallet jack w/ extended forks
    Cold Mass drawings
      Working through redlines for next batch of drawing mods
        dwg for revisions: Magnet Model updated in all drawings
          F10151260 – Released/printed – redlined to clear welding station saddles
          F10178090 – Capillary tube install update – Released & submitted revision ticket for missed corrections
          F10172809 – Pressure test drawing default updates from lower dwg
          Update Drawing tree - as needed after final revisions
    Additional tooling:
      End cover tooling – 1 set complete for one station

## Slide 3: Cold Mass Tooling & Design Status
Cold Mass
  Engr Analysis & Note:

## Slide 4: Cold Mass Tooling & Design Status
Cold Mass
  CM-04 (MQXFA-08b & MQXFA-14b)
    Survey inspection of welding table and saddles complete
    Metrology survey completed post welding and move to Inspection station – result look good – received final Metrology Report today
    Long seam dressing complete – Circ weld grinding 70% complete – CWI to review after lunch
    UT Scheduled end of this week (Nov. 14-15)
    HT-X Flare flanges – need to align HT-X for final welding (CERN sending tooling)
    Beam tube Flare welding – next
    Capillary work prep to follow beam tube welding completion
    Test Nozzle welding prep
  CM-05 Alignment Station set up (MQXFA07b & 15)
    Shell shim sizing review complete – Ok to weld
    Welding scheduled for week of Nov. 18-20
  CM-06 (MQXFA13b & MQXFA __)
    Shells washing complete
    Awaiting shell inspection: thickness & arc length in process
  CM-07
    Shells at Machine shop – 1st is partially machined (1st sect. of 3) both shells projected to ship before Holiday

## Slide 5: Cold Mass Tooling & Design Status
Cold Mass (cont)
  Production Series
    Final 2 items for procurement:
      Tack Blocks – in QCR reviewed and dispositioned – Reviewed rework of first few and passed. Vendor will proceed to repair the balance including second batch returned
      Lower Saddles, cold mass – reviewing QCRs
      Production N-lines - leak test 100% complete
      Formed Plates in stock at FNAL for CM-07, -08, -09 and -10 (ready for machining)
      CM-05 – CM-10 & Spare Tack blocks – received and in stock
      CM-06 thru CM-10 & Spare Shell Plate Machining PO (REQ #355609)
        CM-07 Shells – final machining stage
        CM-08 shells swap approx. week of Dec. 2
      Shell Plate Forming: CM-10 Picked up & back in storage
      CM-05 – CM-10 Lower plates – Received all 30 pcs
        First 5 units: received and in stock (3 used for CM-04)
        Final 25 unit inspected – reviewing QCR this week
        All threads being chased/checked for fit & reamed holes checked for fit up with pin

## Slide 6: Cold Mass Tooling & Design Status
Cold Mass (cont)
  Production Series
    Magnet 16
      In temp storage (ICB)
    Q1-Q3 Bus production
      Units up to CM-10 plus 1 spare are complete
      1 Spare Buss – housing parts received and inspected